## Actuator Valve
PROGRESS OM ACTUATOR VALVE UNIT 1
|  | FINISH | IN PROGRESS | TOTAL | % IN PROGRESS | % FINISH
|  | 0 | 0 | 0 | 0 | 0
AREA | DESCRIPTION | FINISH DATE | PIC | PROGRESS | % | REMARKS
BOILER | ACTUATOR FEED WATER CONTROL VALVE 100% 10LAB30AA210 |  | AMP | FINISH | 100 |  | 1
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | TRUE
BOILER | ACTUATOR FEED WATER CONTROL VALVE 30% 10LAB30AA210 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | ACTUATOR DESH-1 SPRAY WATER ISOLATION |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | ACTUATOR DESH-1 SPRAY WATER CONTROL VALVE |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | ACTUATOR DESH-2 SPRAY WATER ISOLATION |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | ACTUATOR DESH-2 SPRAY WATER CONTROL VALVE |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | ACTUATOR FUEL COAL GATE VALVE 1 (MFT-1) 10HHE11AA01 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | ACTUATOR FUEL COAL GATE VALVE 2 (MFT-2) 10HHE12AA01 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
ID FAN | ACTUATOR IGV ID FAN 1 10HNC01EX001 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
ID FAN | ACTUATOR IGV ID FAN 2 10HNC01EX002 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
ID FAN | ACTUATOR INLET ID FAN 1 MOV 10HNA61AA001 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
ID FAN | ACTUATOR INLET ID FAN 2 MOV 10HNA62AA001 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
ID FAN | ACTUATOR OUTLET ID FAN 1 MOV 10HNA71AA001 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
ID FAN | ACTUATOR OUTLET ID FAN 2 MOV 10HNA72AA001 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
STG | BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L MOV 10LAE10AA110 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
STG | ACTUATOR MAIN STEAM LINE (START UP BYPASS) TO DEAERATOR PRDS I/L CV 10LBH10AA210 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
STG | ACTUATOR BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L CV 10LAE10AA210 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
STG | ACTUATOR TURBINE EXTRACTION III TO DEAERATOR CV 10LBD10AA210 |  | AMP | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
STG | MOV DISCHARGE BFP-1 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
STG | MOV DISCHARGE BFP-2 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | TRUE
| FUNCTION TEST |  | AMP |  | FALSE
PA FAN | ACTUATOR MOV OUTLET PA FAN 1 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
PA FAN | ACTUATOR MOV PA FAN 1 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
BOILER | ACTUATOR ISOLATION STARTUP VENTING BOILER |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR IGV SA FAN 1 10HLB01EX001 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR IGV SA FAN 2 10HLB02EX001 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR IGV SA CONTROL DAMPER 10HLA25AA010 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR IGV SUB 1 10HJL10AA010 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR IGV SUB 2 10HJL11AA010 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR BED MATERIAL DISCHARGE GATE VALVE 10ETG31AA01 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR VALVE DRAIN SOOT BLOWER 10HCB10AA101 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | FALSE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | COMBUSTER ASH DRAIN 1 (BED ASH COLLER DRAIN) MOV 10HHC01AA001 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | FALSE
| FUNCTION TEST |  | AMP |  | FALSE
BOILER | SOOT BLOWER CONTROL VALVE |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | SOOT BLOWER ISOLATION VALVE MOV 10HCB10AA001 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | MS START UP VENT VALVE (REG) MOV 10LBA21AA011 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | MS START UP VENT VALVE (ISO) MOV 10LBA21AA001 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | ACTUATOR SOOT BLOWER CV 10HCB10EX001 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
BOILER | ACTUATOR DAMPER SEALPOT BLOWER 1 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
BOILER | ACTUATOR DAMPER SEALPOT BLOWER 2 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
BOILER | COMBUSTER ASH DRAIN 1 (BED ASH COLLER DRAIN) MOV 10HHC01AA001 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
BOILER | FLUIDIZING VALVE BED MATERIAL |  | MSW | IN PROGRESS | 50
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
BOILER | FLUIDIZING VALVE LIMESTONE 1&2 |  | MSW | IN PROGRESS | 50
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
DRUM | ACTUATOR STEAM DRUM VENTING ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
DRUM | ACTUATOR STEAM DRUM MOV VENTING VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
DRUM | ACTUATOR STEAM DRUM CBD ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
DRUM | ACTUATOR STEAM DRUM MOV CBD CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
DRUM | ACTUATOR STEAM DRUM IBD ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
DRUM | ACTUATOR STEAM DRUM MOV IBD CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
PA FAN | ACTUATOR MOV OUTLET PA FAN 2 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
PA FAN | ACTUATOR MOV PA FAN2 |  | MSW | IN PROGRESS | 50
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
SA FAN | ACTUATOR MOV OUTLET SA FAN 1 |  | MSW | IN PROGRESS | 50
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
SA FAN | ACTUATOR MOV OUTLET SA FAN 2 |  | MSW | IN PROGRESS | 50
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
STG | ACTUATOR HP BYPASS CONTROL VALVE 10LBF10AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | FALSE
| FUNCTION TEST |  | AMP |  | FALSE
STG | ACTUATOR CONDENSATE PUMP RECIRCULATION CONTROL VALVE 10LCA31AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | ACTUATOR MAIN CONDENSATE CONTROL VALVE 10LCA30AA240 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | ACTUATOR GLAND STEAM PRESSURE CONTROL VALVE 10MAW10AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | ACTUATOR GLAND STEAM TEMP. CONTROL VALVE 10LCE10AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | FALSE
| FUNCTION TEST |  | AMP |  | FALSE
STG | ACTUATOR BYPASS SPRAY CONTROL VALVE 10LCE40AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | AMP |  | FALSE
| FUNCTION TEST |  | AMP |  | FALSE
STG | CEP DISCHARGE VALVE |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
STG | DISCHARGE, SUCTION & VENTING VALVE VACUM PUMP-1 & 2 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | MOV MAIN STEAM DRAIN STG-2 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | DRAIN OF ESV 10MAL10AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | DRAIN OF CV CHAMBER 10MAL10AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | TURBINE DRAIN VALVE AFTER FIRST STAGE 10MAL30AA210 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | TURBINE DRAIN VALVE 10MAL40AA210 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
STG | TURBINE DRAIN VALVE 10MAL50AA210 |  | MSW | IN PROGRESS | 50
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | TRUE
| FUNCTION TEST |  | MSW |  | FALSE
STG | TURBINE DRAIN VALVE 10MAL60AA210 |  | MSW | IN PROGRESS | 50
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
STG | TURBINE DRAIN VALVE 10MAL70AA210 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | FALSE
STG | CONTROL VALVE LPH-2 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | CONTROL VALVE LPH-1 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | MOV TURBINE STEAM EXTRACTION-1 & 2 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
STG | ACTUATOR MOV TURBINE STOP VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
STG | ACTUATOR MOV PREHEATING 1 TURBINE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
STG | ACTUATOR MOV PREHEATING 2 TURBINE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
STG | ACTUATOR ON/OFF NRV STEAM EXTRACTION 1, 2, 3 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
STG | ACTUATOR ON/OFF VALVE CEP-1 & CEP-2 |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SUB BURNER 1 VALVE 10HJN11AA003 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
SUB | ACTUATOR SUB BURNER 2 VALVE 10HJN12AA003 |  | MSW | SCHED-OK | 0
| GENERAL INSPECTION, CALIBRATION AND CLEANING |  | MSW |  | FALSE
| FUNCTION TEST |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER MAIN LDO LINE CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 1 LDO LINE CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 1 ATOMISING AIR LINE CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 2 LDO LINE CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 2 ATOMISING AIR LINE CONTROL VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 1 ATOM AIR ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 1 LDO ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 1 SCAVENGING VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 2 ATOM AIR ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 2 LDO ISOLATION VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
SUB | ACTUATOR SKID BURNER 2 SCAVENGING VALVE |  | MSW | SCHED-OK | 0
| General Inspection, Calibration and Cleaning |  | MSW |  | FALSE
| Function Test |  | MSW |  | FALSE
BOILER | ACTUATOR MOV INLET ECONOMIZER |  | MSW | FINISH | 100
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | TRUE
BOILER | ACTUATOR MOV RECIRCULATION ECONOMIZER |  | MSW | FINISH | 100
| General Inspection, Calibration and Cleaning |  | MSW |  | TRUE
| Function Test |  | MSW |  | TRUE
PT MAKMUR SEJAHTERA WISESA
2 X 30 MW COAL FIRED POWER PLANT
EIC SECTION