## UPDATE U1
PROGRESS JOBS OUTAGE UNIT 1
SECTION ELECTRIC, INSTRUMENT, CONTROL (EIC)
|  |  |  | SCHED-OK | FINISH | IN PROGRESS | TOTAL | % FINISH | ∑ PROGRES
|  |  |  | 26 | 3 | 35 | 64 | 36.11% | 2311.2427
| NO | NO WO | JOB DESCRIPTION | DATED |  |  | STATUS | PIC | N Task | %Estimation | SCOPE | REMARKS
|  |  |  | SCHEDULE | ACTUAL START | FINISH
| 1 | WO-100826-0012 | OM EIC Y1 UNIT COMMON COOLING TOWER FAN 1 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 9 | 88.8889 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | [6 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | [6 empty] | TRUE
|  |  | INSPECTION BEARING DAN REPLACEMENT (JIKA DIPERLUKAN) | [6 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | [6 empty] | TRUE
|  |  | INSPECTION TAHANAN WINDING | [6 empty] | TRUE
|  |  | INSPECTION COOLING FAN | [6 empty] | TRUE
|  |  | INSPECTION TERMINASI | [6 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | [6 empty] | TRUE
|  |  | SOLO RUN | [6 empty] | FALSE
| 2 | WO-100826-0013 | OM EIC Y1 UNIT COMMON COOLING TOWER FAN 2 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 9 | 88.8889 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION BEARING DAN REPLACEMENT (JIKA DIPERLUKAN) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | SOLO RUN | 22/8/2026 | [5 empty] | FALSE
| 3 | WO-100826-0014 | OM EIC Y1 UNIT COMMON MAIN COOLING WATER PUMP 1 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 9 | 77.7778 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | SOLO RUN | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 22/8/2026 | [5 empty] | FALSE
| 4 | WO-100826-0015 | OM EIC Y1 UNIT COMMON MAIN COOLING WATER PUMP 2 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 9 | 77.7778 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | SOLO RUN | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 22/8/2026 | [5 empty] | FALSE
| 5 | WO-100826-0016 | OM EIC Y1 UNIT COMMON AUXILIARY COOLING WATER PUMP 1 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 9 | 55.5556 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION BEARING & REPLACEMENT | 22/8/2026 | [5 empty] | FALSE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 22/8/2026 | [5 empty] | FALSE
| 6 | WO-100826-0017 | OM EIC Y1 UNIT COMMON AUXILIARY COOLING WATER PUMP 2 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 9 | 66.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION BEARING & REPLACEMENT | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 22/8/2026 | [5 empty] | FALSE
| 7 | WO-100826-0160 | OM EIC Y1 UNIT 1 INDUCED DRAUGHT FAN 1 | 22/8/2026 |  |  | IN PROGRESS | M. Toher | 14 | 61.5385 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | UNIT 1 INDUCED DRAUGHT FAN 1 INLET GATE ACTUATOR MOV 20HNA61AA001 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | UNIT 1 INDUCED DRAUGHT FAN 1 OUTLET GATE ACTUATOR MOV 20HNA71AA001 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | MSW20HNC10-M103:UNIT 1 INDUCED DRAUGHT FAN 1 MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REPOSISI MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | DISSASEMBLY COVER FAN DAN COVER BEARING SISI DE DAN NDE | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPEKSI DAN CLEANING BALL BEARING DE DAN NDE (REPLACE BEARING IF NEEDED) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REGREASING BEARING DAN PENGUKURAN TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUKURAN TAHANAN BELITAN | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 INDUCED DRAUGHT FAN 1 IGV 10HNC01EX001 | 22/8/2026 |  |  |  | AMP |  | TRUE
|  |  | INLET ID FAN 1 PRESSURE TRANSMITTER 10HNA61CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INLET PRESSURE ESP PRESSURE TRANSMITTER 10HNA41CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | OUTLET PRESSURE ESP PRESSURE TRANSMITTER 10HNA41CP002 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | SOLO RUN | 22/8/2026 |  |  |  | MSW |  | FALSE
| 8 | WO-100826-0161 | OM EIC Y1 UNIT 1 INDUCED DRAUGHT FAN 2 | 22/8/2026 |  |  | SCHED-OK | M. Toher | 12 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | UNIT 1 INDUCED DRAUGHT FAN 2 INLET ACTUATOR MOV 20HNA62AA001 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | UNIT 1 INDUCED DRAUGHT FAN 2 OUTLET ACTUATOR MOV 20HNA72AA001 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | MSW20HNC10-M203:UNIT 1 INDUCED DRAUGHT FAN 2 MOTOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | REPOSISI MOTOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | DISSASEMBLY COVER FAN DAN COVER BEARING SISI DE DAN NDE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPEKSI DAN CLEANING BALL BEARING DE DAN NDE (REPLACE BEARING IF NEEDED) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | REGREASING BEARING DAN PENGUKURAN TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUKURAN TAHANAN BELITAN | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | UNIT 1 INDUCED DRAUGHT FAN 2 IGV 10HNC01EX002 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | SOLO RUN | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | INLET ID FAN 2 PRESSURE TRANSMITTER 10HNA62CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 9 | WO-100826-0020 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 1 | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 10 | 80 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | REPOSISI MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | DISSASEMBLY COVER FAN DAN COVER BEARING SISI DE DAN NDE | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPEKSI DAN CLEANING BALL BEARING DE DAN NDE | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REPLACE BEARING IF NEEDED | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REGREASING BEARING DAN PENGUKURAN TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUKURAN TAHANAN BELITAN | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 PRIMARY AIR FAN 1 IGV | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | UNIT 1 PRIMARY AIR FAN 1 OUTLET MOV | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | PA FAN 1 OUTLET PRESSURE TRANSMITTER 10HLB03CP001 | 22/8/2026 |  |  |  | JAPA |  | TRUE
| 10 | WO-100826-0021 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 1 LUBE OIL SYSTEM | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 6 | 66.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20HLN20-M101:UNIT 1 PRIMARY AIR FAN 1 LUBE OIL PUMP 1 MOTOR (STAND BY) | 22/8/2026 | [5 empty] | TRUE
|  |  | MSW20HLN20-M102:UNIT 1 PRIMARY AIR FAN 1 LUBE OIL PUMP 2 MOTOR (MAIN) | 22/8/2026 | [5 empty] | TRUE
|  |  | 20HLB01CP104: LO HEADER PRESSURE LOW ALARM FOR PA FAN-1 | 22/8/2026 | [5 empty] | TRUE
|  |  | 20HLB01CP103: PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-1 START | 22/8/2026 | [5 empty] | TRUE
|  |  | 20HLB01CP102: PRESSURE SWITCH TO START LO PA FAN-1 STANDBY PUMP | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB01CP101: DP SWITCH ACROSS LO TANK FOR PA FAN-1 | 22/8/2026 | [5 empty] | FALSE
| 11 | WO-100826-0022 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 2 | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 10 | 80 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | REPOSISI MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | DISSASEMBLY COVER FAN DAN COVER BEARING SISI DE DAN NDE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPEKSI DAN CLEANING BALL BEARING DE DAN NDE | 22/8/2026 | [5 empty] | TRUE
|  |  | REPLACE BEARING IF NEEDED | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING BEARING DAN PENGUKURAN TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | PENGUKURAN TAHANAN BELITAN | 22/8/2026 | [5 empty] | TRUE
|  |  | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | UNIT 1 PRIMARY AIR FAN 2 IGV | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HLB20AA202:UNIT 1 PRIMARY AIR FAN 2 OUTLET MOV | 22/8/2026 | [5 empty] | FALSE
|  |  | PA FAN 2 OUTLET PRESSURE TRANSMITTER 10HLB04CP001 | 22/8/2026 | [5 empty] | TRUE
| 12 | WO-100826-0014 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 2 LUBE OIL SYSTEM | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 6 | 83.3333 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20HLN20-M201:UNIT 1 PRIMARY AIR FAN 2 LUBE OIL PUMP 1 MOTOR (STAND BY) | 22/8/2026 | [5 empty] | TRUE
|  |  | MSW20HLN20-M202:UNIT 1 PRIMARY AIR FAN 2 LUBE OIL PUMP 2 MOTOR (MAIN) | 22/8/2026 | [5 empty] | TRUE
|  |  | 20HLB02CP104: LO HEADER PRESSURE LOW ALARM FOR PA FAN-2 | 22/8/2026 | [5 empty] | TRUE
|  |  | 20HLB02CP103: PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-2 START | 22/8/2026 | [5 empty] | TRUE
|  |  | 20HLB02CP102: PRESSURE SWITCH TO START LO PA FAN-2 STANDBY PUMP | 22/8/2026 | [5 empty] | TRUE
|  |  | MSW20HLN20CL201:UNIT 1 PRIMARY AIR FAN 2 LUBE OIL TANK LEVEL SWITCH | 22/8/2026 | [5 empty] | FALSE
| 13 | WO-100826-0014 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 1 | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 10 | 77.7778 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | REPOSISI MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | DISSASEMBLY COVER FAN DAN COVER BEARING SISI DE DAN NDE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPEKSI DAN CLEANING BALL BEARING DE DAN NDE | 22/8/2026 | [5 empty] | TRUE
|  |  | REPLACE BEARING IF NEEDED | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING BEARING DAN PENGUKURAN TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | PENGUKURAN TAHANAN BELITAN | 22/8/2026 | [5 empty] | TRUE
|  |  | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | UNIT 1 SECONDARY AIR FAN 1 OUTLET MOV | 22/8/2026 | [5 empty] | FALSE
|  |  | SA FAN 1 OUTLET PRESSURE TRANSMITTER 10HLB01CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | UNIT 1 SECONDARY AIR FAN 1 IGV SA FAN 1 20HLB01EX001 | 22/8/2026 | [5 empty] | FALSE
| 14 | WO-100826-0014 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 1 LUBE OIL SYSTEM | 22/8/2026 |  |  | SCHED-OK | Aidhiy | 7 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20HLN10-M101:UNIT 1 SECONDARY AIR FAN 1 LUBE OIL PUMP 1 MOTOR (STAND BY) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HLN10-M102:UNIT 1 SECONDARY AIR FAN 1 LUBE OIL PUMP 2 MOTOR (MAIN) | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB02CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-1 | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB05CP104: LO HEADER PRESSURE LOW ALARM FOR SA FAN-1 | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB05CP103: PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-1 START | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB05CP102: PRESSURE SWITCH TO START LO SA FAN-1 STANDBY PUMP | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB05CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-1 | 22/8/2026 | [5 empty] | FALSE
| 15 | WO-100826-0014 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 2 | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 10 | 70 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | REPOSISI MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | DISSASEMBLY COVER FAN DAN COVER BEARING SISI DE DAN NDE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPEKSI DAN CLEANING BALL BEARING DE DAN NDE | 22/8/2026 | [5 empty] | TRUE
|  |  | REPLACE BEARING IF NEEDED | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING BEARING DAN PENGUKURAN TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | PENGUKURAN TAHANAN BELITAN | 22/8/2026 | [5 empty] | TRUE
|  |  | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | UNIT 1 SECONDARY AIR FAN 2 OUTLET MOV | 22/8/2026 | [5 empty] | FALSE
|  |  | UNIT 1 IGV SA FAN 2 10HLB01EX001 | 22/8/2026 | [5 empty] | FALSE
|  |  | SA FAN 2 OUTLET PRESSURE TRANSMITTER 10HLB02CP001 | 22/8/2026 | [5 empty] | FALSE
| 16 | WO-100826-0014 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 2 LUBE OIL SYSTEM | 22/8/2026 |  |  | SCHED-OK | Jhon FM | 6 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20HLN10-M201:UNIT 1 SECONDARY AIR FAN 2 LUBE OIL PUMP 1 MOTOR (STAND BY) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HLN10-M202:UNIT 1 SECONDARY AIR FAN 2 LUBE OIL PUMP 2 MOTOR (MAIN) | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB06CP104: LO HEADER PRESSURE LOW ALARM FOR SA FAN-2 | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB06CP103: PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-2 START | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB06CP102: PRESSURE SWITCH TO START LO SA FAN-2 STANDBY PUMP | 22/8/2026 | [5 empty] | FALSE
|  |  | 20HLB06CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-2 | 22/8/2026 | [5 empty] | FALSE
| 17 | WO-100826-0014 | OM EIC Y1 UNIT 1 COAL FEEDER NO 1 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 13 | 92.3077 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR DRAG CHAIN | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION FRAME MOTOR ROTARY AIR LOCK | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION OF MFT ACTUATOR 10HHE11AA01 | 22/8/2026 | [5 empty] | FALSE
| 18 | WO-100826-0014 | OM EIC Y1 UNIT 1 COAL FEEDER NO 2 | 22/8/2026 |  |  | IN PROGRESS | Aidhiy | 13 | 92.3077 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR DRAG CHAIN | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION FRAME MOTOR ROTARY AIR LOCK | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION OF MFT ACTUATOR 10HHE12AA01 | 22/8/2026 |  |  |  | AMP |  | FALSE
| 19 | WO-100826-0014 | OM EIC Y1 UNIT 1 LDO START-UP BURNER 1 | 22/8/2026 |  |  | IN PROGRESS | Jhon FM | 18 | 11.1111 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION OF IGNITER GUN | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | INSPECTION OF START UP BURNER SKID DEVICE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | LDO PRESSURE BEFORE MTV SWITCH 10HJF11CP301 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ATOM AIR INLET PRESSURE LOW SWITCH 10HJN11CP301 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | LDO PRESSURE LOW TRIP FOR SUB 1 SWITCH 10HJF11CP302 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ATOM AIR PRESSURE LOW TRIP FOR SUB 1 SWITCH 10HJN11CP302 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | LDO PRESSURE HIGH TRIP FOR SUB 1 SWITCH 10HJF11CP303 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | SCANNER AIR PRESSURE OK 1 SWITCH 10HJG69CP301 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | SCANNER AIR PRESSURE OK 2 SWITCH 10HJG69CP302 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER MAIN LDO LINE CONTROL VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 1 LDO LINE CONTROL VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 1 ATOMISING AIR LINE CONTROL VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SUB BURNER 1 VALVE 10HJN11AA003 | 22/8/2026 |  |  | AMP |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 1 ATOM AIR ISOLATION VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 1 LDO ISOLATION VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 1 SCAVENGING VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ATOM AIR PRESSURE AFTER SUB 1 TRANSMITTER 10HJN11CP001 | 22/8/2026 |  |  | JAPA |  |  | TRUE
|  |  | LDO PRESS AFTER SUB1 FVC TRANSMITTER 10HJF11CP001 | 22/8/2026 |  |  | JAPA |  |  | TRUE
| 20 | WO-100826-0014 | OM EIC Y1 UNIT 1 LDO START-UP BURNER 2 | 22/8/2026 |  |  | SCHED-OK | Jhon FM | 13 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION OF IGNITER GUN | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | INSPECTION OF START UP BURNER SKID DEVICE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | LDO PRESSURE LOW TRIP FOR SUB 2 SWITCH 10HJF12CP302 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ATOM AIR PRESSURE LOW TRIP FOR SUB 2 SWITCH 10HJN12CP302 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | LDO PRESSURE HIGH TRIP FOR SUB 2 SWITCH 10HJF12CP303 | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ATOM AIR PRESSURE AFTER SUB 2 TRANSMITTER 10HJN12CP001 | 22/8/2026 |  |  | JAPA |  |  | FALSE
|  |  | LDO PRESS AFTER SUB2 FCV TRANSMITTER 10HJF12CP001 | 22/8/2026 |  |  | JAPA |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 2 LDO LINE CONTROL VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 2 ATOMISING AIR LINE CONTROL VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 2 ATOM AIR ISOLATION VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 2 LDO ISOLATION VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SKID BURNER 2 SCAVENGING VALVE | 22/8/2026 |  |  | MSW |  |  | FALSE
|  |  | ACTUATOR SUB BURNER 2 VALVE 10HJN12AA003 | 22/8/2026 |  |  | AMP |  |  | FALSE
| 21 | WO-100826-0014 | OM EIC Y1 UNIT 1 SEALPOT BLOWER NO 1 | 22/8/2026 |  |  | FINISH | Ferryus | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGGANTIAN BEARING (JIKA DIPERLUKAN) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | SEALPOT BLOWER PRESS OUTLET TRANSMITTER 10HLB41CP001 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | P&S BLOWER PRESS OUTLET TRANSMITTER 10QEB20CP001 | 22/8/2026 |  |  |  | JAPA |  | TRUE
| 22 | WO-100826-0014 | OM EIC Y1 UNIT 1 SEALPOT BLOWER NO 2 | 22/8/2026 |  |  | FINISH | Ferryus | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 | [5 empty] | TRUE
|  |  | PENGGANTIAN BEARING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION COOLING FAN | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 | [5 empty] | TRUE
| 23 | WO-100826-0014 | OM EIC Y1 UNIT 1 ELECTROSTATIC PRECIPITATOR 1-6 | 22/8/2026 |  |  | IN PROGRESS | M. Iqbal | 19 | 26.3158 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20HDE10-M101:UNIT 1 ESP RAPPING MOTOR (GDRM) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M102:UNIT 1 ESP RAPPING MOTOR (CERM-1) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M103:UNIT 1 ESP RAPPING MOTOR (CERM-2) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M104:UNIT 1 ESP RAPPING MOTOR (CERM-3) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M105:UNIT 1 ESP RAPPING MOTOR (CERM-4) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M106:UNIT 1 ESP RAPPING MOTOR (CERM-5) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M107:UNIT 1 ESP RAPPING MOTOR (CERM-6) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M108:UNIT 1 ESP RAPPING MOTOR (EERM-1) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M109:UNIT 1 ESP RAPPING MOTOR (EERM-2) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M110:UNIT 1 ESP RAPPING MOTOR (EERM-3) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M120:UNIT 1 ESP RAPPING MOTOR (EERM-4) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M130:UNIT 1 ESP RAPPING MOTOR (EERM-5) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20HDE10-M140:UNIT 1 ESP RAPPING MOTOR (EERM-6) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | UNIT 1 ESP TRAFO 1 (GENERAL CLEANING, INSPEKSI, IR TEST) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 ESP TRAFO 2 (GENERAL CLEANING, INSPEKSI, IR TEST) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 ESP TRAFO 3 (GENERAL CLEANING, INSPEKSI, IR TEST) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 ESP TRAFO 4 (GENERAL CLEANING, INSPEKSI, IR TEST) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 ESP TRAFO 5 (GENERAL CLEANING, INSPEKSI, IR TEST) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | UNIT 1 ESP TRAFO 6 (GENERAL CLEANING, INSPEKSI, IR TEST) | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 24 | WO-100826-0014 | OM EIC Y1 UNIT 1 BOILER FEED PUMP 1 | 22/8/2026 |  |  | IN PROGRESS | Yoga | 21 | 33.3333 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION BEARING DAN REPLACEMENT (JIKA DIPERLUKAN) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION COOLING FAN | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | MSW20LAC10-M101:MOV DISCHARGE BFP-1 | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | MSW20LAC10AA104:UNIT 1 BOILER FEED PUMP 1 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10AA105:UNIT 1 BOILER FEED PUMP 1 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CG101:UNIT 1 BOILER FEED PUMP 1 LIMIT SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | 20LAC10CP101:UNIT 1 BOILER FEED PUMP 1 PRESSURE DIFFERENTIAL SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT101:UNIT 1 BOILER FEED PUMP 1 R PHASE WDG TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT102:UNIT 1 BOILER FEED PUMP 1 B PHASE WDG TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT103:UNIT 1 BOILER FEED PUMP 1 B PHASE WDG TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT104:UNIT 1 BOILER FEED PUMP 1 B NDE MOTOR BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT105:UNIT 1 BOILER FEED PUMP 1 B NDE MOTOR BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT106:UNIT 1 BOILER FEED PUMP 1 B NDE PUMP BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT107:UNIT 1 BOILER FEED PUMP 1 B NDE PUMP BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10GH101:UNIT 1 BOILER FEED PUMP 1 FCMA PANEL | 22/8/2026 |  |  |  | MSW |  | FALSE
| 25 | WO-100826-0014 | OM EIC Y1 UNIT 1 BOILER FEED PUMP 2 | 22/8/2026 |  |  | IN PROGRESS | Yoga | 21 | 33.3333 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION BEARING DAN REPLACEMENT (JIKA DIPERLUKAN) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION COOLING FAN | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION TERMINASI | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | MSW20LAC10-M201:MOV DISCHARGE BFP-2 | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | MSW20LAC10AA204:UNIT 1 BOILER FEED PUMP 2 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10AA205:UNIT 1 BOILER FEED PUMP 2 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CG201:UNIT 1 BOILER FEED PUMP 2 LIMIT SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CP201:UNIT 1 BOILER FEED PUMP 2 PRESSURE DIFFERENTIAL SWITCH | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT201:UNIT 1 BOILER FEED PUMP 2 R PHASE WDG TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT202:UNIT 1 BOILER FEED PUMP 2 B PHASE WDG TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT203:UNIT 1 BOILER FEED PUMP 2 B PHASE WDG TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT204:UNIT 1 BOILER FEED PUMP 2 B NDE MOTOR BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT205:UNIT 1 BOILER FEED PUMP 2 B NDE MOTOR BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT206:UNIT 1 BOILER FEED PUMP 2 B NDE PUMP BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10CT207:UNIT 1 BOILER FEED PUMP 2 B NDE PUMP BEARING TEMPERATURE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20LAC10GH201:UNIT 1 BOILER FEED PUMP 2 FCMA PANEL | 22/8/2026 |  |  |  | MSW |  | FALSE
| 26 | WO-100826-0014 | OM EIC Y1 UNIT 1 FEED WATER LINE | 22/8/2026 |  |  | IN PROGRESS | M. Toher | 10 | 30 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | UNIT 1 FEED WATER INLET ECONOMIZER MOTORIZED VALVE MOTOR 100% 10LAB30AA220 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | UNIT 1 FEED WATER INLET ECONOMIZER MOTORIZED VALVE ISOLATION VALVE | 22/8/2026 |  |  |  | AMP |  | TRUE
|  |  | UNIT 1 FEED WATER INLET ECONOMIZER MOTORIZED VALVE MOTOR 30% 10LAB30AA210 | 22/8/2026 |  |  |  | AMP |  | TRUE
|  |  | UNIT 1 FEED WATER INLET ECONOMIZER MOTORIZED VALVE ISOLATION VALVE | 22/8/2026 |  |  |  | AMP |  | TRUE
|  |  | ACTUATOR BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L CV 10LAE10AA210 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L MOV 10LAE10AA110 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | DISTRIBUTOR LINE TO FEEDWATER TRANSMITTER 10LAB30CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INLET FEEDWATER PRESSURE TRANSMITTER 10HAC90CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INLET FEEDWATER FLOW TRANSMITTER 10HAC90CF001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INLET FEEDWATER FLOW TRANSMITTER 10HAC90CF002 | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 27 | WO-100826-0014 | OM EIC Y1 UNIT 1 DESH SUPERHEATER LINE 1 | 22/8/2026 |  |  | IN PROGRESS | M. Toher | 3 | 66.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | CALIBRATION/FUNCTION TEST SPRAY CONTROL VALVE 10LAE10EX001 | 22/8/2026 | [5 empty] | TRUE
|  |  | CALIBRATION/FUNCTION ISOLATION (ON/OFF) VALVE | 22/8/2026 | [5 empty] | FALSE
|  |  | DESH 1 SPRAY WATER FLOW TRANSMITTER 10LAE20CF001 | 22/8/2026 | [5 empty] | TRUE
| 28 | WO-100826-0014 | OM EIC Y1 UNIT 1 DESH SUPERHEATER LINE 2 | 22/8/2026 |  |  | IN PROGRESS | M. Toher | 4 | 50 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | DESH 2 SPRAY WATER FLOW TRANSMITTER 10LAE30CF001 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CALIBRATION/FUNCTION TEST SPRAY CONTROL VALVE 10LAE12EX001 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | BEFORE DESH 2 TEMP TRANSMITTER CALIBRATION (20HAH46CT001, 10HAH36CT009, 10HAH36CT009) | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | CALIBRATION/FUNCTION ISOLATION (ON/OFF) VALVE | 22/8/2026 |  |  |  | AMP |  | TRUE
| 29 | WO-100826-0014 | OM EIC Y1 UNIT 1 GENERATOR CIRCUIT BREAKER | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 30 | 10 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION MEKANIK PENGGERAK | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION MOTOR CHARGING | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION BEARING DRIVE RACK OUT/IN | 22/8/2026 | [5 empty] | TRUE
|  |  | REGREASING SOCKET MAIN KONTAK | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION SYSTEM KONTROL | 22/8/2026 | [5 empty] | FALSE
|  |  | TEST TAHANAN KONTAK | 22/8/2026 | [5 empty] | FALSE
|  |  | TEST KESEREMPAKAN | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION TAHANAN ISOLASI KONTAK | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION TAHANAN ISOLASI BUS BAR | 22/8/2026 | [5 empty] | FALSE
|  |  | FUNCTION TEST | 22/8/2026 | [5 empty] | FALSE
|  |  | PENGUKURAN TAHANAN MOTOR CHARGING, CLOSING DAN TRIPPING COIL | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION MODUL CONTROL BREAKER | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION LAMPU SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INDIKATOR DAN LAMPU PANEL SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | PENGETESAN POWER DC UNTUK SUPPLY CONTROL 6,3 KV SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION HEATER CUBICLE SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION DAN CLEANING TERMINASI SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION DAN PENGUJIAN RELAY PROTEKSI SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION GROUNDING SYSTEM SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION TAHANAN ISOLASI BUS BAR SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION CT & PT SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | FUNCTION TEST SWITCH GEAR GCB | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION HEATER SYSTEM | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION DISPLAY BREAKER | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION HEATER BUSDUCT | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION SILICA BUSDUCT | 22/8/2026 | [5 empty] | FALSE
|  |  | CEK KEBOCORAN DAN KELEMBAPAN BUSDUCT | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION CONTACT RESISTANCE BUSDUCT | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION ISOLATION RESISTANCE BUSDUCT | 22/8/2026 | [5 empty] | FALSE
| 30 | WO-100826-0014 | OM EIC Y1 UNIT 1 GENERATOR | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 40 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | DISASSEMBLY BRACKET GENERATOR SISI FRONT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | DISASSEMBLY BRACKET GENERATOR SISI REAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | DISASSEMBLY OIL DEFLECTOR BEARING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CLEANING BODY GENERATOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CLEANING OIL DEFLECTOR BEARING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CLEANING BOLT & NUT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION OIL DEFLECTOR BEARING 3 & 4 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION SHROUD & FAN BLADE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION STATOR GENERATOR (IR, PI) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ROTOR GENERATOR (IR, PI, RSO) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION VISUAL ISOLATOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ROTOR GROUNDING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION VISUAL FLEXIBLE ISOLATOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION BRUSH GROUNDING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN ISOLASI GENERATOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION HEATER NEUTRAL SIDE CUBICLE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION HEATER LINE SIDE CUBICLE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | ASSEMBLY OIL DEFLECTOR BEARING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | ASSEMBLY BRACKET SISI FRONT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | ASSEMBLY BRACKET SISI REAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUKURAN TAHANAN RESISTOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION & CLEANING PT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION & CLEANING CT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUKURAN TAHANAN ISOLASI PERMANEN MAGNET GENERATOR (PMG) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION DIODA EXCITER PERMANEN MAGNET GENERATOR (PMG) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TERMINASI PERMANEN MAGNET GENERATOR (PMG) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION GROUNDING SYSTEM PERMANEN MAGNET GENERATOR (PMG) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION FUSE PANEL PERMANEN MAGNET GENERATOR (PMG) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION DISCONNECTING SWITCH NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TRAFO NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ISOLATOR BUSHING NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TERMINASI NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | TEST TAHANAN ISOLASI NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION HEATER BUSDUCT NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION SILICA BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CEK KEBOCORAN DAN KELEMBAPAN BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION CONTACT RESISTANCE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ISOLATION RESISTANCE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CLEANING | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 31 | WO-100826-0014 | OM EIC Y1 UNIT 1 AUXILIARY TRANSFORMER 2 | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 24 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION ISOLATOR BUSHING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TERMINASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CLEANING BUSHING CONNECTION HV & LV | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION DAN CLEANING PANEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION SILICAGEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION GROUNDING SYSTEM | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION KEBOCORAN MINYAK TRAFO | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PROTECTIVE DEVICE TEST DAN RESET TRAFO | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION PANEL TAP CHANGER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN ISOLASI WINDING TRAFO | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | RDS TEST | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MECHANICAL RELAY TEST | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION DISCONNECTING SWITCH NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TRAFO NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ISOLATOR BUSHING NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TERMINASI NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION GROUNDING SYSTEM NETRAL GROUNDING RESISTANCE (NGR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION HEATER BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION SILICA BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CEK KEBOCORAN DAN KELEMBAPAN BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION CONTACT RESISTANCE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ISOLATION RESISTANCE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CLEANING | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 32 | WO-100826-0014 | OM EIC Y1 UNIT 1 6.6KV MEDIUM VOLTAGE STATION BOARDS PANEL | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 15 | 6.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20BBA10GS101:UNIT 1 SWITCHGEAR 6.6KV INCOMING PANEL (MV UAT 2 CB9) | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | MSW20BBA10GS102:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 1 PA FAN 1 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS103:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 2 PA FAN 2 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS104:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 3 SA FAN 1 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS105:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 4 SA FAN 2 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS106:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 5 ID FAN 1 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS107:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 6 ID FAN 2 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS108:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 8 BF PUMP 1 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS109:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 9 BF PUMP 2 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS110:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 7 CW PUMP 3 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS111:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 11 CW PUMP 4 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS112:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 12 CW PUMP 5 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS113:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 TRAFO FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | UNIT 1 SWITCHGEAR 6,6KV UNIT 1 ADAPTER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20BBA10GS114:UNIT 1 SWITCHGEAR 6,6KV METERING (L10) | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 33 | WO-100826-0014 | OM EIC Y1 UNIT 1 MEDIUM VOLTAGE STATION BOARDS COMMON | 22/8/2026 |  |  | SCHED-OK | Aidhiy | 10 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 1 | 22/8/2026 | [5 empty] | FALSE
|  |  | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 2 | 22/8/2026 | [5 empty] | FALSE
|  |  | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 3 | 22/8/2026 | [5 empty] | FALSE
|  |  | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 4 | 22/8/2026 | [5 empty] | FALSE
|  |  | SWITCHGEAR 6,6KV UNIT 1 OUTGOING TRAFO 1 | 22/8/2026 | [5 empty] | FALSE
|  |  | SWITCHGEAR 6,6KV UNIT 1 OUTGOING TRAFO 2 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00BBA10CE201:MV COMMON METERING | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00BBA10GH201:SWITCHGEAR 6.6KV COMMON BUSTIE RIGHT | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00BBA10GH202:SWITCHGEAR 6.6KV COMMON BUSTIE LEFT | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00BBA10GH203:SWITCHGEAR 6.6KV COMMON TRAFO FEEDER | 22/8/2026 | [5 empty] | FALSE
| 34 | WO-100826-0014 | OM EIC Y1 UNIT 1 MAIN TURBINE | 22/8/2026 |  |  | SCHED-OK | M. Toher | 42 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP001) | 22/8/2026 | [5 empty] | FALSE
|  |  | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP002) | 22/8/2026 | [5 empty] | FALSE
|  |  | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP003) | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR TURBINE EXTRACTION III TO DEAERATOR CV 10LBD20AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR MOV TURBINE STOP VALVE UNIT 1 | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR MOV PREHEATING 1 TURBINE | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR MOV PREHEATING 2 TURBINE | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE EXTRACTION II TO LPH2 TEMPERATURE TRANSMITTER (20LBD30CT001) | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE EXTRACTION III TO DEAERATOR TEMPERATURE TRANSMITTER (20LBD20CT001) | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE EXTRACTION I TO LPH1 TEMPERATURE TRANSMITTER (20LBD10CT001) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20MAA10CP302 : UNIT 1 TURBINE BEHIND CONTROL STAGE PRESSURE TRANSMITTER (20MAA10CP001) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20MAA10CP303 : UNIT 1 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP002) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20MAA10CP304 : UNIT 1 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP003) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20MAA10CP305 : UNIT 1 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP004) | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20MAA10CP306 : UNIT 1 TURBINE BEHIND CONTROL STAGE PRESSURE TRANSMITTER (20MAA10CP005) | 22/8/2026 | [5 empty] | FALSE
|  |  | MOV TURBINE STEAM EXTRACTION-1 | 22/8/2026 | [5 empty] | FALSE
|  |  | MOV TURBINE STEAM EXTRACTION-2 | 22/8/2026 | [5 empty] | FALSE
|  |  | MOV MAIN STEAM DRAIN STG-2 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE CASING TEMPERATURE - INSIDE TRANSMITTER 10MAA10CT012 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE CASING TEMPERATURE - CENTER TRANSMITTER 10MAA10CT013 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP TRANSMITTER 10LBD11CT002 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP TRANSMITTER 10LBD11CT001 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR PRDS TO OUTLET EXTRACTION TRANSMITTER 10LBD11CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR PRDS TO OUTLET EXTRACTION II TRANSMITTER 10LBD11CP002 | 22/8/2026 | [5 empty] | FALSE
|  |  | FEEDWATER STORAGE TANK PRESSURE TRANSMITTER 10LAA20CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | CONTROL VALVE LPH-1 | 22/8/2026 | [5 empty] | FALSE
|  |  | CONTROL VALVE LPH-2 | 22/8/2026 | [5 empty] | FALSE
|  |  | LP HEATER 2 TRANSMITTER 10LCC40CL001 | 22/8/2026 | [5 empty] | FALSE
|  |  | LP HEATER 2 TRANSMITTER 10LCC40CL002 | 22/8/2026 | [5 empty] | FALSE
|  |  | LPH II - TUBE SIDE OUTLET TO DEAERATOR TEMP TRANSMITTER 10LCC20CT001 | 22/8/2026 | [5 empty] | FALSE
|  |  | FEEDWATER STORAGE TANK TRANSMITTER 10LAA20CT001 | 22/8/2026 | [5 empty] | FALSE
|  |  | CYCLE MAKE UP PUMP DEAERATOR TRANSMITTER 10HGC20CF001 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR TANK LEVEL 1 TRANSMITTER 10LAA20CL001 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR TANK LEVEL 2 TRANSMITTER 10LAA20CL002 | 22/8/2026 | [5 empty] | FALSE
|  |  | DEAERATOR TANK LEVEL 3 TRANSMITTER 10LAA20CL003 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE EXTRACTION III TO DEAERATOR PRESSURE TRANSMITTER 10LBD20CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE EXTRACTION III TO LPH PRESSURE TRANSMITTER 10LBD30CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE EXTRACTION 1 TO PNEUMATIC OPERATED VALVE PRESSURE TRANSMITTER 10LBS10CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | LP HEATER 1 TRANSMITTER 10LCC30CL001 | 22/8/2026 | [5 empty] | FALSE
|  |  | LP HEATER 1 TRANSMITTER 10LCC30CL002 | 22/8/2026 | [5 empty] | FALSE
|  |  | FLOW CONDESATE TO LP HEATER 1 TRANSMITTER 10LCA40CF001 | 22/8/2026 | [5 empty] | FALSE
|  |  | CONDENSATE TO LP HEATER TRANSMITTER 10LCA40CF001 | 22/8/2026 | [5 empty] | FALSE
| 35 | WO-100826-0014 | OM EIC 1Y FIRE ALARM LOCAL PANEL ( UNIT 1 ) | 22/8/2026 |  |  | SCHED-OK | Jhon FM | 13 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW00CYE10GH101 : ALARM SYSTEM ADMIN BUILDING | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH102 : ALARM SYSTEM DG SHEET | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH103 : PANEL MAIN FIRE ALARM SYSTEM | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH104 : ALARM SYSTEM DM MCC ROOM | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH105 : ALARM SYSTEM CHP MCC | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH106 : ALARM SYSTEM AHP MCC | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH107 : ALARM SYSTEM COOLING WATER | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH108 : ALARM SYSTEM DM/RW.FW TW PUMP | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH109 : ALARM SYSTEM WORKSHOP OFFICE ROOM | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH110 : ALARM SYSTEM SWAS ROOM | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH111 : ALARM SYSTEM STG BUILDING | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH113 : ALARM SYSTEM SWITCHYARD BUILDING | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW00CYE10GH114 : ALARM SYSTEM REMOTE SUBSTATION BUILDING | 22/8/2026 | [5 empty] | FALSE
| 36 | WO-100826-0014 | OM EIC 1Y UNIT 1 PRIMARY AIR FAN LINE | 22/8/2026 |  |  | IN PROGRESS | Ferryus | 4 | 75 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION AND CALIBRATION OXYGEN ANALYZER | 22/8/2026 | [5 empty] | FALSE
|  |  | P.A APH OUTLET FLOW DP TRANSMITTER 10HLA15CF001 | 22/8/2026 | [5 empty] | TRUE
|  |  | P.A APH OUTLET FLOW DP TRANSMITTER 10HLA15CF002 | 22/8/2026 | [5 empty] | TRUE
|  |  | P.A APH OUTLET PRESSURE TRANSMITTER 10HLA15CP001 | 22/8/2026 | [5 empty] | TRUE
| 37 | WO-100826-0014 | OM EIC 1Y UNIT 1 SECONDARY AIR FAN LINE | 22/8/2026 |  |  | IN PROGRESS | Ferryus | 8 | 62.5 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | AIR SUB1 FLOW DP TRANSMITTER 10HJL10CF010 | 22/8/2026 | [5 empty] | FALSE
|  |  | AIR SUB2 FLOW DP TRANSMITTER 10HJL11CF010 | 22/8/2026 | [5 empty] | FALSE
|  |  | SA APH OUTLET FLOW TRANSMITTER 10HLA25CF001 | 22/8/2026 | [5 empty] | FALSE
|  |  | SA APH OUTLET FLOW TRANSMITTER 10HLA25CF002 | 22/8/2026 | [5 empty] | TRUE
|  |  | SA APH OUTLET PRESSURE TRANSMITTER 10HLA25CP001 | 22/8/2026 | [5 empty] | TRUE
|  |  | UNIT 1 SECONDARY AIR FAN IGV SUB 1 20HJL10AA010 | 22/8/2026 | [5 empty] | TRUE
|  |  | UNIT 1 SECONDARY AIR FAN IGV SUB 2 20HJL11AA010 | 22/8/2026 | [5 empty] | TRUE
|  |  | UNIT 1 SECONDARY AIR FAN IGV SA CONTROL DAMPER 20HLA25AA010 | 22/8/2026 | [5 empty] | TRUE
| 38 | WO-100826-0014 | OM EIC Y1 UNIT 1 BOILER DISTRIBUTED CONTROL PANEL | 22/8/2026 |  |  | SCHED-OK | Jhon FM | 3 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PM PC OWS | 22/8/2026 | [5 empty] | FALSE
|  |  | PM PC EWS | 22/8/2026 | [5 empty] | FALSE
|  |  | PM panel RIO | 22/8/2026 | [5 empty] | FALSE
| 39 | WO-100826-0014 | OM EIC Y1 UNIT 1 BOILER DRUM | 22/8/2026 |  |  | IN PROGRESS | Jhon FM | 12 | 50 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION & CALIBRATION STEAM DRUM VENTING ISOLATION VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION & CALIBRATION STEAM DRUM MOV VENTING REGULATING VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION & CALIBRATION STEAM DRUM CBD ISOLATION VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION & CALIBRATION STEAM DRUM MOV CBD REGULATING VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION & CALIBRATION STEAM DRUM IBD ISOLATION VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | INSPECTION & CALIBRATION STEAM DRUM MOV IBD REGULATING VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | DRUM LEVEL TRANSMITTER 10HAD10CL001 | 22/8/2026 | [5 empty] | FALSE
|  |  | DRUM LEVEL TRANSMITTER 10HAD10CL002 | 22/8/2026 | [5 empty] | FALSE
|  |  | DRUM LEVEL TRANSMITTER 10HAD10CL003 | 22/8/2026 | [5 empty] | FALSE
|  |  | DRUM PRESSURE TRANSMITTER 10HAD10CP002 | 22/8/2026 | [5 empty] | FALSE
|  |  | DRUM PRESSURE TRANSMITTER 10HAD10CP003 | 22/8/2026 | [5 empty] | FALSE
|  |  | DRUM PRESSURE TRANSMITTER 10HAD10CP001 | 22/8/2026 | [5 empty] | FALSE
| 40 | WO-100826-0014 | OM EIC Y1 UNIT 1 COMBUSTOR | 22/8/2026 |  |  | IN PROGRESS | M. Toher | 19 | 26.3158 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | COMBUSTER ASH DRAIN 1 (BED ASH COOLER DRAIN) MOV 10HHC01AA001 | 22/8/2026 | [5 empty] | FALSE
|  |  | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 | 22/8/2026 | [5 empty] | FALSE
|  |  | LIMESTONE GATE VALVE | 22/8/2026 | [5 empty] | TRUE
|  |  | ACTUATOR BED MATERIAL DISCHARGE GATE VALVE 10ETG31AA01 | 22/8/2026 | [5 empty] | TRUE
|  |  | COMBUSTOR LOWER PRESSURE TRANSMITTER 10HHC01CP001 | 22/8/2026 | [5 empty] | TRUE
|  |  | MSW20HHC10CP102 : UNIT 1 COMBUSTOR DP WITH GRATE 10HHC01CP011 | 22/8/2026 | [5 empty] | TRUE
|  |  | MSW20HHC10CP103 : UNIT 1 COMBUSTOR UPPER DP 10HHC01CP012 | 22/8/2026 | [5 empty] | TRUE
|  |  | AIR COMBUSTOR AT LEVEL PRES TRANSMITTER 10HHC01CP060 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HHC10CT101 : UNIT 1 COMBUSTOR LOWER TEMP 10HHC01CT011 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HHC10CT102 : UNIT 1 COMBUSTOR LOWER TEMP 10HHC01CT012 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HHC10CT103 : UNIT 1 COMBUSTOR LOWER TEMP 10HHC01CT013 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HHC10CT104 : UNIT 1 COMBUSTOR MIDDLE TEMP 10HHC01CT041 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HHC10CT105 : UNIT 1 COMBUSTOR MIDDLE TEMP 10HHC01CT042 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HHC10CT106 : UNIT 1 COMBUSTOR MIDDLE TEMP 10HHC01CT043 | 22/8/2026 | [5 empty] | FALSE
|  |  | INLET BACKPASS PRESSURE TRANSMITTER 10HBK01CP003 | 22/8/2026 | [5 empty] | FALSE
|  |  | INLET BACKPASS PRESSURE TRANSMITTER 10HBK01CP002 | 22/8/2026 | [5 empty] | FALSE
|  |  | INLET BACKPASS PRESSURE TRANSMITTER 10HBK01CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | BACKPASS PRESSURE AFTER LT SH TRANSMITTER 10HBK01CP030 | 22/8/2026 | [5 empty] | FALSE
|  |  | BACKPASS PRESSURE AFTER ECO TRANSMITTER 10HBK01CP050 | 22/8/2026 | [5 empty] | FALSE
| 41 | WO-100826-0014 | OM EIC Y1 UNIT 1 CYCLONE | 22/8/2026 |  |  | IN PROGRESS | M. Toher | 6 | 16.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20HDF10CP102 : UNIT 1 BACKPASS INLET PRESSURE | 22/8/2026 | [5 empty] | TRUE
|  |  | CYCLONE TO SEALPOT PRESSURE TRANSMITTER 10HDF01CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HDF10CT101 : UNIT 1 BACKPASS INLET TEMPERATURE | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HDF10CT102 : UNIT 1 CYCLONE OUTLET TEMP 10HNA01CT001 | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HDF10CT103 : UNIT 1 BACKPASS INLET TEMPERATURE | 22/8/2026 | [5 empty] | FALSE
|  |  | MSW20HDF10CT104 : UNIT 1 CYCLONE INLET TEMPERATURE | 22/8/2026 | [5 empty] | FALSE
| 42 | WO-100826-0014 | OM EIC Y1 UNIT 1 SEALPOT | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 4 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | ACTUATOR DAMPER SEALPOT BLOWER 1 | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR DAMPER SEALPOT BLOWER 2 | 22/8/2026 | [5 empty] | FALSE
|  |  | CALIBRATION PRESSURE TRANSMITTER | 22/8/2026 | [5 empty] | FALSE
|  |  | CALIBRATION TEMPERATURE TRANSMITTER | 22/8/2026 | [5 empty] | FALSE
| 43 | WO-100826-0014 | OM EIC Y1 UNIT 1 SUPERHEATER SYSTEM LINE | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 12 | 16.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | ERV PRESSURE SWITCH 10LBA20CP502 | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION TEMP TRANSMITTER 10LBA10CT001 | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION TEMP TRANSMITTER 10LBA10CT002 | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION TEMP TRANSMITTER 10LBA10CT003 | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR MAIN STEAM LINE (START UP BYPASS) TO DEAERATOR PRDS I/L CV 10LBH10AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | MS START-UP VENT VALVE (REGULATING) MOV 10LBA21AA011 | 22/8/2026 | [5 empty] | TRUE
|  |  | MS START-UP VENT VALVE (ISOLATION) MOV 10LBA21AA001 | 22/8/2026 | [5 empty] | TRUE
|  |  | MAIN STEAM LIVE PRESSURE TRANSMITTER 10LAB10CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | MAIN STEAM LIVE PRESSURE TRANSMITTER 10LAB10CP002 | 22/8/2026 | [5 empty] | FALSE
|  |  | MAIN STEAM LIVE PRESSURE TRANSMITTER 10LAB10CP003 | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION FLOW TRANSMITTER 10LBA10CF001 | 22/8/2026 | [5 empty] | FALSE
|  |  | INSPECTION AND CALIBRATION FLOW TRANSMITTER 10LBA10CF002 | 22/8/2026 | [5 empty] | FALSE
| 44 | WO-100826-0014 | OM EIC Y1 UNIT 1 JACKING OIL PUMP | 22/8/2026 |  |  | SCHED-OK | M. Toher | 2 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20MAV10-M101 : UNIT 1 JACKING OIL PUMP MOTOR | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20MAV10CP101 : UNIT 1 JACKING OIL PRESSURE TRANSMITTER | 22/8/2026 |  |  |  | MSW |  | FALSE
| 45 | WO-100826-0014 | OM EIC Y1 UNIT 1 MAIN OIL PUMP | 22/8/2026 |  |  | SCHED-OK | Aidhiy | 4 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPEKSI & PM OIL PUMP MOTOR ( AUXILIARY, EMERGENCY, JACKING, BREATHER ) | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | INSPEKSI DAN KALIBRASI LUB OIL PRESSURE TRANSMITTER 10MAV40CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPEKSI DAN KALIBRASI LUB OIL PRESSURE TRANSMITTER 10MAV40CP002 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPEKSI DAN KALIBRASI LUB OIL PRESSURE TRANSMITTER 10MAV40CP003 | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 46 | WO-100826-0014 | OM EIC Y1 UNIT 1 TURBINE CONTROL VALVE | 22/8/2026 |  |  | SCHED-OK | Aidhiy | 8 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP001) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP002) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP003) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | VALVE BLOCK - OUTLET POSITION LIVE STEAM PT (20MAX45CP004) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CONTROL OIL PRESSURE PT (20MAX40CP001) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | VALVE CHEST TEMPERATURE TRANSMITTER 10MAA10CT011 | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | LIVE STEAM PRESSURE TRANSMITTER 10LBA10CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CALIBRATION/FUNCTION TEST CONTROL VALVE | 22/8/2026 |  |  |  | MSW |  | FALSE
| 47 | WO-100826-0014 | OM EIC Y1 UNIT 1 HP BYPASS VALVE | 22/8/2026 |  |  | SCHED-OK | Jhon FM | 6 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | CALIBRATION/FUNCTION TEST HP BYPASS CONTROL VALVE 20LBF10AA210 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | HP BYPASS TEMPERATURE TRANSMITTER 10LBF10CT001 | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | BYPASS PRESSURE TRANSMITTER 10MAG10CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20LBF10CG101 : UNIT 1 STEAM BYPASS REDUCING CONTROL VALVE PRESSURE TRANSMITTER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20LBF10CP101 : UNIT 1 STEAM BYPASS REDUCING PRESSURE TRANSMITTER 10LBF10CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | MSW20LBF10CT101 : UNIT 1 STEAM BYPASS REDUCING TEMPERATURE TRANSMITTER | 22/8/2026 |  |  |  | MSW |  | FALSE
| 48 | WO-100826-0014 | OM EIC Y1 UNIT 1 TURBINE DRAINAGE MAIN HEADER LINE TO EXPANSION TUBE | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 7 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | DRAIN OF ESV 10MAL10AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | DRAIN OF CV CHAMBER 10MAL20AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE DRAIN VALVE AFTER FIRST STAGE 10MAL30AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE DRAIN VALVE 10MAL40AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE DRAIN VALVE 10MAL50AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE DRAIN VALVE 10MAL60AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | TURBINE DRAIN VALVE 10MAL70AA210 | 22/8/2026 | [5 empty] | FALSE
| 49 | WO-100826-0014 | OM EIC Y1 UNIT 1 VACUUM PUMP A | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 4 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20MAJ10-M102 : UNIT 1 VACUUM PUMP A MOTOR (MEGGER, INSPEKSI TERMINAL BLOK, DAN SISTEM COOLING MOTOR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | DISCHARGE, SUCTION & VENTING VALVE VACUUM PUMP-1 | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20MAJ10AA101 : UNIT 1 AIR REMOVAL SYSTEM VACUUM BREAKER SOLENOID VALVE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20MAJ10CG101 : UNIT 1 AIR REMOVAL SYSTEM POSITION TRANSMITTER | 22/8/2026 | [5 empty] | FALSE
| 50 | WO-100826-0014 | OM EIC Y1 UNIT 1 VACUUM PUMP B | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 4 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20MAJ10-M202 : UNIT 1 VACUUM PUMP B MOTOR (MEGGER, INSPEKSI TERMINAL BLOK, DAN SISTEM COOLING MOTOR) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | DISCHARGE, SUCTION & VENTING VALVE VACUUM PUMP-2 | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20MAJ10AA201 : UNIT 1 AIR REMOVAL SYSTEM VACUUM BREAKER SOLENOID VALVE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | MSW20MAJ10CG201 : UNIT 1 AIR REMOVAL SYSTEM POSITION TRANSMITTER | 22/8/2026 | [5 empty] | FALSE
| 51 | WO-100826-0014 | OM EIC Y1 UNIT 1 CONDENSER | 22/8/2026 |  |  | SCHED-OK | M Iqbal | 5 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | MSW20MAG10CP103 : UNIT 1 CONDENSER BYPASS PRESSURE TRANSMITTER 10MAG10CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | COOLING WATER SUPPLY TEMPERATURE TRANSMITTER 10PAB11CT001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | COOLING WATER SUPPLY TEMPERATURE TRANSMITTER 10PAB12CT001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | COOLING WATER RETURN TEMPERATURE TRANSMITTER 10PAB21CT001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | COOLING WATER RETURN TEMPERATURE TRANSMITTER 10PAB22CT001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 52 | WO-100826-0014 | OM EIC Y1 UNIT 1 MAIN CONDENSATE PUMP A | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 12 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION COOLING FAN | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TERMINASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CALIBRATION LIMIT SWITCH | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PRESSURE TRANSMITTER CONDENSATE PUMP TO DELIVERY 10LCA30CP001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | ACTUATOR CONDENSATE PUMP RECIRCULATION CONTROL VALVE 10LCA31AA210 | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | ACTUATOR MAIN CONDENSATE CONTROL VALVE 10LCA30AA240 | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | CEP DISCHARGE ISOLATION VALVE | 22/8/2026 |  |  |  | MSW |  | FALSE
| 53 | WO-100826-0014 | OM EIC Y1 UNIT 1 MAIN CONDENSATE PUMP B | 22/8/2026 |  |  | SCHED-OK | M. Zaini | 9 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION FRAME MOTOR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN ISOLASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION COOLING FAN | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TAHANAN WINDING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION TERMINASI | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION KONEKSI GROUNDING SYSTEM | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CALIBRATION LIMIT SWITCH | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CEP DISCHARGE ISOLATION VALVE | 22/8/2026 |  |  |  | MSW |  | FALSE
| 54 | WO-100826-0014 | OM EIC Y1 UNIT 1 GENERATOR CONTROL PANEL | 22/8/2026 |  |  | IN PROGRESS | M. Zaini | 13 | 53.8462 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PENGUJIAN PROTEKSI FREQUENCY | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI DIFFERENSIAL GENERATOR | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI SHORT CIRCUIT | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI OVERCURRENT | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI OVERVOLTAGE | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI ROTOR EARTH FAULT | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI STATOR EARTH FAULT | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PENGUJIAN PROTEKSI REVERSE POWER | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | PENGUJIAN PROTEKSI UNDER EXCITATION | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | PENGUJIAN PROTEKSI OVER EXCITATION | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | PENGUJIAN PROTEKSI NEGATIVE SEQUENCE | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | PENGUJIAN PROTEKSI OVERLOAD | 22/8/2026 |  |  |  | MSW |  | FALSE
|  |  | CLEANING DAN TIGHTNING | 22/8/2026 |  |  |  | MSW |  | FALSE
| 55 | WO-100826-0014 | OM EIC Y1 UNIT 1 GENERATOR EXCITATION PANEL | 22/8/2026 |  |  | FINISH | M. Zaini | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PERAWATAN BAGIAN EXTERNAL ENCLOSURE PANEL | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | MEMBERSIHKAN FILTER PANEL | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | PEMELIHARAAN FAN CONVERTER UNITROL | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | MEMBERSIHKAN KOMPARTEMEN DALAM PANEL | 22/8/2026 |  |  |  | MSW |  | TRUE
|  |  | HOUSEKEEPING | 22/8/2026 |  |  |  | MSW |  | TRUE
| 56 | WO-100826-0014 | OM EIC Y1 UNIT 1 SOOT BLOWER | 22/8/2026 |  |  | IN PROGRESS | Yoga | 16 | 75 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 1 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 2 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 3 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 4 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 5 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 6 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 7 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 8 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 9 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 10 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 11 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | SOOT BLOWER STEAM OUTLET TRANSMITTER 10HCB10CP001 | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | SOOT BLOWER STEAM FLOW TRANSMITTER 10HCB10CF001 | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | ACTUATOR VALVE DRAIN SOOT BLOWER 10HCB10AA201 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | SOOT BLOWER VALVE MOV 10HCB10AA001 | 22/8/2026 |  |  |  | AMP |  | FALSE
|  |  | ACTUATOR SOOT BLOWER CONTROL VALVE 10HCB10EX001 | 22/8/2026 |  |  |  | MSW |  | FALSE
| 57 | WO-100826-0014 | OM EIC Y1 UNIT 1 TURBINE CONTROL PANEL | 22/8/2026 |  |  | SCHED-OK | Jhon FM | 3 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PM PC OWS | 22/8/2026 | [5 empty] | FALSE
|  |  | PM PC EWS | 22/8/2026 | [5 empty] | FALSE
|  |  | PM panel RIO | 22/8/2026 | [5 empty] | FALSE
| 58 | WO-100826-0014 | OM EIC Y1 UNIT 1 LV DISTRIBUTION | 22/8/2026 |  |  | SCHED-OK | M Iqbal | 36 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPEKSI LV TRANSFORMER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | RDC Test LV TRANSFORMER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | FUNGSI RACK OUT RACK IN | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI BUSBAR *)sudah termasuk busbar dan busduct | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN KABEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN TRAFO KONTROL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN SOOTBLOWER MCC FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN TG MCC FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN ADAPTER PANEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK BUSDUCT BUSTIE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN ANALISA CB | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN ACB ESP FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI ACB ESP FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK ACB ESP FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN ANALISA CB ESP FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN ACB BOILER FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK ACB BOILER FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN ANALISA CB BOILER FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN ACB COOLING TOWER MCC FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI ACB COOLING TOWER FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK ACB COOLING TOWER FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN ANALISA CB COOLING TOWER FEEDER | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION HEATER BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION SILICA BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | CEK KEBOCORAN DAN KELEMBAPAN BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION CONTACT RESISTANCE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | INSPECTION ISOLATION RESISTANCE BUSDUCT | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | HOUSEKEEPING | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 59 | WO-100826-0014 | OM EIC Y1 UNIT 1 380V MCC SWICTHGEAR BOILER | 22/8/2026 |  |  | SCHED-OK | Yoga | 12 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN KABEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN MODULE WITHDRAWABLE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI ACB INCOMING | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK ACB | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN ANALISA CB | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | HOUSEKEEPING | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 60 | WO-100826-0014 | OM EIC Y1 UNIT 1 380V MCC SWICTHGEAR TG | 22/8/2026 |  |  | SCHED-OK | M Iqbal | 8 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN ISOLASI BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PENGUJIAN TAHANAN KONTAK BUSBAR | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN KABEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | PERAWATAN MODULE WITHDRAWABLE | 22/8/2026 |  |  |  | JAPA |  | FALSE
|  |  | HOUSEKEEPING | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 61 | WO-100826-0014 | OM EIC Y1 UNIT 1 380V MCC SWICTHGEAR ESP | 22/8/2026 |  |  | IN PROGRESS | M Iqbal | 12 | 91.6667 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PERAWATAN KOMPARTEMEN BUSBAR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUJIAN TAHANAN ISOLASI BUSBAR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUJIAN TAHANAN KONTAK BUSBAR | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PERAWATAN KOMPARTEMEN KABEL | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PERAWATAN MODULE WITHDRAWABLE | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PERAWATAN ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUJIAN TAHANAN ISOLASI ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUJIAN TAHANAN KONTAK ACB INCOMMING | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | PENGUJIAN ANALISA CB | 22/8/2026 |  |  |  | JAPA |  | TRUE
|  |  | HOUSEKEEPING | 22/8/2026 |  |  |  | JAPA |  | FALSE
| 62 | WO-100826-0014 | OM Y1 EIC UNIT 1 GLAND STEAM SEALING CONDENSER | 22/8/2026 |  |  | SCHED-OK | Aidhiy | 5 | 0 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | GLAND STEAM CONDENSER VENTING MOTOR | 22/8/2026 | [5 empty] | FALSE
|  |  | GLAND STEAM PRESSURE TRANSMITTER 10MAW11CP001 | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR GLAND STEAM PRESSURE CONTROL VALVE 10MAW10AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | ACTUATOR GLAND STEAM TEMPERATURE CONTROL VALVE 10LCE10AA210 | 22/8/2026 | [5 empty] | FALSE
|  |  | GENERAL CLEANING | 22/8/2026 | [5 empty] | FALSE
| 63 | WO-100826-0014 | OM Y1 EIC UNIT 2 CONVECTIVE PASS | 22/8/2026 |  |  | IN PROGRESS | Ferryus | 6 | 83.3333 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | INSPECTION AND CALIBRATION OXYGEN ANALYZER | 22/8/2026 | [5 empty] | FALSE
|  |  | INLET BACKPASS PRESSURE TRANSMITTER | 22/8/2026 | [5 empty] | TRUE
|  |  | INLET BACKPASS PRESSURE TRANSMITTER | 22/8/2026 | [5 empty] | TRUE
|  |  | INLET BACKPASS PRESSURE TRANSMITTER | 22/8/2026 | [5 empty] | TRUE
|  |  | BACKPASS PRESSURE AFTER LT SH TRANSMITTER | 22/8/2026 | [5 empty] | TRUE
|  |  | BACKPASS PRESSURE AFTER ECO TRANSMITTER | 22/8/2026 | [5 empty] | TRUE
| 64 | WO-100826-0014 | OM Y1 EIC UNIT 2 FLY ASH HANDLING | 22/8/2026 |  |  | IN PROGRESS | M Iqbal | 6 | 33.3333 | SUPERVISE, QC, OTHER TASK AS PER EIC JP
|  |  | Panel Bapcon - Rapcon Field 1 | 22/8/2026 | [5 empty] | TRUE
|  |  | Panel Bapcon - Rapcon Field 2 | 22/8/2026 | [5 empty] | TRUE
|  |  | Panel Bapcon - Rapcon Field 3 | 22/8/2026 | [5 empty] | FALSE
|  |  | Panel Bapcon - Rapcon Field 4 | 22/8/2026 | [5 empty] | FALSE
|  |  | Panel Bapcon - Rapcon Field 5 | 2025-07-21 | [5 empty] | FALSE
|  |  | Panel Bapcon - Rapcon Field 6 | 2025-07-21 | [5 empty] | FALSE