## Dashboard_Summary
EIC OUTAGE PROGRESS SUMMARY DASHBOARD — UNIT 1
*This sheet contains automated FORMULAS — do not edit manually. Update data in respective sheets.
1. WORK ORDERS (WorkOrder)
Unit | SCHED-OK | IN PROGRESS | FINISH | TOTAL | % FINISH
1
2. ACTUATOR VALVES (ActuatorValve)
Unit | SCHED-OK | IN PROGRESS | FINISH | TOTAL | % FINISH
1
3. FIELD INSTRUMENT CALIBRATION (Pressure TX + Temperature TX + Pressure Switch)
Unit | COMPLETED (WDONE) | NOT COMPLETED | TOTAL
1
4. FINDINGS SUMMARY (FINDINGS)
Data Source | Total Rows with Recorded Findings
WorkOrder
WorkOrder_Checklist
ActuatorValve
Instrument_PressureTX
Instrument_TemperatureTX
Instrument_PressureSwitch
5. OUTAGE SCHEDULE & S-CURVE PERIOD
Parameter | Date | Notes
Outage Start Date | 2026-08-22 | Official Outage Start Baseline for S-Curve Calculation | 2026-08-22
Outage Finish Date | 2026-09-20 | Planned Outage Completion Baseline for S-Curve Calculation
Target Duration (Days) | 15 | Total planned outage overhaul window duration in calendar days

## README
DATA TEMPLATE — OUTAGE EIC WORK ORDER MONITORING SYSTEM
MSW POWER PLANT — Unit 1 & Unit 2
INSTRUCTIONS & GUIDELINES:
1. This file is the primary DATA SOURCE read directly by the Outage EIC Monitoring web system.
2. Cells highlighted in YELLOW must be manually filled/updated by field PIC personnel.
3. The 'Temuan' (Findings) and 'Tindak Lanjut' (Action Taken) columns are used for abnormal conditions during inspection.
4. The 'Photo Count' column does NOT need manual entry — it is automatically populated by the web application
when uploading finding photos (stored in Finding/<WO or Component Name>/).
5. The web system can READ and WRITE directly to this file — do not alter column positions or structure
because web parsers map data based on this standard structure.
6. Light green rows on each sheet serve as EXAMPLES — overwrite with actual outage records.
when beginning actual data entry.
7. The 'Unit' column indicates 1 or 2 according to the operating outage unit.
8. For Actuator Valve sheet: equipment list is identical for Unit 1 and Unit 2 –
Unit 1 and Unit 2 — maintain separate status rows per unit,
with same Equipment_ID, but progress/status/findings tracked separately per unit.
SHEET DIRECTORY:
- WorkOrder : Master Work Orders (WO) list for EIC section
- WorkOrder_Checklist : Sub-task breakdown and checklist per WO
- ActuatorValve : Actuator and valve progress monitoring (Unit 1 & 2)
- Instrument_PressureTX : Pressure and flow transmitter calibration
- Instrument_TemperatureTX : Temperature transmitter calibration
- Instrument_PressureSwitch : Pressure switch verification & calibration
- PIC_Scope_Master : Job scope allocation & PIC master (Vendor / MSW)
- Dashboard_Summary : Automated statistical summary (formula protected)

## WorkOrder
No | No_WO | Unit | Job_Description | Area | Schedule_Date | Actual_Start_Date | Finish_Date | Status | PIC | N_Task | Progress_Percent | Scope | Remarks | Findings | Action_Taken | Photo_Count
1 | WO-100826-0012 | 1 | OM EIC Y1 UNIT COMMON COOLING TOWER FAN 1 | COOLING TOWER | 22/08/2026 | 22/08/2026 | 01/09/2026 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
2 | WO-100826-0013 | 1 | OM EIC Y1 UNIT COMMON COOLING TOWER FAN 2 | COOLING TOWER | 22/08/2026 | 22/08/2026 | 01/09/2026 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
3 | WO-100826-0014 | 1 | OM EIC Y1 UNIT COMMON MAIN COOLING WATER PUMP 1 | COOLING WATER | 22/08/2026 | 22/08/2026 | 01/09/2026 | FINISH | H AIDI | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
4 | WO-100826-0015 | 1 | OM EIC Y1 UNIT COMMON MAIN COOLING WATER PUMP 2 | COOLING WATER | 22/08/2026 | 22/08/2026 | 01/09/2026 | FINISH | H AIDI | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
5 | WO-100826-0016 | 1 | OM EIC Y1 UNIT COMMON AUXILIARY COOLING WATER PUMP 1 | COOLING WATER | 22/08/2026 | 22/08/2026 | 09/09/2026 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
6 | WO-100826-0017 | 1 | OM EIC Y1 UNIT COMMON AUXILIARY COOLING WATER PUMP 2 | COOLING WATER | 22/08/2026 | 22/08/2026 | 09/09/2026 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
7 | WO-100826-0160 | 1 | OM EIC Y1 UNIT 1 INDUCED DRAUGHT FAN 1 | BOILER | 22/08/2026 | 22/08/2026 | 09/09/2026 | FINISH | M TOHER | 15 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
8 | WO-100826-0161 | 1 | OM EIC Y1 UNIT 1 INDUCED DRAUGHT FAN 2 | BOILER | 22/08/2026 |  | 09/09/2026 | FINISH | M TOHER | 11 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
9 | WO-100826-0020 | 1 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 1 | BOILER | 22/08/2026 | 22/08/2026 | 01/09/2026 | FINISH | M ZAINI | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
10 | WO-100826-0021 | 1 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 1 LUBE OIL SYSTEM | BOILER | 22/08/2026 | 22/08/2026 | 02/09/2026 | FINISH | FERRYUS | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
11 | WO-100826-0022 | 1 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 2 | BOILER | 22/08/2026 | 22/08/2026 | 07/09/2026 | FINISH | M ZAINI | 10 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
12 | WO-100826-0023 | 1 | OM EIC Y1 UNIT 1 PRIMARY AIR FAN 2 LUBE OIL SYSTEM | BOILER | 22/08/2026 | 22/08/2026 | 02/09/2026 | FINISH | FERRYUS | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
13 | WO-100826-0024 | 1 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 1 | BOILER | 22/08/2026 | 22/08/2026 | 07/09/2026 | FINISH | H AIDI | 11 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
14 | WO-100826-0025 | 1 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 1 LUBE OIL SYSTEM | BOILER | 22/08/2026 |  | 02/09/2026 | FINISH | JHON | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
15 | WO-100826-0026 | 1 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 2 | BOILER | 22/08/2026 | 22/08/2026 | 07/09/2026 | FINISH | H AIDI | 11 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
16 | WO-100826-0027 | 1 | OM EIC Y1 UNIT 1 SECONDARY AIR FAN 2 LUBE OIL SYSTEM | BOILER | 22/08/2026 |  | 02/09/2026 | FINISH | JHON | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
17 | WO-100826-0028 | 1 | OM EIC Y1 UNIT 1 COAL FEEDER NO 1 | COAL HANDLING | 22/08/2026 | 22/08/2026 |  | FINISH | H AIDI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
18 | WO-100826-0029 | 1 | OM EIC Y1 UNIT 1 COAL FEEDER NO 2 | COAL HANDLING | 22/08/2026 | 22/08/2026 | 04/09/2026 | FINISH | H AIDI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
19 | WO-100826-0030 | 1 | OM EIC Y1 UNIT 1 LDO START-UP BURNER 1 | BOILER | 22/08/2026 | 22/08/2026 | 24/09/2026 | FINISH | JHON | 21 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
20 | WO-100826-0031 | 1 | OM EIC Y1 UNIT 1 LDO START-UP BURNER 2 | BOILER | 22/08/2026 |  | 28/09/2026 | FINISH | JHON | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
21 | WO-100826-0032 | 1 | OM EIC Y1 UNIT 1 SEALPOT BLOWER NO 1 | BOILER | 22/08/2026 | 22/08/2026 | 22/08/2026 | FINISH | FERRYUS | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
22 | WO-100826-0033 | 1 | OM EIC Y1 UNIT 1 SEALPOT BLOWER NO 2 | BOILER | 22/08/2026 | 22/08/2026 | 22/08/2026 | FINISH | FERRYUS | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
23 | WO-100826-0034 | 1 | OM EIC Y1 UNIT 1 ELECTROSTATIC PRECIPITATOR 1-6 | ESP | 22/08/2026 | 22/08/2026 | 14/09/2026 | FINISH | M IQBAL | 19 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
24 | WO-100826-0035 | 1 | OM EIC Y1 UNIT 1 BOILER FEED PUMP 1 | TURBINE | 22/08/2026 | 22/08/2026 | 17/09/2026 | FINISH | YOGA | 26 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
25 | WO-100826-0036 | 1 | OM EIC Y1 UNIT 1 BOILER FEED PUMP 2 | TURBINE | 22/08/2026 | 22/08/2026 | 08/09/2026 | FINISH | YOGA | 20 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
26 | WO-100826-0037 | 1 | OM EIC Y1 UNIT 1 FEED WATER LINE | FEED WATER | 22/08/2026 | 22/08/2026 | 04/09/2026 | FINISH | M TOHER | 10 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
27 | WO-100826-0038 | 1 | OM EIC Y1 UNIT 1 DESH SUPERHEATER LINE 1 | BOILER | 22/08/2026 | 22/08/2026 | 09/09/2026 | FINISH | M TOHER | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
28 | WO-100826-0039 | 1 | OM EIC Y1 UNIT 1 DESH SUPERHEATER LINE 2 | BOILER | 22/08/2026 | 22/08/2026 | 09/09/2026 | FINISH | M TOHER | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
29 | WO-100826-0040 | 1 | OM EIC Y1 UNIT 1 GENERATOR CIRCUIT BREAKER | ELECTRICAL | 22/08/2026 | 22/08/2026 | 02/09/2026 | FINISH | M ZAINI | 28 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
30 | WO-100826-0041 | 1 | OM EIC Y1 UNIT 1 GENERATOR | ELECTRICAL | 22/08/2026 |  | 24/09/2026 | FINISH | M ZAINI | 38 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
31 | WO-100826-0042 | 1 | OM EIC Y1 UNIT 1 AUXILIARY TRANSFORMER 2 | ELECTRICAL | 22/08/2026 |  | 08/09/2026 | FINISH | M ZAINI | 22 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
32 | WO-100826-0043 | 1 | OM EIC Y1 UNIT 1 6.6KV MEDIUM VOLTAGE STATION BOARDS PANEL | ELECTRICAL | 22/08/2026 | 22/08/2026 | 02/09/2026 | FINISH | M ZAINI | 15 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
33 | WO-100826-0044 | 1 | OM EIC Y1 UNIT 1 MEDIUM VOLTAGE STATION BOARDS COMMON | ELECTRICAL | 22/08/2026 |  | 04/09/2026 | FINISH | H AIDI | 10 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
34 | WO-100826-0045 | 1 | OM EIC Y1 UNIT 1 MAIN TURBINE | TURBINE | 22/08/2026 |  | 20/09/2026 | FINISH | M TOHER | 55 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
35 | WO-100826-0046 | 1 | OM EIC 1Y FIRE ALARM LOCAL PANEL ( UNIT 1 ) | FIRE PROTECTION | 22/08/2026 |  | 24/09/2026 | FINISH | JHON | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
36 | WO-100826-0047 | 1 | OM EIC 1Y UNIT 1 PRIMARY AIR FAN LINE | BOILER | 22/08/2026 | 22/08/2026 | 31/08/2026 | FINISH | FERRYUS | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
37 | WO-100826-0048 | 1 | OM EIC 1Y UNIT 1 SECONDARY AIR FAN LINE | BOILER | 22/08/2026 | 22/08/2026 | 04/09/2026 | FINISH | FERRYUS | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
38 | WO-100826-0049 | 1 | OM EIC Y1 UNIT 1 BOILER DISTRIBUTED CONTROL PANEL | DCS | 22/08/2026 |  | 17/09/2026 | FINISH | JHON | 3 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
39 | WO-100826-0050 | 1 | OM EIC Y1 UNIT 1 BOILER DRUM | BOILER | 22/08/2026 | 22/08/2026 | 31/08/2026 | FINISH | JHON | 18 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
40 | WO-100826-0051 | 1 | OM EIC Y1 UNIT 1 COMBUSTOR | BOILER | 22/08/2026 | 22/08/2026 | 11/09/2026 | FINISH | FERRYUS | 21 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
41 | WO-100826-0052 | 1 | OM EIC Y1 UNIT 1 CYCLONE | BOILER | 22/08/2026 | 22/08/2026 | 14/09/2026 | FINISH | M TOHER | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
42 | WO-100826-0053 | 1 | OM EIC Y1 UNIT 1 SEALPOT | BOILER | 22/08/2026 |  | 20/09/2026 | FINISH | M ZAINI | 3 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
43 | WO-100826-0054 | 1 | OM EIC Y1 UNIT 1 SUPERHEATER SYSTEM LINE | BOILER | 22/08/2026 | 22/08/2026 | 14/09/2026 | FINISH | M ZAINI | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
44 | WO-100826-0055 | 1 | OM EIC Y1 UNIT 1 JACKING OIL PUMP | TURBINE | 22/08/2026 |  | 07/09/2026 | FINISH | M TOHER | 2 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
45 | WO-100826-0056 | 1 | OM EIC Y1 UNIT 1 MAIN OIL PUMP | TURBINE | 22/08/2026 |  | 14/09/2026 | FINISH | H AIDI | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
46 | WO-100826-0057 | 1 | OM EIC Y1 UNIT 1 TURBINE CONTROL VALVE | TURBINE | 22/08/2026 |  | 24/09/2026 | FINISH | H AIDI | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
47 | WO-100826-0058 | 1 | OM EIC Y1 UNIT 1 HP BYPASS VALVE | TURBINE | 22/08/2026 |  | 20/09/2026 | FINISH | M TOHER | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
48 | WO-100826-0059 | 1 | OM EIC Y1 UNIT 1 TURBINE DRAINAGE MAIN HEADER LINE TO EXPANSION TUBE | TURBINE | 22/08/2026 |  | 08/09/2026 | FINISH | M TOHER | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
49 | WO-100826-0060 | 1 | OM EIC Y1 UNIT 1 VACUUM PUMP A | TURBINE | 22/08/2026 |  | 29/08/2026 | FINISH | YOGA | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
50 | WO-100826-0061 | 1 | OM EIC Y1 UNIT 1 VACUUM PUMP B | TURBINE | 22/08/2026 |  | 29/08/2026 | FINISH | YOGA | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
51 | WO-100826-0062 | 1 | OM EIC Y1 UNIT 1 CONDENSER | TURBINE | 22/08/2026 |  | 20/09/2026 | FINISH | FERRYUS | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
52 | WO-100826-0063 | 1 | OM EIC Y1 UNIT 1 MAIN CONDENSATE PUMP A | TURBINE | 22/08/2026 |  | 07/09/2026 | FINISH | M ZAINI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
53 | WO-100826-0064 | 1 | OM EIC Y1 UNIT 1 MAIN CONDENSATE PUMP B | TURBINE | 22/08/2026 |  | 07/09/2026 | FINISH | M ZAINI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
54 | WO-100826-0065 | 1 | OM EIC Y1 UNIT 1 GENERATOR CONTROL PANEL | ELECTRICAL | 22/08/2026 | 22/08/2026 | 11/09/2026 | FINISH | M ZAINI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
55 | WO-100826-0066 | 1 | OM EIC Y1 UNIT 1 GENERATOR EXCITATION PANEL | ELECTRICAL | 22/08/2026 | 22/08/2026 | 22/08/2026 | FINISH | M ZAINI | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
56 | WO-100826-0067 | 1 | OM EIC Y1 UNIT 1 SOOT BLOWER | BOILER | 22/08/2026 | 22/08/2026 | 10/09/2026 | FINISH | YOGA | 17 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
57 | WO-100826-0068 | 1 | OM EIC Y1 UNIT 1 TURBINE CONTROL PANEL | TURBINE | 22/08/2026 |  | 17/09/2026 | FINISH | JHON | 3 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
58 | WO-100826-0069 | 1 | OM EIC Y1 UNIT 1 LV DISTRIBUTION | ELECTRICAL | 22/08/2026 |  | 04/09/2026 | FINISH | M IQBAL | 34 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
59 | WO-100826-0070 | 1 | OM EIC Y1 UNIT 1 380V MCC SWICTHGEAR BOILER | ELECTRICAL | 22/08/2026 |  | 04/09/2026 | FINISH | YOGA | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
60 | WO-100826-0071 | 1 | OM EIC Y1 UNIT 1 380V MCC SWICTHGEAR TG | ELECTRICAL | 22/08/2026 |  | 04/09/2026 | FINISH | M IQBAL | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
61 | WO-100826-0072 | 1 | OM EIC Y1 UNIT 1 380V MCC SWICTHGEAR ESP | ELECTRICAL | 22/08/2026 | 22/08/2026 | 31/08/2026 | FINISH | M IQBAL | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
62 | WO-100826-0073 | 1 | OM Y1 EIC UNIT 1 GLAND STEAM SEALING CONDENSER | TURBINE | 22/08/2026 |  | 02/09/2026 | FINISH | M TOHER | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
63 | WO-100826-0074 | 1 | OM Y1 EIC UNIT 1 CONVECTIVE PASS | BOILER | 22/08/2026 | 22/08/2026 | 09/09/2026 | FINISH | FERRYUS | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
64 | WO-100826-0075 | 1 | OM Y1 EIC UNIT 1 FLY ASH HANDLING | ASH HANDLING | 22/08/2026 | 22/08/2026 | 01/09/2026 | FINISH | M IQBAL | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0

## WorkOrder_Checklist
No_WO | Sub_Task_Description | Date | PIC_Task | Done_TRUE_FALSE | Findings | Action_Taken | Photo_Count
WO-100826-0012 | INSPECTION FRAME MOTOR | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | INSULATION RESISTANCE INSPECTION | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | WINDING RESISTANCE INSPECTION | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | INSPECTION COOLING FAN | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | INSPECTION TERMINASI | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | INSPECTION KONEKSI GROUNDING SYSTEM | 29/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0012 | SOLO RUN | 01/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | INSPECTION FRAME MOTOR | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | WINDING RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0013 | SOLO RUN | 01/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | INSPECTION FRAME MOTOR | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | WINDING RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0014 | SOLO RUN | 01/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | INSPECTION FRAME MOTOR | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | WINDING RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0015 | SOLO RUN | 01/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSPECTION FRAME MOTOR | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSPECTION BEARING & REPLACEMENT | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | WINDING RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSPECTION COOLING FAN | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSPECTION KONEKSI GROUNDING SYSTEM | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0016 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 09/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSPECTION FRAME MOTOR | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSPECTION BEARING & REPLACEMENT | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | WINDING RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSPECTION TERMINASI | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSPECTION KONEKSI GROUNDING SYSTEM | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0017 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 09/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0160 | UNIT 1 INDUCED DRAUGHT FAN 1 INLET GATE ACTUATOR MOV 20HNA61AA001 | 31/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0160 | UNIT 1 INDUCED DRAUGHT FAN 1 OUTLET GATE ACTUATOR MOV 20HNA71AA001 | 31/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0160 | REPOSISI MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | INSPEKSI And CLEANING BALL BEARING DE And NDE (REPLACE BEARING IF NEEDED) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | WINDING RESISTANCE MEASUREMENT | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | UNIT 1 INDUCED DRAUGHT FAN 1 IGV 10HNC01EX001 | 29/8/2026 | AMP | TRUE |  |  | 0
WO-100826-0160 | INLET ID FAN 1 PRESSURE TRANSMITTER 10HNA61CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | INLET PRESSURE ESP PRESSURE TRANSMITTER 10HNA41CP001 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | OUTLET PRESSURE ESP PRESSURE TRANSMITTER 10HNA41CP002 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0160 | SOLO RUN | 01/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0161 | UNIT 1 INDUCED DRAUGHT FAN 2 INLET ACTUATOR MOV 20HNA62AA001 | 09/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0161 | UNIT 1 INDUCED DRAUGHT FAN 2 OUTLET ACTUATOR MOV 20HNA72AA001 | 04/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0161 | REPOSISI MOTOR | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0161 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0161 | INSPEKSI And CLEANING BALL BEARING DE And NDE (REPLACE BEARING IF NEEDED) | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0161 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0161 | WINDING RESISTANCE MEASUREMENT | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0161 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0161 | UNIT 1 INDUCED DRAUGHT FAN 2 IGV 10HNC01EX002 | 02/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0161 | SOLO RUN | 09/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0161 | INLET ID FAN 2 PRESSURE TRANSMITTER 10HNA62CP001 | 28/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | REPOSISI MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | REPLACE BEARING IF NEEDED | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | WINDING RESISTANCE MEASUREMENT | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0020 | UNIT 1 PRIMARY AIR FAN 1 IGV | 29/8/2026 | MSW | TRUE |  |  | 0
WO-100826-0020 | UNIT 1 PRIMARY AIR FAN 1 OUTLET MOV | 01/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0020 | PA FAN 1 OUTLET PRESSURE TRANSMITTER 10HLB03CP001 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0021 | MSW10HLN20-M101:UNIT 1 PRIMARY AIR FAN 1 LUBE OIL PUMP 1 MOTOR (STAND BY) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0021 | MSW10HLN20-M102:UNIT 1 PRIMARY AIR FAN 1 LUBE OIL PUMP 2 MOTOR (MAIN) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0021 | 20HLB01CP104: LO HEADER PRESSURE LOW ALARM FOR PA FAN-1 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0021 | 20HLB01CP103: PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-1 START | 10/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0021 | 20HLB01CP102: PRESSURE SWITCH TO START LO PA FAN-1 STANDBY PUMP | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0021 | 20HLB01CP101: DP SWITCH ACROSS LO TANK FOR PA FAN-1 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0022 | REPOSISI MOTOR | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | REPLACE BEARING IF NEEDED | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | WINDING RESISTANCE MEASUREMENT | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | UNIT 1 PRIMARY AIR FAN 2 IGV | 29/8/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | MSW10HLB20AA202:UNIT 1 PRIMARY AIR FAN 2 OUTLET MOV | 07/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0022 | PA FAN 2 OUTLET PRESSURE TRANSMITTER 10HLB04CP001 | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0023 | MSW10HLN20-M201:UNIT 1 PRIMARY AIR FAN 2 LUBE OIL PUMP 1 MOTOR (STAND BY) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0023 | MSW10HLN20-M202:UNIT 1 PRIMARY AIR FAN 2 LUBE OIL PUMP 2 MOTOR (MAIN) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0023 | 20HLB02CP104: LO HEADER PRESSURE LOW ALARM FOR PA FAN-2 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0023 | 20HLB02CP103: PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-2 START | 10/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0023 | 20HLB02CP102: PRESSURE SWITCH TO START LO PA FAN-2 STANDBY PUMP | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0023 | MSW10HLN20CL201:UNIT 1 PRIMARY AIR FAN 2 LUBE OIL TANK LEVEL SWITCH | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0024 | REPOSISI MOTOR | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | REPLACE BEARING IF NEEDED | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | WINDING RESISTANCE MEASUREMENT | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | UNIT 1 SECONDARY AIR FAN 1 OUTLET MOV | 07/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | SA FAN 1 OUTLET PRESSURE TRANSMITTER 10HLB01CP001 | 04/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0024 | UNIT 1 SECONDARY AIR FAN 1 IGV SA FAN 1 20HLB01EX001 | 29/8/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0025 | MSW10HLN10-M101:UNIT 1 SECONDARY AIR FAN 1 LUBE OIL PUMP 1 MOTOR (STAND BY) | 31/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0025 | MSW10HLN10-M102:UNIT 1 SECONDARY AIR FAN 1 LUBE OIL PUMP 2 MOTOR (MAIN) | 31/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0025 | 20HLB02CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-1 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0025 | 20HLB05CP104: LO HEADER PRESSURE LOW ALARM FOR SA FAN-1 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0025 | 20HLB05CP103: PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-1 START | 10/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0025 | 20HLB05CP102: PRESSURE SWITCH TO START LO SA FAN-1 STANDBY PUMP | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0025 | 20HLB05CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-1 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0026 | REPOSISI MOTOR | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | REPLACE BEARING IF NEEDED | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | WINDING RESISTANCE MEASUREMENT | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | UNIT 1 SECONDARY AIR FAN 2 OUTLET MOV | 07/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | UNIT 1 IGV SA FAN 2 10HLB01EX001 | 29/8/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0026 | SA FAN 2 OUTLET PRESSURE TRANSMITTER 10HLB02CP001 | 07/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0027 | MSW10HLN10-M201:UNIT 1 SECONDARY AIR FAN 2 LUBE OIL PUMP 1 MOTOR (STAND BY) | 30/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0027 | MSW10HLN10-M202:UNIT 1 SECONDARY AIR FAN 2 LUBE OIL PUMP 2 MOTOR (MAIN) | 30/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0027 | 20HLB06CP104: LO HEADER PRESSURE LOW ALARM FOR SA FAN-2 | 02/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0027 | 20HLB06CP103: PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-2 START | 10/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0027 | 20HLB06CP102: PRESSURE SWITCH TO START LO SA FAN-2 STANDBY PUMP | 02/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0027 | 20HLB06CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-2 | 02/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0028 | INSPECTION FRAME MOTOR DRAG CHAIN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION FRAME MOTOR ROTARY AIR LOCK | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0028 | INSPECTION OF MFT ACTUATOR 10HHE11AA01 | 29/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0029 | INSPECTION FRAME MOTOR DRAG CHAIN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION FRAME MOTOR ROTARY AIR LOCK | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION COOLING FAN | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION TERMINASI | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0029 | INSPECTION OF MFT ACTUATOR 10HHE12AA01 | 04/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0030 | INSPECTION OF IGNITER GUN | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | INSPECTION OF START UP BURNER SKID DEVICE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | LDO PRESSURE BEFORE MTV SWITCH 10HJF11CP301 | 10/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ATOM AIR INLET PRESSURE LOW SWITCH 10HJN11CP301 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | LDO PRESSURE LOW TRIP FOR SUB 1 SWITCH 10HJF11CP302 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ATOM AIR PRESSURE LOW TRIP FOR SUB 1 SWITCH 10HJN11CP302 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | LDO PRESSURE HIGH TRIP FOR SUB 1 SWITCH 10HJF11CP303 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | SCANNER AIR PRESSURE OK 1 SWITCH 10HJG69CP301 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | SCANNER AIR PRESSURE OK 2 SWITCH 10HJG69CP302 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SKID BURNER MAIN LDO LINE CONTROL VALVE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SKID BURNER 1 LDO LINE CONTROL VALVE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SKID BURNER 1 ATOMISING AIR LINE CONTROL VALVE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SUB BURNER 1 VALVE 10HJN11AA003 | 24/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SKID BURNER 1 ATOM AIR ISOLATION VALVE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SKID BURNER 1 LDO ISOLATION VALVE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ACTUATOR SKID BURNER 1 SCAVENGING VALVE | 24/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0030 | ATOM AIR PRESSURE AFTER SUB 1 TRANSMITTER 10HJN11CP001 | 30/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0030 | LDO PRESS AFTER SUB1 FVC TRANSMITTER 10HJF11CP001 | 30/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0031 | INSPECTION OF IGNITER GUN | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | INSPECTION OF START UP BURNER SKID DEVICE | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | LDO PRESSURE LOW TRIP FOR SUB 2 SWITCH 10HJF12CP302 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ATOM AIR PRESSURE LOW TRIP FOR SUB 2 SWITCH 10HJN12CP302 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | LDO PRESSURE HIGH TRIP FOR SUB 2 SWITCH 10HJF12CP303 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ATOM AIR PRESSURE AFTER SUB 2 TRANSMITTER 10HJN12CP001 | 30/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0031 | LDO PRESS AFTER SUB2 FCV TRANSMITTER 10HJF12CP001 | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0031 | ACTUATOR SKID BURNER 2 LDO LINE CONTROL VALVE | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ACTUATOR SKID BURNER 2 ATOMISING AIR LINE CONTROL VALVE | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ACTUATOR SKID BURNER 2 ATOM AIR ISOLATION VALVE | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ACTUATOR SKID BURNER 2 LDO ISOLATION VALVE | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ACTUATOR SKID BURNER 2 SCAVENGING VALVE | 28/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0031 | ACTUATOR SUB BURNER 2 VALVE 10HJN12AA003 | 28/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0032 | INSPECTION FRAME MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | BEARING REPLACEMENT (IF NECESSARY) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | INSPECTION COOLING FAN | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | INSPECTION TERMINASI | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | SEALPOT BLOWER PRESS OUTLET TRANSMITTER 10HLB41CP001 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0032 | P&S BLOWER PRESS OUTLET TRANSMITTER 10QEB20CP001 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0033 | INSPECTION FRAME MOTOR | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0033 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0033 | BEARING REPLACEMENT | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0033 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0033 | INSPECTION COOLING FAN | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0033 | INSPECTION TERMINASI | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0033 | INSPECTION KONEKSI GROUNDING SYSTEM | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M101:UNIT 1 ESP RAPPING MOTOR (GDRM) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M102:UNIT 1 ESP RAPPING MOTOR (CERM-1) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M103:UNIT 1 ESP RAPPING MOTOR (CERM-2) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M104:UNIT 1 ESP RAPPING MOTOR (CERM-3) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M105:UNIT 1 ESP RAPPING MOTOR (CERM-4) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M106:UNIT 1 ESP RAPPING MOTOR (CERM-5) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M107:UNIT 1 ESP RAPPING MOTOR (CERM-6) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M108:UNIT 1 ESP RAPPING MOTOR (EERM-1) | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M109:UNIT 1 ESP RAPPING MOTOR (EERM-2) | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M110:UNIT 1 ESP RAPPING MOTOR (EERM-3) | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M120:UNIT 1 ESP RAPPING MOTOR (EERM-4) | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M130:UNIT 1 ESP RAPPING MOTOR (EERM-5) | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | MSW10HDE10-M140:UNIT 1 ESP RAPPING MOTOR (EERM-6) | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | UNIT 1 ESP TRAFO 1 (GENERAL CLEANING, INSPEKSI, IR TEST) | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | UNIT 1 ESP TRAFO 2 (GENERAL CLEANING, INSPEKSI, IR TEST) | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | UNIT 1 ESP TRAFO 3 (GENERAL CLEANING, INSPEKSI, IR TEST) | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | UNIT 1 ESP TRAFO 4 (GENERAL CLEANING, INSPEKSI, IR TEST) | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | UNIT 1 ESP TRAFO 5 (GENERAL CLEANING, INSPEKSI, IR TEST) | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0034 | UNIT 1 ESP TRAFO 6 (GENERAL CLEANING, INSPEKSI, IR TEST) | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | INSPECTION FRAME MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | WINDING RESISTANCE INSPECTION | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | INSPECTION COOLING FAN | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | INSPECTION TERMINASI | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | INSPECTION KONEKSI GROUNDING SYSTEM | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10-M101:MOV DISCHARGE BFP-1 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CG101:UNIT 1 BOILER FEED PUMP 1 LIMIT SWITCH | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | 20LAC10CP101:UNIT 1 BOILER FEED PUMP 1 PRESSURE DIFFERENTIAL SWITCH | 08/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT101:UNIT 1 BOILER FEED PUMP 1 R PHASE WDG TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT102:UNIT 1 BOILER FEED PUMP 1 B PHASE WDG TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT103:UNIT 1 BOILER FEED PUMP 1 B PHASE WDG TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT104:UNIT 1 BOILER FEED PUMP 1 B NDE MOTOR BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT105:UNIT 1 BOILER FEED PUMP 1 B NDE MOTOR BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT106:UNIT 1 BOILER FEED PUMP 1 B NDE PUMP BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10CT107:UNIT 1 BOILER FEED PUMP 1 B NDE PUMP BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | MSW10LAC10GH101:UNIT 1 BOILER FEED PUMP 1 FCMA PANEL | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | INSPECTION FRAME MOTOR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | INSULATION RESISTANCE INSPECTION | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | WINDING RESISTANCE INSPECTION | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | INSPECTION COOLING FAN | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | INSPECTION TERMINASI | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | INSPECTION KONEKSI GROUNDING SYSTEM | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10-M201:MOV DISCHARGE BFP-2 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CG201:UNIT 1 BOILER FEED PUMP 2 LIMIT SWITCH | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CP201:UNIT 1 BOILER FEED PUMP 2 PRESSURE DIFFERENTIAL SWITCH | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT201:UNIT 1 BOILER FEED PUMP 2 R PHASE WDG TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT202:UNIT 1 BOILER FEED PUMP 2 B PHASE WDG TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT203:UNIT 1 BOILER FEED PUMP 2 B PHASE WDG TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT204:UNIT 1 BOILER FEED PUMP 2 B NDE MOTOR BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT205:UNIT 1 BOILER FEED PUMP 2 B NDE MOTOR BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT206:UNIT 1 BOILER FEED PUMP 2 B NDE PUMP BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10CT207:UNIT 1 BOILER FEED PUMP 2 B NDE PUMP BEARING TEMPERATURE | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0036 | MSW10LAC10GH201:UNIT 1 BOILER FEED PUMP 2 FCMA PANEL | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0037 | UNIT 1 FEED WATER INLET ECONOMIZER MOTORIZED VALVE MOTOR 100% 10LAB30AA220 | 22/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0037 | UNIT 1 FEED WATER INLET ECONOMIZER MOTORIZED VALVE MOTOR 30% 10LAB30AA210 | 04/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0037 | ACTUATOR BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L CV 10LAE10AA210 | 04/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0037 | BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L MOV 10LAE10AA110 | 04/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0037 | DISTRIBUTOR LINE TO FEEDWATER TRANSMITTER 10LAB30CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0037 | INLET FEEDWATER PRESSURE TRANSMITTER 10HAC90CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0037 | INLET FEEDWATER FLOW TRANSMITTER 10HAC90CF001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0037 | INLET FEEDWATER FLOW TRANSMITTER 10HAC90CF002 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0038 | CALIBRATION/FUNCTION TEST SPRAY CONTROL VALVE 10LAE10EX001 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0038 | CALIBRATION/FUNCTION ISOLATION (ON/OFF) VALVE | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0038 | DESH 1 SPRAY WATER FLOW TRANSMITTER 10LAE20CF001 | 04/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0039 | DESH 2 SPRAY WATER FLOW TRANSMITTER 10LAE30CF001 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0039 | CALIBRATION/FUNCTION TEST SPRAY CONTROL VALVE 10LAE12EX001 | 22/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0039 | BEFORE DESH 2 TEMP TRANSMITTER CALIBRATION (20HAH46CT001, 10HAH36CT009, 10HAH36CT009) | 09/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0040 | INSPECTION MEKANIK PENGGERAK | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION MOTOR CHARGING | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION BEARING DRIVE RACK OUT/IN | 22/08/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | REGREASING SOCKET MAIN KONTAK | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION SYSTEM KONTROL | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | CONTACT RESISTANCE TEST | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | TEST KESEREMPAKAN | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSULATION RESISTANCE INSPECTION KONTAK | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSULATION RESISTANCE INSPECTION BUS BAR | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | FUNCTION TEST | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | MOTOR CHARGING, CLOSING AND TRIPPING COIL RESISTANCE MEASUREMENT | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION MODUL CONTROL BREAKER | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION LAMPU SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INDIKATOR And LAMPU PANEL SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | DC POWER TESTING FOR 6.3 KV GCB SWITCHGEAR CONTROL SUPPLY | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION HEATER CUBICLE SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION And CLEANING TERMINASI SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION AND PROTECTION RELAY TESTING FOR GCB SWITCHGEAR | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION GROUNDING SYSTEM SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSULATION RESISTANCE INSPECTION BUS BAR SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION CT & PT SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | FUNCTION TEST SWITCH GEAR GCB | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION HEATER SYSTEM | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION DISPLAY BREAKER | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION HEATER BUSDUCT | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 02/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | INSPECTION SILICA BUSDUCT | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0040 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0041 | DISASSEMBLY BRACKET GENERATOR SISI FRONT | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | DISASSEMBLY BRACKET GENERATOR SISI REAR | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | DISASSEMBLY OIL DEFLECTOR BEARING | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | CLEANING BODY GENERATOR | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | CLEANING OIL DEFLECTOR BEARING | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | CLEANING BOLT & NUT | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION OIL DEFLECTOR BEARING 3 & 4 | 05/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION SHROUD & FAN BLADE | 05/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION STATOR GENERATOR (IR, PI) | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION ROTOR GENERATOR (IR, PI, RSO) | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION VISUAL ISOLATOR | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION ROTOR GROUNDING | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION VISUAL FLEXIBLE ISOLATOR | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION BRUSH GROUNDING | 11/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSULATION RESISTANCE INSPECTION GENERATOR | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION HEATER NEUTRAL SIDE CUBICLE | 11/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION HEATER LINE SIDE CUBICLE | 11/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | ASSEMBLY OIL DEFLECTOR BEARING | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | ASSEMBLY BRACKET SISI FRONT | 11/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | ASSEMBLY BRACKET SISI REAR | 11/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | RESISTOR RESISTANCE MEASUREMENT | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION & CLEANING PT | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION & CLEANING CT | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | PERMANENT MAGNET GENERATOR (PMG) INSULATION RESISTANCE MEASUREMENT | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION DIODA EXCITER PERMANEN MAGNET GENERATOR (PMG) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION TERMINASI PERMANEN MAGNET GENERATOR (PMG) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION GROUNDING SYSTEM PERMANEN MAGNET GENERATOR (PMG) | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION FUSE PANEL PERMANEN MAGNET GENERATOR (PMG) | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION DISCONNECTING SWITCH NETRAL GROUNDING RESISTANCE (NGR) | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION TRAFO NETRAL GROUNDING RESISTANCE (NGR) | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION ISOLATOR BUSHING NETRAL GROUNDING RESISTANCE (NGR) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION TERMINASI NETRAL GROUNDING RESISTANCE (NGR) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | NEUTRAL GROUNDING RESISTOR (NGR) INSULATION RESISTANCE TEST | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION HEATER BUSDUCT NETRAL GROUNDING RESISTANCE (NGR) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | INSPECTION SILICA BUSDUCT | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0041 | CLEANING | 24/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION ISOLATOR BUSHING | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION TERMINASI | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | CLEANING BUSHING CONNECTION HV & LV | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION And CLEANING PANEL | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION SILICAGEL | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION GROUNDING SYSTEM | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | TRANSFORMER OIL LEAKAGE INSPECTION | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | PROTECTIVE DEVICE TEST AND TRANSFORMER RESET | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION PANEL TAP CHANGER | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | TRANSFORMER WINDING INSULATION RESISTANCE INSPECTION | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | RDS TEST | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | MECHANICAL RELAY TEST | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION DISCONNECTING SWITCH NETRAL GROUNDING RESISTANCE (NGR) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION TRAFO NETRAL GROUNDING RESISTANCE (NGR) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION ISOLATOR BUSHING NETRAL GROUNDING RESISTANCE (NGR) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION TERMINASI NETRAL GROUNDING RESISTANCE (NGR) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION GROUNDING SYSTEM NETRAL GROUNDING RESISTANCE (NGR) | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION HEATER BUSDUCT | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | INSPECTION SILICA BUSDUCT | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0042 | CLEANING | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS101:UNIT 1 SWITCHGEAR 6.6KV INCOMING PANEL (MV UAT 2 CB9) | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS102:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 1 PA FAN 1 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS103:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 2 PA FAN 2 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS104:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 3 SA FAN 1 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS105:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 4 SA FAN 2 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS106:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 5 ID FAN 1 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS107:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 6 ID FAN 2 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS108:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 8 BF PUMP 1 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS109:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 9 BF PUMP 2 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS110:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 7 CW PUMP 3 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS111:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 11 CW PUMP 4 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS112:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 OUTGOING FEEDER 12 CW PUMP 5 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS113:UNIT 1 SWITCHGEAR 6,6KV UNIT 1 TRAFO FEEDER | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | UNIT 1 SWITCHGEAR 6,6KV UNIT 1 ADAPTER | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0043 | MSW10BBA10GS114:UNIT 1 SWITCHGEAR 6,6KV METERING (L10) | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0044 | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 1 | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 2 | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 3 | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | SWITCHGEAR 6,6KV UNIT 1 INCOMMING GENERATOR 4 | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | SWITCHGEAR 6,6KV UNIT 1 OUTGOING TRAFO 1 | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | SWITCHGEAR 6,6KV UNIT 1 OUTGOING TRAFO 2 | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | MSW00BBA10CE201:MV COMMON METERING | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | MSW00BBA10GH201:SWITCHGEAR 6.6KV COMMON BUSTIE RIGHT | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | MSW00BBA10GH202:SWITCHGEAR 6.6KV COMMON BUSTIE LEFT | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0044 | MSW00BBA10GH203:SWITCHGEAR 6.6KV COMMON TRAFO FEEDER | 04/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0045 | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP001) | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP002) | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP003) | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | ACTUATOR TURBINE EXTRACTION III TO DEAERATOR CV 10LBD20AA210 | 10/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | ACTUATOR MOV PREHEATING 1 TURBINE | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | ACTUATOR MOV PREHEATING 2 TURBINE | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE EXTRACTION II TO LPH2 TEMPERATURE TRANSMITTER (20LBD30CT001) | 08/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE EXTRACTION III TO DEAERATOR TEMPERATURE TRANSMITTER (20LBD20CT001) | 20/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE EXTRACTION I TO LPH1 TEMPERATURE TRANSMITTER (20LBD10CT001) | 20/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MSW10MAA10CP302 : UNIT 1 TURBINE BEHIND CONTROL STAGE PRESSURE TRANSMITTER (20MAA10CP001) | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MSW10MAA10CP303 : UNIT 1 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP002) | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MSW10MAA10CP304 : UNIT 1 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP003) | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MSW10MAA10CP305 : UNIT 1 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP004) | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MSW10MAA10CP306 : UNIT 1 TURBINE BEHIND CONTROL STAGE PRESSURE TRANSMITTER (20MAA10CP005) | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MOV TURBINE STEAM EXTRACTION-1 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | MOV TURBINE STEAM EXTRACTION-2 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE CASING TEMPERATURE - INSIDE TRANSMITTER 10MAA10CT012 | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE CASING TEMPERATURE - CENTER TRANSMITTER 10MAA10CT013 | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP TRANSMITTER 10LBD11CT002 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP TRANSMITTER 10LBD11CT001 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR PRDS TO OUTLET EXTRACTION TRANSMITTER 10LBD11CP001 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR PRDS TO OUTLET EXTRACTION II TRANSMITTER 10LBD11CP002 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | FEEDWATER STORAGE TANK PRESSURE TRANSMITTER 10LAA20CP001 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | CONTROL VALVE LPH-1 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | CONTROL VALVE LPH-2 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | LP HEATER 2 TRANSMITTER 10LCC40CL001 | 08/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | LP HEATER 2 TRANSMITTER 10LCC40CL002 | 08/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | LPH II - TUBE SIDE OUTLET TO DEAERATOR TEMP TRANSMITTER 10LCC20CT001 | 08/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | FEEDWATER STORAGE TANK TRANSMITTER 10LAA20CT001 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | CYCLE MAKE UP PUMP DEAERATOR TRANSMITTER 10HGC20CF001 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR TANK LEVEL 1 TRANSMITTER 10LAA20CL001 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR TANK LEVEL 2 TRANSMITTER 10LAA20CL002 | 01/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | DEAERATOR TANK LEVEL 3 TRANSMITTER 10LAA20CL003 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE EXTRACTION III TO DEAERATOR PRESSURE TRANSMITTER 10LBD20CP001 | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE EXTRACTION III TO LPH PRESSURE TRANSMITTER 10LBD30CP001 | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | TURBINE EXTRACTION 1 TO PNEUMATIC OPERATED VALVE PRESSURE TRANSMITTER 10LBS10CP001 | 02/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | LP HEATER 1 TRANSMITTER 10LCC30CL001 | 05/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | LP HEATER 1 TRANSMITTER 10LCC30CL002 | 05/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | FLOW CONDESATE TO LP HEATER 1 TRANSMITTER 10LCA40CF001 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0045 | CONDENSATE TO LP HEATER TRANSMITTER 10LCA40CF001 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH101 : ALARM SYSTEM ADMIN BUILDING | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH102 : ALARM SYSTEM DG SHEET | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH103 : PANEL MAIN FIRE ALARM SYSTEM | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH104 : ALARM SYSTEM DM MCC ROOM | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH105 : ALARM SYSTEM CHP MCC | 24/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH106 : ALARM SYSTEM AHP MCC | 14/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH107 : ALARM SYSTEM COOLING WATER | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH108 : ALARM SYSTEM DM/RW.FW TW PUMP | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH109 : ALARM SYSTEM WORKSHOP OFFICE ROOM | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH110 : ALARM SYSTEM SWAS ROOM | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH111 : ALARM SYSTEM STG BUILDING | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH113 : ALARM SYSTEM SWITCHYARD BUILDING | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0046 | MSW00CYE10GH114 : ALARM SYSTEM REMOTE SUBSTATION BUILDING | 01/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0047 | INSPECTION AND CALIBRATION OXYGEN ANALYZER | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0047 | P.A APH OUTLET FLOW DP TRANSMITTER 10HLA15CF001 | 29/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0047 | P.A APH OUTLET FLOW DP TRANSMITTER 10HLA15CF002 | 29/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0047 | P.A APH OUTLET PRESSURE TRANSMITTER 10HLA15CP001 | 29/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | AIR SUB1 FLOW DP TRANSMITTER 10HJL10CF010 | 31/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | AIR SUB2 FLOW DP TRANSMITTER 10HJL11CF010 | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | SA APH OUTLET FLOW TRANSMITTER 10HLA25CF001 | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | SA APH OUTLET FLOW TRANSMITTER 10HLA25CF002 | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | SA APH OUTLET PRESSURE TRANSMITTER 10HLA25CP001 | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | UNIT 1 SECONDARY AIR FAN IGV SUB 1 20HJL10AA010 | 04/09/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | UNIT 1 SECONDARY AIR FAN IGV SUB 2 20HJL11AA010 | 04/09/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0048 | UNIT 1 SECONDARY AIR FAN IGV SA CONTROL DAMPER 20HLA25AA010 | 04/09/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0049 | PM PC OWS | 10/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0049 | PM PC EWS | 10/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0049 | PM panel RIO | 17/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | INSPECTION & CALIBRATION STEAM DRUM VENTING ISOLATION VALVE | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | INSPECTION & CALIBRATION STEAM DRUM MOV VENTING REGULATING VALVE | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | INSPECTION & CALIBRATION STEAM DRUM CBD ISOLATION VALVE | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | INSPECTION & CALIBRATION STEAM DRUM MOV CBD REGULATING VALVE | 22/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | INSPECTION & CALIBRATION STEAM DRUM IBD ISOLATION VALVE | 22/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | INSPECTION & CALIBRATION STEAM DRUM MOV IBD REGULATING VALVE | 22/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | DRUM LEVEL TRANSMITTER 10HAD10CL001 | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | DRUM LEVEL TRANSMITTER 10HAD10CL002 | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | DRUM LEVEL TRANSMITTER 10HAD10CL003 | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | DRUM PRESSURE TRANSMITTER 10HAD10CP002 | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | DRUM PRESSURE TRANSMITTER 10HAD10CP003 | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0050 | DRUM PRESSURE TRANSMITTER 10HAD10CP001 | 31/08/2026 | JHON | TRUE |  |  | 0
WO-100826-0051 | COMBUSTER ASH DRAIN 1 (BED ASH COOLER DRAIN) MOV 10HHC01AA001 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | LIMESTONE GATE VALVE | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | ACTUATOR BED MATERIAL DISCHARGE GATE VALVE 10ETG31AA01 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | COMBUSTOR LOWER PRESSURE TRANSMITTER 10HHC01CP001 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CP102 : UNIT 1 COMBUSTOR DP WITH GRATE 10HHC01CP011 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CP103 : UNIT 1 COMBUSTOR UPPER DP 10HHC01CP012 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | AIR COMBUSTOR AT LEVEL PRES TRANSMITTER 10HHC01CP060 | 29/8/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CT101 : UNIT 1 COMBUSTOR LOWER TEMP 10HHC01CT011 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CT102 : UNIT 1 COMBUSTOR LOWER TEMP 10HHC01CT012 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CT103 : UNIT 1 COMBUSTOR LOWER TEMP 10HHC01CT013 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CT104 : UNIT 1 COMBUSTOR MIDDLE TEMP 10HHC01CT041 | 11/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CT105 : UNIT 1 COMBUSTOR MIDDLE TEMP 10HHC01CT042 | 14/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | MSW10HHC10CT106 : UNIT 1 COMBUSTOR MIDDLE TEMP 10HHC01CT043 | 14/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | INLET BACKPASS PRESSURE TRANSMITTER 10HBK01CP003 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | INLET BACKPASS PRESSURE TRANSMITTER 10HBK01CP002 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | INLET BACKPASS PRESSURE TRANSMITTER 10HBK01CP001 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | BACKPASS PRESSURE AFTER LT SH TRANSMITTER 10HBK01CP030 | 22/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0051 | BACKPASS PRESSURE AFTER ECO TRANSMITTER 10HBK01CP050 | 31/08/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0052 | CYCLONE TO SEALPOT PRESSURE TRANSMITTER 10HDF01CP001 | 04/09/2026 | M TOHER | TRUE |  |  | 0
WO-100826-0053 | ACTUATOR DAMPER SEALPOT BLOWER 1 | 07/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0053 | ACTUATOR DAMPER SEALPOT BLOWER 2 | 07/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0053 | CALIBRATION PRESSURE TRANSMITTER | 04/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | ERV PRESSURE SWITCH 10LBA20CP502 | 04/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | INSPECTION AND CALIBRATION TEMP TRANSMITTER 10LBA10CT001 | 14/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | INSPECTION AND CALIBRATION TEMP TRANSMITTER 10LBA10CT002 | 14/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | INSPECTION AND CALIBRATION TEMP TRANSMITTER 10LBA10CT003 | 14/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | ACTUATOR MAIN STEAM LINE (START UP BYPASS) TO DEAERATOR PRDS I/L CV 10LBH10AA210 | 04/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | MS START-UP VENT VALVE (REGULATING) MOV 10LBA21AA011 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | MS START-UP VENT VALVE (ISOLATION) MOV 10LBA21AA001 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | MAIN STEAM LIVE PRESSURE TRANSMITTER 10LAB10CP001 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | MAIN STEAM LIVE PRESSURE TRANSMITTER 10LAB10CP002 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | MAIN STEAM LIVE PRESSURE TRANSMITTER 10LAB10CP003 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | INSPECTION AND CALIBRATION FLOW TRANSMITTER 10LBA10CF001 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0054 | INSPECTION AND CALIBRATION FLOW TRANSMITTER 10LBA10CF002 | 01/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0055 | MSW10MAV10-M101 : UNIT 1 JACKING OIL PUMP MOTOR | 07/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0055 | MSW10MAV10CP101 : UNIT 1 JACKING OIL PRESSURE TRANSMITTER | 05/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0056 | INSPEKSI & PM OIL PUMP MOTOR ( AUXILIARY, EMERGENCY, JACKING, BREATHER ) | 14/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0056 | INSPECTION AND CALIBRATION LUB OIL PRESSURE TRANSMITTER 10MAV40CP001 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0056 | INSPECTION AND CALIBRATION LUB OIL PRESSURE TRANSMITTER 10MAV40CP002 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0056 | INSPECTION AND CALIBRATION LUB OIL PRESSURE TRANSMITTER 10MAV40CP003 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP001) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP002) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP003) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | VALVE BLOCK - OUTLET POSITION LIVE STEAM PT (20MAX45CP004) | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | CONTROL OIL PRESSURE PT (20MAX40CP001) | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | VALVE CHEST TEMPERATURE TRANSMITTER 10MAA10CT011 | 20/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0057 | LIVE STEAM PRESSURE TRANSMITTER 10LBA10CP001 | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0058 | CALIBRATION/FUNCTION TEST HP BYPASS CONTROL VALVE 20LBF10AA210 | 29/8/2026 | AMP | TRUE |  |  | 0
WO-100826-0058 | HP BYPASS TEMPERATURE TRANSMITTER 10LBF10CT001 | 20/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0058 | BYPASS PRESSURE TRANSMITTER 10MAG10CP001 | 20/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0058 | MSW10LBF10CG101 : UNIT 1 STEAM BYPASS REDUCING CONTROL VALVE PRESSURE TRANSMITTER | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0058 | MSW10LBF10CP101 : UNIT 1 STEAM BYPASS REDUCING PRESSURE TRANSMITTER 10LBF10CP001 | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0058 | MSW10LBF10CT101 : UNIT 1 STEAM BYPASS REDUCING TEMPERATURE TRANSMITTER | 20/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0059 | DRAIN OF ESV 10MAL10AA210 | 05/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0059 | DRAIN OF CV CHAMBER 10MAL20AA210 | 05/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0059 | TURBINE DRAIN VALVE AFTER FIRST STAGE 10MAL30AA210 | 24/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0059 | TURBINE DRAIN VALVE 10MAL40AA210 | 24/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0059 | TURBINE DRAIN VALVE 10MAL50AA210 | 24/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0059 | TURBINE DRAIN VALVE 10MAL60AA210 | 24/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0059 | TURBINE DRAIN VALVE 10MAL70AA210 | 24/09/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0060 | MSW10MAJ10-M102 : UNIT 1 VACUUM PUMP A MOTOR (MEGGER, INSPEKSI TERMINAL BLOK, And SISTEM COOLING MOTOR) | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0060 | DISCHARGE, SUCTION & VENTING VALVE VACUUM PUMP-1 | 29/8/2026 | MSW | TRUE |  |  | 0
WO-100826-0060 | MSW10MAJ10AA101 : UNIT 1 AIR REMOVAL SYSTEM VACUUM BREAKER SOLENOID VALVE | 29/8/2026 | MSW | TRUE |  |  | 0
WO-100826-0060 | MSW10MAJ10CG101 : UNIT 1 AIR REMOVAL SYSTEM POSITION TRANSMITTER | 29/8/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0061 | MSW10MAJ10-M202 : UNIT 1 VACUUM PUMP B MOTOR (MEGGER, INSPEKSI TERMINAL BLOK, And SISTEM COOLING MOTOR) | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0061 | DISCHARGE, SUCTION & VENTING VALVE VACUUM PUMP-2 | 29/8/2026 | MSW | TRUE |  |  | 0
WO-100826-0061 | MSW10MAJ10AA201 : UNIT 1 AIR REMOVAL SYSTEM VACUUM BREAKER SOLENOID VALVE | 29/8/2026 | MSW | TRUE |  |  | 0
WO-100826-0061 | MSW10MAJ10CG201 : UNIT 1 AIR REMOVAL SYSTEM POSITION TRANSMITTER | 29/8/2026 | M ZAINI | TRUE |  |  | 0
WO-100826-0062 | MSW10MAG10CP103 : UNIT 1 CONDENSER BYPASS PRESSURE TRANSMITTER 10MAG10CP001 | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0062 | COOLING WATER SUPPLY TEMPERATURE TRANSMITTER 10PAB11CT001 | 20/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0062 | COOLING WATER SUPPLY TEMPERATURE TRANSMITTER 10PAB12CT001 | 20/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0062 | COOLING WATER RETURN TEMPERATURE TRANSMITTER 10PAB21CT001 | 20/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0062 | COOLING WATER RETURN TEMPERATURE TRANSMITTER 10PAB22CT001 | 20/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | INSPECTION FRAME MOTOR | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | INSULATION RESISTANCE INSPECTION | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | INSPECTION COOLING FAN | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | WINDING RESISTANCE INSPECTION | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | INSPECTION TERMINASI | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | INSPECTION KONEKSI GROUNDING SYSTEM | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | CALIBRATION LIMIT SWITCH | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | PRESSURE TRANSMITTER CONDENSATE PUMP TO DELIVERY 10LCA30CP001 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0063 | ACTUATOR CONDENSATE PUMP RECIRCULATION CONTROL VALVE 10LCA31AA210 | 07/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0063 | ACTUATOR MAIN CONDENSATE CONTROL VALVE 10LCA30AA240 | 07/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0063 | CEP DISCHARGE ISOLATION VALVE | 07/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0064 | INSPECTION FRAME MOTOR | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | INSULATION RESISTANCE INSPECTION | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | INSPECTION COOLING FAN | 29/8/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | WINDING RESISTANCE INSPECTION | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | INSPECTION TERMINASI | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | INSPECTION KONEKSI GROUNDING SYSTEM | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | CALIBRATION LIMIT SWITCH | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0064 | CEP DISCHARGE ISOLATION VALVE | 07/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | FREQUENCY PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | GENERATOR DIFFERENTIAL PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | SHORT CIRCUIT PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | OVERCURRENT PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | OVERVOLTAGE PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | ROTOR EARTH FAULT PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | STATOR EARTH FAULT PROTECTION TEST | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | REVERSE POWER PROTECTION TEST | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | UNDER EXCITATION PROTECTION TEST | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | OVER EXCITATION PROTECTION TEST | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | NEGATIVE SEQUENCE PROTECTION TEST | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | OVERLOAD PROTECTION TEST | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0065 | CLEANING AND TIGHTENING | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0066 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE PANEL | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0066 | MEMBERSIHKAN FILTER PANEL | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0066 | PEMELIHARAAN FAN CONVERTER UNITROL | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0066 | MEMBERSIHKAN KOMPARTEMEN DALAM PANEL | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0066 | HOUSEKEEPING | 22/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 1 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 2 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 3 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 4 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 5 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 6 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 7 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 8 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 9 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 10 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 11 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | SOOT BLOWER STEAM OUTLET TRANSMITTER 10HCB10CP001 | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | SOOT BLOWER STEAM FLOW TRANSMITTER 10HCB10CF001 | 07/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0067 | ACTUATOR VALVE DRAIN SOOT BLOWER 10HCB10AA201 | 10/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0067 | SOOT BLOWER VALVE MOV 10HCB10AA001 | 10/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0067 | ACTUATOR SOOT BLOWER CONTROL VALVE 10HCB10EX001 | 10/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0068 | PM PC OWS | 11/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0068 | PM PC EWS | 11/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0068 | PM panel RIO | 17/09/2026 | JHON | TRUE |  |  | 0
WO-100826-0069 | INSPEKSI LV TRANSFORMER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | RDC Test LV TRANSFORMER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | FUNGSI RACK OUT RACK IN | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN BUSBAR | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | BUSBAR INSULATION RESISTANCE TEST *)including busbar and busduct | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | BUSBAR CONTACT RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN KABEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN TRAFO KONTROL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN SOOTBLOWER MCC FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN TG MCC FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN KOMPARTEMEN ADAPTER PANEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | BUSTIE BUSDUCT CONTACT RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN ACB INCOMMING | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | INCOMING ACB INSULATION RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | INCOMING ACB CONTACT RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | CB ANALYSIS TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN ACB ESP FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | ESP FEEDER ACB INSULATION RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | ACB CONTACT RESISTANCE TEST ESP FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | ESP FEEDER CB ANALYSIS TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN ACB BOILER FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | ACB CONTACT RESISTANCE TEST BOILER FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | BOILER FEEDER CB ANALYSIS TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | PERAWATAN ACB COOLING TOWER MCC FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | COOLING TOWER FEEDER ACB INSULATION RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | ACB CONTACT RESISTANCE TEST COOLING TOWER FEEDER | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | COOLING TOWER FEEDER CB ANALYSIS TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | INSPECTION HEATER BUSDUCT | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | INSPECTION SILICA BUSDUCT | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0069 | HOUSEKEEPING | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | PERAWATAN KOMPARTEMEN BUSBAR | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | BUSBAR CONTACT RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | PERAWATAN KOMPARTEMEN KABEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | PERAWATAN MODULE WITHDRAWABLE | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | PERAWATAN ACB INCOMMING | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0070 | HOUSEKEEPING | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | PERAWATAN KOMPARTEMEN BUSBAR | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | BUSBAR INSULATION RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | BUSBAR CONTACT RESISTANCE TEST | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | PERAWATAN KOMPARTEMEN KABEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | PERAWATAN MODULE WITHDRAWABLE | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0071 | HOUSEKEEPING | 04/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | PERAWATAN KOMPARTEMEN BUSBAR | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | BUSBAR INSULATION RESISTANCE TEST | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | BUSBAR CONTACT RESISTANCE TEST | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | PERAWATAN KOMPARTEMEN KABEL | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | PERAWATAN MODULE WITHDRAWABLE | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | PERAWATAN ACB INCOMMING | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | INCOMING ACB INSULATION RESISTANCE TEST | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | INCOMING ACB CONTACT RESISTANCE TEST | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | CB ANALYSIS TEST | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0072 | HOUSEKEEPING | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0073 | GLAND STEAM CONDENSER VENTING MOTOR | 01/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0073 | GLAND STEAM PRESSURE TRANSMITTER 10MAW11CP001 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0073 | ACTUATOR GLAND STEAM PRESSURE CONTROL VALVE 10MAW10AA210 | 02/09/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0073 | ACTUATOR GLAND STEAM TEMPERATURE CONTROL VALVE 10LCE10AA210 | 29/8/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0073 | GENERAL CLEANING | 29/8/2026 | H AIDI | TRUE |  |  | 0
WO-100826-0074 | INSPECTION AND CALIBRATION OXYGEN ANALYZER | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0074 | INLET BACKPASS PRESSURE TRANSMITTER | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0074 | INLET BACKPASS PRESSURE TRANSMITTER | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0074 | INLET BACKPASS PRESSURE TRANSMITTER | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0074 | BACKPASS PRESSURE AFTER LT SH TRANSMITTER | 22/08/2026 | FERRYUS | TRUE |  |  | 0
WO-100826-0075 | Panel Bapcon - Rapcon Field 1 | 22/08/2026 | M IQBAL | TRUE |  |  | 0
WO-100826-0075 | Panel Bapcon - Rapcon Field 2 | 22/08/2026 | M IQBAL | TRUE |  |  | 0
WO-100826-0075 | Panel Bapcon - Rapcon Field 3 | 29/8/2026 | M IQBAL | TRUE |  |  | 0
WO-100826-0075 | Panel Bapcon - Rapcon Field 4 | 01/09/2026 | M IQBAL | TRUE |  |  | 0
WO-100826-0075 | Panel Bapcon - Rapcon Field 5 | 01/09/2026 | M IQBAL | TRUE |  |  | 0
WO-100826-0075 | Panel Bapcon - Rapcon Field 6 | 01/09/2026 | M IQBAL | TRUE |  |  | 0
WO-100826-0059 | MOV MAIN STEAM DRAIN | 31/08/2026 |  | TRUE |  |  | 0
WO-100826-0038 | ACTUATOR DESH-1 SPRAY WATER ISOLATION | 29/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0039 | ACTUATOR DESH-2 SPRAY WATER ISOLATION | 08/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0160 | ACTUATOR INLET ID FAN 1 MOV 10HNA61AA001 | 28/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0160 | ACTUATOR OUTLET ID FAN 1 MOV 10HNA71AA001 | 04/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0020 | ACTUATOR MOV OUTLET PA FAN 1 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0020 | ACTUATOR MOV PA FAN 1 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | ACTUATOR ISOLATION STARTUP VENTING BOILER | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0026 | ACTUATOR IGV SA FAN 2 10HLB02EX001 | 30/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0051 | FLUIDIZING VALVE BED MATERIAL | 04/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0051 | FLUIDIZING VALVE LIMESTONE 1&2 | 04/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0050 | ACTUATOR STEAM DRUM VENTING ISOLATION VALVE | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0050 | ACTUATOR STEAM DRUM MOV VENTING VALVE | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0050 | ACTUATOR STEAM DRUM CBD ISOLATION VALVE | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0050 | ACTUATOR STEAM DRUM MOV CBD CONTROL VALVE | 14/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0050 | ACTUATOR STEAM DRUM IBD ISOLATION VALVE | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0050 | ACTUATOR STEAM DRUM MOV IBD CONTROL VALVE | 14/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | ACTUATOR MOV PA FAN2 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0024 | ACTUATOR MOV OUTLET SA FAN 1 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0058 | ACTUATOR HP BYPASS CONTROL VALVE 10LBF10AA210 | 10/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0058 | ACTUATOR BYPASS SPRAY CONTROL VALVE 10LCE40AA210 | 10/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0045 | CEP DISCHARGE VALVE | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0045 | MOV MAIN STEAM DRAIN STG-2 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0045 | ACTUATOR ON/OFF NRV STEAM EXTRACTION 1, 2, 3 | 09/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0063 | ACTUATOR ON/OFF VALVE CEP-1 & CEP-2 | 07/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0037 | ACTUATOR MOV INLET ECONOMIZER | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0037 | ACTUATOR MOV RECIRCULATION ECONOMIZER | 31/08/2026 | MSW | TRUE |  |  | 0
WO-100826-0045 | 10MAA10CP001: PRESSURE BEHIND TURBINE CONTROL | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10MAX45CP004: VALVE BLOCK, OUTLET POSITION LIVE STEAM | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0039 | 10HAH46CT001: TEMPERATURE AFTER DESH 2 | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0039 | 10HAH36CT0010: TEMPERATURE BEFORE DESH 2 | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0038 | 10HAH46CT010: TEMPERATURE AFTER DESH 1 | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0030 | 10HJF13CP302: LDO PRESSURE LOW TRIP FOR LANCES | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0030 | 10HJF13CP303: LDO PRESSURE HIGH TRIP FOR LANCES | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | 10HJG89CP301: LPG GAS PRESSURE BEFORE MTV | 10/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | 10HLB01CP101: DP SWITCH ACRROS LO TANK FOR PA FAN-1 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | 10HLB02CP101: DP SWITCH ACRROS LO TANK FOR SA FAN-1 | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0035 | 10LAC10CP101: DP SWITCH BFP 1 | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0036 | 10LAC30CP101: DP SWITCH BFP 2 | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0038 | ACTUATOR DESH-1 SPRAY WATER CONTROL VALVE | 29/08/2026 | AMP | TRUE |  |  | 0
WO-100826-0045 | MOV DISCHARGE BFP-1 | 02/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0067 | SOOT BLOWER CONTROL VALVE | 10/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0045 | ACTUATOR MOV TURBINE STOP VALVE | 11/09/2026 | MSW | TRUE |  |  | 0
WO-100826-0035 | 10QEB10CP001: P&S BLOWER PRESS OUTLET | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0038 | 10LAE10CF001: DESH 1 SPRAY WATER FLOW | 22/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10LAA10CP001: FEEDWATER STORAGE TANK PRESSURE | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10HGC10CF001: CYCLE MAKE UP PUMP DEAERATOR | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10LAA10CL001: DEAERATOR TANK LEVEL 1 | 01/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10LBD10CP001: TURBINE EXTRACTION III TO DEAERATOR PRESSURE | 10/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10MAA10CP002: TURBINE EXHAUST PRESSURE | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10LAA10CT001: FEEDWATER STORAGE TANK | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10LCC10CT001: LPH II - TUBE SIDE OUTLET TO DEAERATOR TEMP | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0045 | 10LBS10CT001: TURBINE EXTRACTION I TO LPH1 TEMP | 08/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0030 | 10HJN13CP302: ATOM AIR PRESSURE LOW TRIP FOR LANCES | 02/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0074 | 10HBK01CP050: BACKPASS PRESSURE AFTER ECO | 09/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0057 | ACTUATOR TURBINE CONTROL VALVE (GOVERNOR) 10MAA10AA210 | 24/09/2026 | AMP | TRUE |  |  | 0
WO-100826-0052 | 10HNA11CT001: CYCLONE OUTLET TEMPERATURE | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0052 | 10HNA11CT002: CYCLONE OUTLET TEMPERATURE | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0052 | 10HNA11CT003: CYCLONE OUTLET TEMPERATURE | 14/09/2026 | JAPA | TRUE |  |  | 0
WO-100826-0052 | 10HNA01CT001: INLET CYCLONE | 14/09/2026 | JAPA | TRUE |  |  | 0

## ActuatorValve
Equipment_ID | Area | Equipment_Description | KKS | Unit | PIC | Status | Progress_Percent | Finish_Date | General_Inspection_TRUE_FALSE | Function_Test_TRUE_FALSE | Remarks | Findings | Action_Taken | Photo_Count | No_WO
AV-001 | BOILER | ACTUATOR FEED WATER CONTROL VALVE 100% 10LAB30AA210 |  | 1 | AMP | FINISH | 100 | 11/09/2026 | TRUE | TRUE | Testing OK |  |  | 0 | WO-100826-0037
AV-002 | BOILER | ACTUATOR FEED WATER CONTROL VALVE 30% 10LAB30AA210 | 10LAB30AA210 | 1 | AMP | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0037
AV-003 | BOILER | ACTUATOR DESH-1 SPRAY WATER ISOLATION |  | 1 | AMP | FINISH | 100 | 08/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0038
AV-004 | BOILER | ACTUATOR DESH-1 SPRAY WATER CONTROL VALVE |  | 1 | AMP | FINISH | 100 | 29/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0038
AV-005 | BOILER | ACTUATOR DESH-2 SPRAY WATER ISOLATION |  | 1 | AMP | FINISH | 100 | 08/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0038
AV-006 | BOILER | ACTUATOR DESH-2 SPRAY WATER CONTROL VALVE |  | 1 | AMP | FINISH | 100 | 29/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0038
AV-007 | BOILER | ACTUATOR FUEL COAL GATE VALVE 1 (MFT-1) 10HHE11AA01 | 10HHE11AA01 | 1 | AMP | FINISH | 100 | 29/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0028
AV-008 | BOILER | ACTUATOR FUEL COAL GATE VALVE 2 (MFT-2) 10HHE12AA01 | 10HHE12AA01 | 1 | AMP | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0029
AV-009 | ID FAN | ACTUATOR IGV ID FAN 1 10HNC01EX001 | 10HNC01EX001 | 1 | AMP | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0160
AV-010 | ID FAN | ACTUATOR IGV ID FAN 2 10HNC01EX002 | 10HNC01EX002 | 1 | AMP | FINISH | 100 | 02/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0161
AV-011 | ID FAN | ACTUATOR INLET ID FAN 1 MOV 10HNA61AA001 | 10HNA61AA001 | 1 | AMP | FINISH | 100 | 01/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0160
AV-012 | ID FAN | ACTUATOR INLET ID FAN 2 MOV 10HNA62AA001 | 10HNA62AA001 | 1 | AMP | FINISH | 100 | 09/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0161
AV-013 | ID FAN | ACTUATOR OUTLET ID FAN 1 MOV 10HNA71AA001 | 10HNA71AA001 | 1 | AMP | FINISH | 100 | 14/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0052
AV-014 | ID FAN | ACTUATOR OUTLET ID FAN 2 MOV 10HNA72AA001 | 10HNA72AA001 | 1 | AMP | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0161
AV-015 | STG | BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L MOV 10LAE10AA110 | 10LAE10AA110 | 1 | AMP | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0037
AV-016 | STG | ACTUATOR MAIN STEAM LINE (START UP BYPASS) TO DEAERATOR PRDS I/L CV 10LBH10AA210 | 10LBH10AA210 | 1 | AMP | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0054
AV-017 | STG | ACTUATOR BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L CV 10LAE10AA210 | 10LAE10AA210 | 1 | AMP | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0037
AV-018 | STG | ACTUATOR TURBINE EXTRACTION III TO DEAERATOR CV 10LBD10AA210 | 10LBD10AA210 | 1 | AMP | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-019 | STG | MOV DISCHARGE BFP-1 |  | 1 | MSW | FINISH | 100 | 02/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0035
AV-020 | STG | MOV DISCHARGE BFP-2 |  | 1 | MSW | FINISH | 100 | 02/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0036
AV-021 | PA FAN | ACTUATOR MOV OUTLET PA FAN 1 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0020
AV-022 | PA FAN | ACTUATOR MOV PA FAN 1 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0020
AV-023 | BOILER | ACTUATOR ISOLATION STARTUP VENTING BOILER |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0035
AV-024 | BOILER | ACTUATOR IGV SA FAN 1 10HLB01EX001 | 10HLB01EX001 | 1 | MSW | FINISH | 100 | 30/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0024
AV-025 | BOILER | ACTUATOR IGV SA FAN 2 10HLB02EX001 | 10HLB02EX001 | 1 | MSW | FINISH | 100 | 30/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0026
AV-026 | BOILER | ACTUATOR IGV SA CONTROL DAMPER 10HLA25AA010 | 10HLA25AA010 | 1 | MSW | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0048
AV-027 | BOILER | ACTUATOR IGV SUB 1 10HJL10AA010 | 10HJL10AA010 | 1 | MSW | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0048
AV-028 | BOILER | ACTUATOR IGV SUB 2 10HJL11AA010 | 10HJL11AA010 | 1 | MSW | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0048
AV-029 | BOILER | ACTUATOR BED MATERIAL DISCHARGE GATE VALVE 10ETG31AA01 | 10ETG31AA01 | 1 | MSW | FINISH | 100 | 22/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-030 | BOILER | ACTUATOR VALVE DRAIN SOOT BLOWER 10HCB10AA101 | 10HCB10AA101 | 1 | MSW | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0067
AV-031 | BOILER | COMBUSTER ASH DRAIN 1 (BED ASH COLLER DRAIN) MOV 10HHC01AA001 | 10HHC01AA001 | 1 | MSW | FINISH | 100 | 22/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-032 | BOILER | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 | 10HHC01AA002 | 1 | MSW | FINISH | 100 | 22/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-033 | BOILER | SOOT BLOWER CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0067
AV-034 | BOILER | SOOT BLOWER ISOLATION VALVE MOV 10HCB10AA001 | 10HCB10AA001 | 1 | MSW | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0067
AV-035 | BOILER | MS START UP VENT VALVE (REG) MOV 10LBA21AA011 | 10LBA21AA011 | 1 | MSW | FINISH | 100 | 01/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0054
AV-036 | BOILER | MS START UP VENT VALVE (ISO) MOV 10LBA21AA001 | 10LBA21AA001 | 1 | MSW | FINISH | 100 | 01/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0054
AV-037 | BOILER | ACTUATOR SOOT BLOWER CV 10HCB10EX001 | 10HCB10EX001 | 1 | MSW | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0067
AV-038 | BOILER | ACTUATOR DAMPER SEALPOT BLOWER 1 |  | 1 | MSW | FINISH | 100 | 07/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0053
AV-039 | BOILER | ACTUATOR DAMPER SEALPOT BLOWER 2 |  | 1 | MSW | FINISH | 100 | 07/09/2026 | TRUE | TRUE | ganti limit swtich close dan temuan line venting open buntu |  |  | 0 | WO-100826-0053
AV-040 | BOILER | COMBUSTER ASH DRAIN 1 (BED ASH COLLER DRAIN) MOV 10HHC01AA001 | 10HHC01AA001 | 1 | MSW | FINISH | 100 | 22/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-041 | BOILER | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 | 10HHC01AA002 | 1 | MSW | FINISH | 100 | 22/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-042 | BOILER | FLUIDIZING VALVE BED MATERIAL |  | 1 | MSW | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-043 | BOILER | FLUIDIZING VALVE LIMESTONE 1&2 |  | 1 | MSW | FINISH | 100 | 04/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0051
AV-044 | DRUM | ACTUATOR STEAM DRUM VENTING ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0050
AV-045 | DRUM | ACTUATOR STEAM DRUM MOV VENTING VALVE |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0050
AV-046 | DRUM | ACTUATOR STEAM DRUM CBD ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0050
AV-047 | DRUM | ACTUATOR STEAM DRUM MOV CBD CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 14/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0050
AV-048 | DRUM | ACTUATOR STEAM DRUM IBD ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0050
AV-049 | DRUM | ACTUATOR STEAM DRUM MOV IBD CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0050
AV-050 | PA FAN | ACTUATOR MOV OUTLET PA FAN 2 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0020
AV-051 | PA FAN | ACTUATOR MOV PA FAN2 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0020
AV-052 | SA FAN | ACTUATOR MOV OUTLET SA FAN 1 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0020
AV-053 | SA FAN | ACTUATOR MOV OUTLET SA FAN 2 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0020
AV-054 | STG | ACTUATOR HP BYPASS CONTROL VALVE 10LBF10AA210 | 10LBF10AA210 | 1 | MSW | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0058
AV-055 | STG | ACTUATOR CONDENSATE PUMP RECIRCULATION CONTROL VALVE 10LCA31AA210 | 10LCA31AA210 | 1 | MSW | FINISH | 100 | 07/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0063
AV-056 | STG | ACTUATOR MAIN CONDENSATE CONTROL VALVE 10LCA30AA240 | 10LCA30AA240 | 1 | MSW | FINISH | 100 | 07/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0063
AV-057 | STG | ACTUATOR GLAND STEAM PRESSURE CONTROL VALVE 10MAW10AA210 | 10MAW10AA210 | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0073
AV-058 | STG | ACTUATOR GLAND STEAM TEMP. CONTROL VALVE 10LCE10AA210 | 10LCE10AA210 | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0073
AV-059 | STG | ACTUATOR BYPASS SPRAY CONTROL VALVE 10LCE40AA210 | 10LCE40AA210 | 1 | MSW | FINISH | 100 | 10/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0058
AV-060 | STG | CEP DISCHARGE VALVE |  | 1 | MSW | FINISH | 100 | 11/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0063
AV-061 | STG | DISCHARGE, SUCTION & VENTING VALVE VACUM PUMP-1 & 2 |  | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0060
AV-062 | STG | MOV MAIN STEAM DRAIN STG-2 |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-063 | STG | DRAIN OF ESV 10MAL10AA210 | 10MAL10AA210 | 1 | MSW | FINISH | 100 | 05/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-064 | STG | DRAIN OF CV CHAMBER 10MAL10AA210 | 10MAL10AA210 | 1 | MSW | FINISH | 100 | 05/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-065 | STG | TURBINE DRAIN VALVE AFTER FIRST STAGE 10MAL30AA210 | 10MAL30AA210 | 1 | MSW | FINISH | 100 | 24/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-066 | STG | TURBINE DRAIN VALVE 10MAL40AA210 | 10MAL40AA210 | 1 | MSW | FINISH | 100 | 24/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-067 | STG | TURBINE DRAIN VALVE 10MAL50AA210 | 10MAL50AA210 | 1 | MSW | FINISH | 100 | 24/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-068 | STG | TURBINE DRAIN VALVE 10MAL60AA210 | 10MAL60AA210 | 1 | MSW | FINISH | 100 | 24/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-069 | STG | TURBINE DRAIN VALVE 10MAL70AA210 | 10MAL70AA210 | 1 | MSW | FINISH | 100 | 24/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0059
AV-070 | STG | CONTROL VALVE LPH-2 |  | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-071 | STG | CONTROL VALVE LPH-1 |  | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-072 | STG | MOV TURBINE STEAM EXTRACTION-1 & 2 |  | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-073 | STG | ACTUATOR MOV TURBINE STOP VALVE |  | 1 | MSW | FINISH | 100 | 11/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-074 | STG | ACTUATOR MOV PREHEATING 1 TURBINE |  | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-075 | STG | ACTUATOR MOV PREHEATING 2 TURBINE |  | 1 | MSW | FINISH | 100 | 29/8/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-076 | STG | ACTUATOR ON/OFF NRV STEAM EXTRACTION 1, 2, 3 |  | 1 | MSW | FINISH | 100 | 09/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0045
AV-077 | STG | ACTUATOR ON/OFF VALVE CEP-1 & CEP-2 |  | 1 | MSW | FINISH | 100 | 07/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0063
AV-078 | SUB | ACTUATOR SUB BURNER 1 VALVE 10HJN11AA003 | 10HJN11AA003 | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-079 | SUB | ACTUATOR SUB BURNER 2 VALVE 10HJN12AA003 | 10HJN12AA003 | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0031
AV-080 | SUB | ACTUATOR SKID BURNER MAIN LDO LINE CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-081 | SUB | ACTUATOR SKID BURNER 1 LDO LINE CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-082 | SUB | ACTUATOR SKID BURNER 1 ATOMISING AIR LINE CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-083 | SUB | ACTUATOR SKID BURNER 2 LDO LINE CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-084 | SUB | ACTUATOR SKID BURNER 2 ATOMISING AIR LINE CONTROL VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-085 | SUB | ACTUATOR SKID BURNER 1 ATOM AIR ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-086 | SUB | ACTUATOR SKID BURNER 1 LDO ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-087 | SUB | ACTUATOR SKID BURNER 1 SCAVENGING VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-088 | SUB | ACTUATOR SKID BURNER 2 ATOM AIR ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-089 | SUB | ACTUATOR SKID BURNER 2 LDO ISOLATION VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-090 | SUB | ACTUATOR SKID BURNER 2 SCAVENGING VALVE |  | 1 | MSW | FINISH | 100 | 28/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0030
AV-091 | BOILER | ACTUATOR MOV INLET ECONOMIZER |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0037
AV-092 | BOILER | ACTUATOR MOV RECIRCULATION ECONOMIZER |  | 1 | MSW | FINISH | 100 | 31/08/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0037
AV-099 | TURBINE | ACTUATOR TURBINE CONTROL VALVE (GOVERNOR) | 10MAA10AA210 | 1 | MSW | FINISH | 100 | 24/09/2026 | TRUE | TRUE |  |  |  | 0 | WO-100826-0057

## Instrument_PressureTX
No | Area | Equipment | KKS | Unit | Range | Date | Status_WDONE_TRUE_FALSE | Remarks | Findings | Action_Taken | Photo_Count | Calibration_TRUE_FALSE | No_WO
1 | ESP | INLET ID FAN 2 | 10HNA62CP001 | 1 | -70 - 70 mbar | 28/09/2026 | TRUE |  | Testing | Ok | 1 | TRUE | WO-100826-0161
2 | ESP | INLET ID FAN 1 | 10HNA61CP001 | 1 | -70 - 70 mbar | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0160
3 | ESP | INLET PRESSURE ESP | 10HNA41CP001 | 1 | -70 - 70 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0160
4 | ESP | OUTLET PRESSURE ESP | 10HNA41CP002 | 1 | -70 - 70 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0160
5 | Boiler | AIR SUB1 FLOW DP | 10HJL10CF010 | 1 | 0-130mmH2O | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0048
6 | Boiler | P.A APH OUTLET FLOW DP | 10HLA15CF001 | 1 | 0-130 mmH2O |  | TRUE |  |  |  | 0 | TRUE | WO-100826-0047
7 | Boiler | P.A APH OUTLET FLOW DP | 10HLA15CF002 | 1 | 0.0-130.0 mmH2O | 29/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0047
8 | Boiler | P.A APH OUTLET PRESSURE | 10HLA15CP001 | 1 | 0.0-350.0 mbar | 29/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0047
9 | Boiler | ATOM AIR PRESSURE AFTER SUB 1 | 10HJN11CP001 | 1 | 0,7 - 14 Bar | 30/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0030
10 | Boiler | ATOM AIR PRESSURE AFTER SUB 2 | 10HJN12CP001 | 1 | 0-14 Bar | 30/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0031
11 | Boiler | LDO PRESS AFTER SUB2 FCV | 10HJF12CP001 | 1 | 0-20 bar | 29/8/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0031
12 | Boiler | SEALPOT BLOWER PRESS OUTLET | 10HLB41CP001 | 1 | 0-1 bar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0032
13 | Boiler | P&S BLOWER PRESS OUTLET | 10QEB10CP001 | 1 | 0-1500 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0035
14 | Boiler | LDO PRESS AFTER SUB1 FVC | 10HJF11CP001 | 1 | 0-20 bar | 30/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0030
15 | Boiler | AIR SUB2 FLOW DP | 10HJL11CF010 | 1 | 0-130 mmH20 | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0048
16 | Boiler | COMBUSTOR LOWER PRESSURE | 10HHC01CP001 | 1 | 0.0 - 350 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
17 | Boiler | AIR COMBUSTOR AT LEVEL PRES | 10HHC01CP060 | 1 | 0 - 100 mbar | 29/8/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
18 | Boiler | PA FAN 1 OUTLET PRESSURE | 10HLB03CP001 | 1 | 0-350 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0020
19 | Boiler | PA FAN 2 OUTLET PRESSURE | 10HLB04CP001 | 1 | 0-350 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0022
20 | Boiler | SA FAN 1 OUTLET PRESSURE | 10HLB01CP001 | 1 | 0-250 mbar | 04/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0024
21 | Boiler | SA FAN 2 OUTLET PRESSURE | 10HLB02CP001 | 1 | 0-250 mbar | 07/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0026
22 | Boiler | MAIN STEAM FLOW | 10LBA10CF001 | 1 | 0-12500 mmH20 | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
23 | Boiler | MAIN STEAM FLOW | 10LBA10CF002 | 1 | 0-12500 mmH20 | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
24 | Boiler | INLET FEEDWATER FLOW | 10HAC90CF001 | 1 | 0-5000 mmH20 | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0037
25 | Boiler | INLET FEEDWATER FLOW | 10HAC90CF002 | 1 | 0-5000 mmH20 | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0037
26 | Boiler | DISTRIBUTOR LINE TO FEEDWATER | 10LAB30CP001 | 1 | 0-180 bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0037
27 | Boiler | SA APH OUTLET FLOW | 10HLA25CF001 | 1 | 0-130 mmH20 | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0048
28 | Boiler | SA APH OUTLET FLOW | 10HLA25CF002 | 1 | 0 - 130 mmH20 | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0048
29 | Boiler | SA APH OUTLET PRESSURE | 10HLA25CP001 | 1 | 0-250 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0048
30 | Boiler | CYCLONE TO SEALPOT PRESSURE | 10HDF01CP001 | 1 | -39.00 - 196.00 mbar | 04/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0052
31 | Boiler | DESH 1 SPRAY WATER FLOW | 10LAE10CF001 | 1 | 0.0 - 6700.0 mmH20 | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0038
32 | Boiler | BACKPASS PRESSURE AFTER ECO | 10HBK01CP050 | 1 | -70 - 70 mbar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
33 | Boiler | INLET FEEDWATER PRESSURE | 10HAC90CP001 | 1 | 0.00 - 160.00 bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0037
34 | Boiler | COMBUSTOR DP WITH GRATE | 10HHC01CP011 | 1 | 0 -250 mbar | 29/8/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
35 | Boiler | COMBUSTOR UPPER DP | 10HHC01CP012 | 1 | -10 - 60 mbar | 29/8/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
36 | Boiler | BACKPASS PRESSURE AFTER LT SH | 10HBK01CP030 | 1 | -70 - 70 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
37 | Boiler | DRUM LEVEL | 10HAD10CL001 | 1 | -910 - 0 mmH20 | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0050
38 | Boiler | DRUM LEVEL | 10HAD10CL002 | 1 | -910 - 0 mmH20 | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0050
39 | Boiler | DRUM LEVEL | 10HAD10CL003 | 1 | -910 - 0 mmH20 | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0050
40 | Boiler | SOOT BLOWER STEAM OUTLET | 10HCB10CP001 | 1 | 0 - 40 bar | 22/08/2026 | TRUE |  |  |  | 0 |  | WO-100826-0067
41 | Boiler | SOOT BLOWER STEAM FLOW | 10HCB10CF001 | 1 | 30 - 35000 mmH20 | 07/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0067
42 | Boiler | DESH 2 SPRAY WATER FLOW | 10LAE30CF001 | 1 | 16 - 6716 mmH20 | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0039
43 | Boiler | DRUM PRESSURE | 10HAD10CP002 | 1 | 0 - 160 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0050
44 | Boiler | DRUM PRESSURE | 10HAD10CP003 | 1 | 0 - 160 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0050
45 | Boiler | DRUM PRESSURE | 10HAD10CP001 | 1 | 0 - 160 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0050
46 | Boiler | MAIN STEAM LIVE PRESSURE | 10LAB10CP001 | 1 | 0 - 160 Bar | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
47 | Boiler | MAIN STEAM LIVE PRESSURE | 10LAB10CP002 | 1 | 0 - 160 Bar | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
48 | Boiler | MAIN STEAM LIVE PRESSURE | 10LAB10CP003 | 1 | 0 - 160 Bar | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
49 | Boiler | INLET BACKPASS PRESSURE | 10HBK01CP003 | 1 | -70 - 70 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
50 | Boiler | INLET BACKPASS PRESSURE | 10HBK01CP002 | 1 | -70 - 70 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
51 | Boiler | INLET BACKPASS PRESSURE | 10HBK01CP001 | 1 | -70 - 70 mbar | 22/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
52 | STG | DEAERATOR PRDS TO OUTLET EXTRACTION | 10LBD11CP001 | 1 | 0 - 10 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
53 | STG | DEAERATOR PRDS TO OUTLET EXTRACTION II | 10LBD11CP002 | 1 | 0 - 10 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
54 | STG | FEEDWATER STORAGE TANK PRESSURE | 10LAA10CP001 | 1 | 0 - 10 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
55 | STG | LP HEATER 2 | 10LCC40CL001 | 1 | -500 - 0 mmH20 | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
56 | STG | LP HEATER 2 | 10LCC40CL002 | 1 | -500 - 0 mmH20 | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
57 | STG | CYCLE MAKE UP PUMP DEAERATOR | 10HGC10CF001 | 1 | 0 - 100 Kpa | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
58 | STG | DEAERATOR TANK LEVEL 1 | 10LAA10CL001 | 1 | -1750 - 0 mmH20 | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
59 | STG | DEAERATOR TANK LEVEL 2 | 10LAA10CL002 | 1 | -1750 - 0 mmH20 | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
60 | STG | DEAERATOR TANK LEVEL 3 | 10LAA10CL003 | 1 | -1750 - 0 mmH20 | 01/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
61 | STG | TURBINE EXTRACTION III TO DEAERATOR PRESSURE | 10LBD10CP001 | 1 | 0 - 10 Bar | 10/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
62 | STG | TURBINE EXTRACTION III TO LPH PRESSURE | 10LBD30CP001 | 1 | 0 - 4 Bar | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
63 | STG | LIVE STEAM PRESSURE TO BYPASS | 10LBF10CP001 | 1 | 0 - 160 Bar | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0058
64 | STG | TURBINE EXTRACTION 1 TO PNEUMATIC OPERATED VALVE | 10LBS10CP001 | 1 | 0 - 1 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
65 | STG | PRESSURE CONDENSATE PUMP TO DELIVERY | 10LCA30CP001 | 1 | 0 - 25 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0063
66 | STG | CONDENSATE TO LP HEATER | 10LCA40CF001 | 1 | 0 - 2500 mmH20 | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
67 | STG | CONDENSATE PRESSURE TO BYPASS SPRAY | 10LCE40CP001 | 1 | 0 -25 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
68 | STG | CONDENSATE PRESSURE TO BYPASS SPRAY | 10LCE40CP002 | 1 | 0 -25 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
69 | STG | CONDENSATE PRESSURE TO BYPASS SPRAY | 10LCE40CP003 | 1 | 0 -25 Bar | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
70 | STG | PRESSURE BEHIND TURBINE CONTROL | 10MAA10CP001 | 1 | -1 - 99 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
71 | STG | TURBINE EXHAUST PRESSURE | 10MAA10CP002 | 1 | -1 - 0.6 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
72 | STG | TURBINE EXHAUST PRESSURE | 10MAA10CP003 | 1 | -1 - 0.6 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
73 | STG | TURBINE EXHAUST PRESSURE | 10MAA10CP004 | 1 | -1 - 0.6 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
74 | STG | PRESSURE BEHIND TURBINE CONTROL STAGE | 10MAA10CP005 | 1 | -1 - 99 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
75 | STG | BYPASS PRESSURE | 10MAG10CP001 | 1 | -1 - 3 Bar | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0058
76 | STG | LUBRICATION OIL PRESSURE | 10MAV40CP001 | 1 | 0 - 4 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0056
77 | STG | LUBRICATION OIL PRESSURE | 10MAV40CP002 | 1 | 0 - 4 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0056
78 | STG | LUBRICATION OIL PRESSURE | 10MAV40CP003 | 1 | 0 - 4 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0056
79 | STG | GLAND STEAM PRESSURE | 10MAW11CP001 | 1 | 0 - 0.25 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0073
80 | STG | CONTROL OIL PRESSURE | 10MAX40CP001 | 1 | 0 - 16 Bar | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0057
81 | STG | VALVE POSITION BLOCK LIVE STEAM | 10MAX45CP001 | 1 | 0 - 16 Bar | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0057
82 | STG | VALVE POSITION BLOCK LIVE STEAM | 10MAX45CP002 | 1 | 0 - 16 Bar | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0057
83 | STG | VALVE POSITION BLOCK LIVE STEAM | 10MAX45CP003 | 1 | 1 - 16 Bar | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0057
84 | STG | LIVE STEAM PRESSURE | 10LBA10CP001 | 1 | 0 - 160 Bar | 08/09/2026 | TRUE |  | Drift calibration +0.5% | Zero & span recalibrated | 0 | TRUE | WO-100826-0057
85 | STG | FLOW CONDESATE TO LP HEATER 1 | 10LCA40CF001 | 1 | 0 - 2500 mmH20 | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
86 | STG | LP HEATER 1 | 10LCC30CL001 | 1 | -500 - 0 mmH20 | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
87 | STG | LP HEATER 1 | 10LCC30CL002 | 1 | -500 - 0 mmH20 | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
88 | STG | VALVE BLOCK, OUTLET POSITION LIVE STEAM | 10MAX45CP004 | 1 | 0-16 Bar | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0057

## Instrument_TemperatureTX
No | Area | Equipment | KKS | Unit | Range | Finish_Date | Status_WDONE_TRUE_FALSE | Remarks | Findings | Action_Taken | Photo_Count | Calibration_TRUE_FALSE | No_WO
1 | Boiler | TEMPERATURE AFTER DESH 2 | 10HAH46CT001 | 1 | 0-600 °C | 09/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0039
2 | Boiler | TEMPERATURE BEFORE DESH 2 | 10HAH36CT009 | 1 | 0-600 °C | 09/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0039
3 | Boiler | TEMPERATURE BEFORE DESH 2 | 10HAH36CT0010 | 1 | 0-600 °C | 09/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0039
4 | Boiler | TEMPERATURE AFTER DESH 1 | 10HAH46CT010 | 1 | 0-600 °C | 09/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0038
5 | Boiler | CYCLONE OUTLET TEMPERATURE | 10HNA11CT001 | 1 | 0-1200 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0052
6 | Boiler | CYCLONE OUTLET TEMPERATURE | 10HNA11CT002 | 1 | 0-1200 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0052
7 | Boiler | CYCLONE OUTLET TEMPERATURE | 10HNA11CT003 | 1 | 0-1200 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0052
8 | Boiler | COMBUSTOR MIDDLE TEMPERATURE | 10HHC01CT041 | 1 | 0-1200 °C | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
9 | Boiler | COMBUSTOR MIDDLE TEMPERATURE | 10HHC01CT042 | 1 | 0-1200 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
10 | Boiler | COMBUSTOR MIDDLE TEMPERATURE | 10HHC01CT043 | 1 | 0-1200 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
11 | Boiler | INLET CYCLONE | 10HNA01CT001 | 1 | 0-1200 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0052
12 | Boiler | TEMPERATURE AFTER FINAL SH | 10LBA10CT001 | 1 | 0-600 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
13 | Boiler | TEMPERATURE AFTER FINAL SH | 10LBA10CT003 | 1 | 0-600 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
14 | Boiler | TEMPERATURE AFTER FINAL SH | 10LBA10CT002 | 1 | 0-600 °C | 14/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0054
15 | Boiler | COMBUSTOR LOWER TEMPERATURE | 10HHC01CT011 | 1 | 0-1200 °C | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
16 | Boiler | COMBUSTOR LOWER TEMPERATURE | 10HHC01CT012 | 1 | 0-1200 °C | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
17 | Boiler | COMBUSTOR LOWER TEMPERATURE | 10HHC01CT013 | 1 | 0-1200 °C | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0051
18 | STG | FEEDWATER STORAGE TANK | 10LAA10CT001 | 1 | 0-150 °C | 31/08/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
19 | STG | LPH II - TUBE SIDE OUTLET TO DEAERATOR TEMP | 10LCC10CT001 | 1 | 0-150 °C | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
20 | BOP | COOLING WATER SUPPLY TEMP | 10PAB11CT001 | 1 | 0-60 °C | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0062
21 | BOP | COOLING WATER SUPPLY TEMP | 10PAB12CT001 | 1 | 0-60 °C | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0062
22 | BOP | COOLING WATER RETURN TEMP | 10PAB21CT001 | 1 | 0-60 °C | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0062
23 | BOP | COOLING WATER RETURN TEMP | 10PAB22CT001 | 1 | 0-60 °C | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0062
24 | STG | VALVE CHEST TEMPERATURE | 10MAA10CT011 | 1 | 0-600 °C | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0057
25 | STG | TURBINE CASING TEMPERATURE - INSIDE | 10MAA10CT012 | 1 | 0-600 °C | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
26 | STG | TURBINE CASING TEMPERATURE - CENTER | 10MAA10CT013 | 1 | 0-600 °C | 02/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
27 | STG | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP | 10LBD11CT002 | 1 | 0-300 °C | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
28 | STG | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP | 10LBD11CT001 | 1 | 0-300 °C | 11/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
29 | STG | HP BYPASS TEMP | 10LBF10CT001 | 1 | 0-600 | 20/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0058
30 | STG | TURBINE EXTRACTION II TO LPH2 TEMP | 10LBD30CT001 | 1 | 0-300 °C | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
31 | STG | TURBINE EXTRACTION III TO DEAERATOR TEMP | 10LBD10CT001 | 1 | 0-300 °C | 10/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045
32 | STG | TURBINE EXTRACTION I TO LPH1 TEMP | 10LBS10CT001 | 1 | 0-150 °C | 08/09/2026 | TRUE |  |  |  | 0 | TRUE | WO-100826-0045

## Instrument_PressureSwitch
No | Area | Description | KKS | Unit | Sub_Area | Set_Point | Contact_Type_NO_NC | AsFound_Set | AsFound_Reset | AsLeft_Set | AsLeft_Reset | Status_OK_NotOK | Status_WDONE_TRUE_FALSE | Dated | Finish_Date | Remarks | Findings | Action_Taken | Photo_Count | Calibration_TRUE_FALSE | No_WO
1 | BOILER | LDO PRESSURE BEFORE MTV | 10HJF11CP301 | 1 | SUB 1 | 8 Bar (HIGH) | NO | 8 | 9 | 8 | 9 | OK | TRUE | 10/09/2026 | 10/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030
3 | BOILER | LDO PRESSURE LOW TRIP FOR SUB 1 | 10HJF11CP302 | 1 | SUB 1 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030
4 | BOILER | ATOM AIR PRESSURE LOW TRIP FOR SUB 1 | 10HJN11CP302 | 1 | SUB 1 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030
5 | BOILER | LDO PRESSURE HIGH TRIP FOR SUB 1 | 10HJF11CP303 | 1 | SUB 1 | 13.0 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030
6 | BOILER | LDO PRESSURE LOW TRIP FOR SUB 2 | 10HJF12CP302 | 1 | SUB 2 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0031
7 | BOILER | ATOM AIR PRESSURE LOW TRIP FOR SUB 2 | 10HJN12CP302 | 1 | SUB 2 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0031
8 | BOILER | LDO PRESSURE HIGH TRIP FOR SUB 2 | 10HJF12CP303 | 1 | SUB 2 | 13.0 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0031
12 | BOILER | LPG GAS PRESSURE BEFORE MTV | 10HJG89CP301 | 1 | SUB | 1.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 10/09/2026 | 10/09/2026 |  |  |  | 0 | TRUE | WO-100826-0035
13 | BOILER | SCANNER AIR PRESSURE OK 1 | 10HJG69CP301 | 1 | SUB | 0.6 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030
14 | BOILER | SCANNER AIR PRESSURE OK 2 | 10HJG69CP302 | 1 | SUB | 2.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030
15 | BOILER | LO HEADER PRESSURE LOW ALARM FOR PA FAN-1 | 10HLB01CP104 | 1 | PA Fan 1 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0021
16 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-1 START | 10HLB01CP103 | 1 | PA Fan 1 | 0.8 Kg/Cm2 | NO | 0.8 | 0.9 | 0.8 | 0.9 | OK | TRUE | 10/09/2026 | 10/09/2026 |  |  |  | 0 | TRUE | WO-100826-0021
17 | BOILER | PRESSURE SWITCH TO START LO PA FAN-1 STANDBY PUMP | 10HLB01CP102 | 1 | PA Fan 1 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0021
18 | BOILER | DP SWITCH ACRROS LO TANK FOR PA FAN-1 | 10HLB01CP101 | 1 | PA Fan 1 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0021
19 | BOILER | LO HEADER PRESSURE LOW ALARM FOR PA FAN-2 | 10HLB02CP104 | 1 | PA Fan 2 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0023
10 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-2 START | 10HLB02CP103 | 1 | PA Fan 2 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0023
21 | BOILER | PRESSURE SWITCH TO START LO PA FAN-2 STANDBY PUMP | 10HLB02CP102 | 1 | PA Fan 2 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0023
22 | BOILER | DP SWITCH ACRROS LO TANK FOR SA FAN-1 | 10HLB02CP101 | 1 | PA Fan 2 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0025
23 | BOILER | LO HEADER PRESSURE LOW ALARM FOR SA FAN-1 | 10HLB05CP104 | 1 | SA Fan 1 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0025
24 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-1 START | 10HLB05CP103 | 1 | SA Fan 1 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0025
25 | BOILER | PRESSURE SWITCH TO START LO SA FAN-1 STANDBY PUMP | 10HLB05CP102 | 1 | SA Fan 1 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0025
26 | BOILER | DP SWITCH ACRROS LO TANK FOR SA FAN-1 | 10HLB05CP101 | 1 | SA Fan 1 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0025
27 | BOILER | LO HEADER PRESSURE LOW ALARM FOR SA FAN-2 | 10HLB06CP104 | 1 | SA Fan 2 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0027
28 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-2 START | 10HLB06CP103 | 1 | SA Fan 2 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0027
29 | BOILER | PRESSURE SWITCH TO START LO SA FAN-2 STANDBY PUMP | 10HLB06CP102 | 1 | SA Fan 2 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0027
30 | BOILER | DP SWITCH ACRROS LO TANK FOR SA FAN-2 | 10HLB06CP101 | 1 | SA Fan 2 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0027
31 | STG | DP SWITCH BFP 1 | 10LAC10CP101 | 1 | BFP 1 | 0.5 Bar | NO | [5 empty] | TRUE | 08/09/2026 | 08/09/2026 |  |  |  | 0 | TRUE | WO-100826-0035
32 | STG | DP SWITCH BFP 2 | 10LAC30CP101 | 1 | BFP 2 | 0.5 Bar | NO | [5 empty] | TRUE | 08/09/2026 | 08/09/2026 |  |  |  | 0 | TRUE | WO-100826-0036
33 | BOILER | ERV PRESSURE SWITCH | 10LBA10CP502 | 1 | ERV | 93 Bar (HIGH) | NO |  |  |  |  | OK | TRUE | 04/09/2026 | 04/09/2026 |  |  |  | 0 | TRUE | WO-100826-0054
34 | BOILER | ATOM AIR INLET PRESSURE LOW | 10HJN11CP301 | 1 | SUB 1 | 5.0 Kg/Cm2 (LOW) | NO |  |  |  |  | OK | TRUE | 02/09/2026 | 02/09/2026 |  |  |  | 0 | TRUE | WO-100826-0030

## PIC_Scope_Master
Category | Equipment_Scope_Name | Scope_Type_Vendor_MSW | Work_Scope_ME_SI_SE | Activity_Description | PIC | Unit
| 1. BOILER TEST EQUIPMENT | MSW | ME | Insulation resistance measurement, polarization index (PI), winding resistance test, connection check, cooler inspection, excitation system check, PMG, ventilation duct cleaning, grounding check | JHON | 1
| 2. Generator Trafo 40 MVA,11/66 kV | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M ZAINI | 1
| 3. MV Auxiliary Trafo 10 MVA,11/6.6 kV | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M ZAINI | 1
| 4. LV Auxiliary Trafo 2.5 MVA,6.6/0.4 kV | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M IQBAL | 1
| 5. ESP Rectifier Trafo 250 kW,380 VAC/70 kVDC | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M IQBAL | 1
| 6. Panel MV Switchgear 6.6 kV | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 1
| 7. Panel LV PMCC 380 V | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 1
| 8.Panel MCC 380 V (Boiler,Turbin Generator, ESP,AHP) | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 1
| 9. Panel Generator CB | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 1
| 10. Generator Control Panel | Vendor | ME |  | M ZAINI | 1
| 11. Generator Exciter Panel | Vendor | ME |  | M ZAINI | 1
| 12. Panel Bapcon – Rapcon ESP | Vendor | ME |  | M IQBAL | 1
| 13. Panel Inverter LV motor | Vendor | ME |  | M ZAINI | 1
| 14. Panel Soft Starter/FCMA | Vendor | ME |  | H AIDI | 1
| 15. Relay Proteksi | Vendor | ME | Secondary Injection Test to verify relay tripping against time curve and current setting values, event recorder log verification | M ZAINI | 1
| 16. LV Motor 380 V | Vendor | SI | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | YOGA | 1
| 21. Remote Control Panel (RCP) | Vendor | ME |  | M ZAINI | 1
| 22. Busduct Trafo | Vendor | SI | INSULATION RESISTANCE TEST, kontak resistan bagian konduktor, grounding check | M IQBAL | 1
| 23. Busduct Generator | Vendor | SI | INSULATION RESISTANCE TEST, kontak resistan bagian konduktor, grounding check | M IQBAL | 1
| 24. MV Motor Cable 6.6 kV | Vendor | SI | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | H AIDI | 1
| 25. LV Motor Cable 380 V | Vendor | SI | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | M IQBAL | 1
| 26. Electrical Grounding | Vendor | SI | Visual inspection on connections and damage, tightening & cleaning, grounding resistance measurement and verification | YOGA | 1
| 1. Panel DCS | Vendor | SI | Physical inspection of panel (cleanliness, doors, locks, grounding), CPU/I/O/Power Supply LED indicators, panel temperature, and ensuring no active alarms or system faults. | JHON | 1
| 2. Pressure tx range -70~1500 mBar | Vendor | SI | Verification & Calibration | FERRYUS | 1
| 3. Pressure tx range -1~180 Bar | Vendor | SI | Verification & Calibration | FERRYUS | 1
| 4. Flow tx range -500~12500 mmH2O | Vendor | SI | Verification & Calibration | FERRYUS | 1
| 5. Temperature tx range 0 ~ 1200 celcius | Vendor | SI | Verification & Calibration | FERRYUS | 1
| PRESSURE SWITCH | MSW | Verification & Calibration | Verification & Calibration | FERRYUS | 1
| ACTUATOR ON OFF VALVE | MSW | General Inspection | Verification & Calibration | JHON | 1
| IGV CONTROL (SA, SUB) | MSW | General Inspection | Verification & Calibration | JHON | 1
| GOVERNOR VALVE | MSW | General Inspection | Verification & Calibration | JHON | 1
| ACTUATOR CONTROL VALVE | MSW | General Inspection | Verification & Calibration | M TOHER | 1
| ACTUATOR MOTORIZED VALVE | MSW | General Inspection | Verification & Calibration | M TOHER | 1
| LEVEL SWITCH | MSW | Verification & Function Test | Verification & Calibration | FERRYUS | 1
| FIRE ALARM SYSTEM | MSW | Verification & Function Test | Verification & Calibration | M TOHER | 1