## Dashboard_Summary
EIC OUTAGE PROGRESS SUMMARY DASHBOARD — UNIT 1
*This sheet contains automated FORMULAS — do not edit manually. Update data in respective sheets.
1. WORK ORDERS (WorkOrder)
Unit | SCHED-OK | IN PROGRESS | FINISH | TOTAL | % FINISH
2
2. ACTUATOR VALVES (ActuatorValve)
Unit | SCHED-OK | IN PROGRESS | FINISH | TOTAL | % FINISH
2
3. FIELD INSTRUMENT CALIBRATION (Pressure TX + Temperature TX + Pressure Switch)
Unit | COMPLETED (WDONE) | NOT COMPLETED | TOTAL
2
4. FINDINGS SUMMARY (FINDINGS)
Data Source | Total Rows with Recorded Findings
WorkOrder
WorkOrder_Checklist
ActuatorValve
Instrument_PressureTX
Instrument_TemperatureTX
Instrument_PressureSwitch
5. OUTAGE SCHEDULE & S-CURVE PERIOD
Parameter | Date | Notes
Outage Start Date | 2026-07-21 | Official Outage Start Baseline for S-Curve Calculation
Outage Finish Date | 2026-08-31 | Planned Outage Completion Baseline for S-Curve Calculation
Target Duration (Days) | 42 | Total planned outage overhaul window duration in calendar days

## README
DATA TEMPLATE — OUTAGE EIC WORK ORDER MONITORING SYSTEM
MSW POWER PLANT — Unit 1 & Unit 2
INSTRUCTIONS & GUIDELINES:
1. This file is the primary DATA SOURCE read directly by the Outage EIC Monitoring web system.
2. Cells highlighted in YELLOW must be manually filled/updated by field PIC personnel.
3. The 'Temuan' (Findings) and 'Tindak Lanjut' (Action Taken) columns are used for abnormal conditions during inspection.
4. The 'Photo Count' column does NOT need manual entry — it is automatically populated by the web application
when uploading finding photos (stored in Finding/<WO or Component Name>/).
5. The web system can READ and WRITE directly to this file — do not alter column positions or structure
because web parsers map data based on this standard structure.
6. Light green rows on each sheet serve as EXAMPLES — overwrite with actual outage records.
when beginning actual data entry.
7. The 'Unit' column indicates 1 or 2 according to the operating outage unit.
8. For Actuator Valve sheet: equipment list is identical for Unit 1 and Unit 2 –
Unit 1 and Unit 2 — maintain separate status rows per unit,
with same Equipment_ID, but progress/status/findings tracked separately per unit.
SHEET DIRECTORY:
- WorkOrder : Master Work Orders (WO) list for EIC section
- WorkOrder_Checklist : Sub-task breakdown and checklist per WO
- ActuatorValve : Actuator and valve progress monitoring (Unit 1 & 2)
- Instrument_PressureTX : Pressure and flow transmitter calibration
- Instrument_TemperatureTX : Temperature transmitter calibration
- Instrument_PressureSwitch : Pressure switch verification & calibration
- PIC_Scope_Master : Job scope allocation & PIC master (Vendor / MSW)
- Dashboard_Summary : Automated statistical summary (formula protected)

## WorkOrder
No | No_WO | Unit | Job_Description | Area | Schedule_Date | Actual_Start_Date | Finish_Date | Status | PIC | N_Task | Progress_Percent | Scope | Remarks | Findings | Action_Taken | Photo_Count
1 | WO-180726-0003 | 2 | OM EIC Y1 UNIT COMMON COOLING TOWER FAN 3 | COOLING TOWER | 2026-07-21 | 2026-07-25 | 2026-07-25 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
2 | WO-180726-0004 | 2 | OM EIC Y1 UNIT COMMON COOLING TOWER FAN 4 | COOLING TOWER | 2026-07-21 | 2026-07-25 | 2026-07-25 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
3 | WO-180726-0002 | 2 | OM EIC Y1 UNIT COMMON MAIN COOLING WATER PUMP 4 | WATER TREATMENT | 2026-07-21 | 2026-07-23 | 2026-07-23 | FINISH | H AIDI | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
4 | WO-180726-0005 | 2 | OM EIC Y1 UNIT COMMON MAIN COOLING WATER PUMP 5 | WATER TREATMENT | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | H AIDI | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
5 | WO-180726-0006 | 2 | OM EIC Y1 UNIT COMMON AUXILIARY COOLING WATER PUMP 3 | WATER TREATMENT | 2026-07-21 | 2026-07-26 | 2026-07-27 | FINISH | H AIDI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
6 | WO-180726-0007 | 2 | OM EIC Y1 UNIT 2 INDUCED DRAUGHT FAN 1 | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 14 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
7 | WO-180726-0008 | 2 | OM EIC Y1 UNIT 2 INDUCED DRAUGHT FAN 2 | GENERAL | 2026-07-21 | 2026-07-23 | 31/08/2026 | FINISH | M TOHER | 11 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
8 | WO-180726-0009 | 2 | OM EIC Y1 UNIT 2 PRIMARY AIR FAN 1 | GENERAL | 2026-07-21 | 2026-07-22 | 2026-07-22 | FINISH | M ZAINI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
9 | WO-180726-0010 | 2 | OM EIC Y1 UNIT 2 PRIMARY AIR FAN 1 LUBE OIL SYSTEM | GENERAL | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | H AIDI | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
10 | WO-180726-0011 | 2 | OM EIC Y1 UNIT 2 PRIMARY AIR FAN 2 | GENERAL | 2026-07-21 | 2026-07-22 | 2026-07-22 | FINISH | M ZAINI | 10 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
11 | WO-180726-0012 | 2 | OM EIC Y1 UNIT 2 PRIMARY AIR FAN 2 LUBE OIL SYSTEM | GENERAL | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | H AIDI | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
12 | WO-180726-0013 | 2 | OM EIC Y1 UNIT 2 SECONDARY AIR FAN 1 | GENERAL | 2026-07-21 | 2026-07-23 | 2026-07-23 | FINISH | M ZAINI | 11 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
13 | WO-180726-0014 | 2 | OM EIC Y1 UNIT 2 SECONDARY AIR FAN 1 LUBE OIL SYSTEM | GENERAL | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | H AIDI | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
14 | WO-180726-0015 | 2 | OM EIC Y1 UNIT 2 SECONDARY AIR FAN 2 | GENERAL | 2026-07-21 | 2026-07-23 | 2026-07-23 | FINISH | M ZAINI | 11 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
15 | WO-180726-0016 | 2 | OM EIC Y1 UNIT 2 SECONDARY AIR FAN 2 LUBE OIL SYSTEM | GENERAL | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | JHON | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
16 | WO-180726-0017 | 2 | OM EIC Y1 UNIT 2 COAL FEEDER NO 1 | COAL HANDLING | 2026-07-21 | 2026-07-24 | 2026-07-28 | FINISH | H AIDI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
17 | WO-180726-0018 | 2 | OM EIC Y1 UNIT 2 COAL FEEDER NO 2 | COAL HANDLING | 2026-07-21 | 2026-07-24 | 2026-07-28 | FINISH | H AIDI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
18 | WO-180726-0019 | 2 | OM EIC Y1 UNIT 2 LDO START-UP BURNER 1 | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 21 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
19 | WO-180726-0020 | 2 | OM EIC Y1 UNIT 2 LDO START-UP BURNER 2 | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
20 | WO-180726-0021 | 2 | OM EIC Y1 UNIT 2 SEALPOT BLOWER NO 1 | GENERAL | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | FERRYUS | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
21 | WO-180726-0022 | 2 | OM EIC Y1 UNIT 2 SEALPOT BLOWER NO 2 | GENERAL | 2026-07-21 | 2026-07-24 | 2026-07-24 | FINISH | FERRYUS | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
22 | WO-180726-0023 | 2 | OM EIC Y1 UNIT 2 ELECTROSTATIC PRECIPITATOR 1-6 | GENERAL | 2026-07-21 |  |  | FINISH | M IQBAL | 19 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
23 | WO-180726-0024 | 2 | OM EIC Y1 UNIT 2 BOILER FEED PUMP 1 | BOILER | 2026-07-21 | 2026-07-25 | 2026-07-25 | FINISH | YOGA | 25 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
24 | WO-180726-0025 | 2 | OM EIC Y1 UNIT 2 BOILER FEED PUMP 2 | BOILER | 2026-07-21 | 2026-07-25 | 2026-07-25 | FINISH | YOGA | 22 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
25 | WO-180726-0026 | 2 | OM EIC Y1 UNIT 2 FEED WATER LINE | WATER TREATMENT | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
26 | WO-180726-0027 | 2 | OM EIC Y1 UNIT 2 DESH SUPERHEATER LINE 1 | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
27 | WO-180726-0028 | 2 | OM EIC Y1 UNIT 2 DESH SUPERHEATER LINE 2 | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
28 | WO-180726-0029 | 2 | OM EIC Y1 UNIT 2 GENERATOR CIRCUIT BREAKER | GENERAL | 2026-07-21 |  |  | FINISH | M ZAINI | 30 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
29 | WO-180726-0030 | 2 | OM EIC Y1 UNIT 2 GENERATOR | GENERAL | 2026-07-21 |  |  | FINISH | M ZAINI | 40 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
30 | WO-180726-0031 | 2 | OM EIC Y1 UNIT 2 AUXILIARY TRANSFORMER 2 | GENERAL | 2026-07-21 | 2026-07-25 | 2026-07-27 | FINISH | M ZAINI | 24 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
31 | WO-180726-0032 | 2 | OM EIC Y1 UNIT 2 6.6KV MEDIUM VOLTAGE STATION BOARDS PANEL | GENERAL | 2026-07-21 | 2026-07-23 |  | FINISH | M ZAINI | 15 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
32 | WO-180726-0001 | 2 | OM EIC Y1 UNIT 2 MEDIUM VOLTAGE STATION BOARDS COMMON | GENERAL | 2026-07-21 |  |  | FINISH | H AIDI | 10 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
33 | WO-180726-0033 | 2 | OM EIC Y1 UNIT 2 MAIN TURBINE | TURBINE | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 75 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
34 | WO-180726-0034 | 2 | OM EIC 1Y FIRE ALARM LOCAL PANEL ( UNIT 2 ) | GENERAL | 2026-07-21 | 2026-07-21 |  | FINISH | JHON | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
35 | WO-180726-0033 | 2 | OM EIC 1Y UNIT 2 PRIMARY AIR FAN LINE | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | FERRYUS | 75 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
36 | WO-180726-0033 | 2 | OM EIC 1Y UNIT 2 SECONDARY AIR FAN LINE | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | FERRYUS | 75 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
37 | WO-180726-0033 | 2 | OM EIC Y1 UNIT 2 BOILER DISTRIBUTED CONTROL PANEL | BOILER | 2026-07-21 |  | 31/08/2026 | FINISH | JHON | 75 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
38 | WO-180726-0033 | 2 | OM EIC Y1 UNIT 2 BOILER DRUM | BOILER | 2026-07-21 |  | 31/08/2026 | FINISH | JHON | 75 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
39 | WO-180726-0039 | 2 | OM EIC Y1 UNIT 2 COMBUSTOR | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 20 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
40 | WO-180726-0040 | 2 | OM EIC Y1 UNIT 2 CYCLONE | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M TOHER | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
41 | WO-180726-0041 | 2 | OM EIC Y1 UNIT 2 SEALPOT | GENERAL | 2026-07-21 |  |  | FINISH | M ZAINI | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
42 | WO-180726-0042 | 2 | OM EIC Y1 UNIT 2 SUPERHEATER SYSTEM LINE | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M ZAINI | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
43 | WO-180726-0043 | 2 | OM EIC Y1 UNIT 2 JACKING OIL PUMP | GENERAL | 2026-07-21 |  |  | FINISH | M TOHER | 2 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
44 | WO-180726-0044 | 2 | OM EIC Y1 UNIT 2 MAIN OIL PUMP | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | H AIDI | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
45 | WO-180726-0045 | 2 | OM EIC Y1 UNIT 2 TURBINE CONTROL VALVE | TURBINE | 2026-07-21 |  | 31/08/2026 | FINISH | H AIDI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
46 | WO-180726-0046 | 2 | OM EIC Y1 UNIT 2 HP BYPASS VALVE | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | JHON | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
47 | WO-180726-0047 | 2 | OM EIC Y1 UNIT 2 TURBINE DRAINAGE MAIN HEADER LINE TO EXPANSION TUBE | TURBINE | 2026-07-21 |  |  | FINISH | M ZAINI | 7 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
48 | WO-180726-0048 | 2 | OM EIC Y1 UNIT 2 VACUUM PUMP A | GENERAL | 2026-07-21 | 2026-07-23 |  | FINISH | M ZAINI | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
49 | WO-180726-0049 | 2 | OM EIC Y1 UNIT 2 VACUUM PUMP B | GENERAL | 2026-07-21 | 2026-07-23 |  | FINISH | M ZAINI | 4 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
50 | WO-180726-0050 | 2 | OM EIC Y1 UNIT 2 CONDENSER | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | M IQBAL | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
51 | WO-180726-0051 | 2 | OM EIC Y1 UNIT 2 MAIN CONDENSATE PUMP A | GENERAL | 2026-07-21 | 2026-07-25 | 2026-07-25 | FINISH | M ZAINI | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
52 | WO-180726-0052 | 2 | OM EIC Y1 UNIT 2 MAIN CONDENSATE PUMP B | GENERAL | 2026-07-21 | 2026-07-25 | 2026-07-25 | FINISH | M ZAINI | 9 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
53 | WO-180726-0053 | 2 | OM EIC Y1 UNIT 2 GENERATOR CONTROL PANEL | GENERAL | 2026-07-21 | 2026-07-21 | 2026-07-21 | FINISH | JHON | 13 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
54 | WO-180726-0054 | 2 | OM EIC Y1 UNIT 2 GENERATOR EXCITATION PANEL | GENERAL | 2026-07-21 | 2026-07-21 | 2026-07-21 | FINISH | JHON | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
55 | WO-180726-0055 | 2 | OM EIC Y1 UNIT 2 SOOT BLOWER | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | YOGA | 17 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
56 | WO-180726-0056 | 2 | OM EIC Y1 UNIT 2 TURBINE CONTROL PANEL | TURBINE | 2026-07-21 |  |  | FINISH | JHON | 3 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
57 | WO-180726-0057 | 2 | OM EIC Y1 UNIT 2 LV DISTRIBUTION | GENERAL | 2026-07-21 |  |  | FINISH | M IQBAL | 36 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
58 | WO-180726-0058 | 2 | OM EIC Y1 UNIT 2 380V MCC SWICTHGEAR BOILER | BOILER | 2026-07-21 | 2026-07-22 | 2026-07-24 | FINISH | YOGA | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
59 | WO-180726-0059 | 2 | OM EIC Y1 UNIT 2 380V MCC SWICTHGEAR TG | GENERAL | 2026-07-21 |  |  | FINISH | M IQBAL | 8 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
60 | WO-180726-0060 | 2 | OM EIC Y1 UNIT 2 380V MCC SWICTHGEAR ESP | ESP | 2026-07-21 |  |  | FINISH | M IQBAL | 12 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
61 | WO-180726-0061 | 2 | OM Y1 EIC UNIT 2 GLAND STEAM SEALING CONDENSER | GENERAL | 2026-07-21 | 2026-07-23 | 2026-07-23 | FINISH | H AIDI | 5 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
62 | WO-180726-0142 | 2 | OM Y1 EIC UNIT 2 CONVECTIVE PASS | GENERAL | 2026-07-21 |  | 31/08/2026 | FINISH | FERRYUS | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0
63 | WO-180726-0062 | 2 | OM Y1 EIC UNIT 2 FLY ASH HANDLING | GENERAL | 2026-07-21 |  |  | FINISH | M IQBAL | 6 | 100 | SUPERVISE, QC, OTHER TASK AS PER EIC JP |  |  |  | 0

## WorkOrder_Checklist
No_WO | Sub_Task_Description | Date | PIC_Task | Done_TRUE_FALSE | Findings | Action_Taken | Photo_Count
WO-180726-0003 | INSPECTION FRAME MOTOR |  |  | TRUE |  |  | 0
WO-180726-0003 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) |  |  | TRUE |  |  | 0
WO-180726-0003 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) |  |  | TRUE |  |  | 0
WO-180726-0003 | INSULATION RESISTANCE INSPECTION |  |  | TRUE |  |  | 0
WO-180726-0003 | WINDING RESISTANCE INSPECTION |  |  | TRUE |  |  | 0
WO-180726-0003 | INSPECTION COOLING FAN |  |  | TRUE |  |  | 0
WO-180726-0003 | INSPECTION TERMINASI |  |  | TRUE |  |  | 0
WO-180726-0003 | INSPECTION KONEKSI GROUNDING SYSTEM |  |  | TRUE |  |  | 0
WO-180726-0003 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE |  |  | TRUE |  |  | 0
WO-180726-0004 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0004 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0002 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0005 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSPECTION BEARING & REPLACEMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0006 | INSPECTION AND CALIBRATION MEASUREMENT DEVICE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0007 | UNIT 2 INDUCED DRAUGHT FAN 1 INLET GATE ACTUATOR MOV 20HNA61AA001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0007 | UNIT 2 INDUCED DRAUGHT FAN 1 OUTLET GATE ACTUATOR MOV 20HNA71AA001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0007 | MSW20HNC10-M103:UNIT 2 INDUCED DRAUGHT FAN 1 MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | REPOSISI MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | INSPEKSI And CLEANING BALL BEARING DE And NDE (REPLACE BEARING IF NEEDED) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | WINDING RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0007 | UNIT 2 INDUCED DRAUGHT FAN 1 IGV 20HNC01EX001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0007 | INLET ID FAN 1 PRESSURE TRANSMITTER 20HNA61CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0007 | INLET PRESSURE ESP PRESSURE TRANSMITTER 20HNA41CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0007 | OUTLET PRESSURE ESP PRESSURE TRANSMITTER 20HNA41CP002 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0008 | UNIT 2 INDUCED DRAUGHT FAN 2 INLET ACTUATOR MOV 20HNA62AA001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0008 | UNIT 2 INDUCED DRAUGHT FAN 2 OUTLET ACTUATOR MOV 20HNA72AA001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0008 | MSW20HNC10-M203:UNIT 2 INDUCED DRAUGHT FAN 2 MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | REPOSISI MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | INSPEKSI And CLEANING BALL BEARING DE And NDE (REPLACE BEARING IF NEEDED) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | WINDING RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0008 | UNIT 2 INDUCED DRAUGHT FAN 2 IGV 20HNC01EX002 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0008 | INLET ID FAN 2 PRESSURE TRANSMITTER 20HNA62CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0009 | MSW20HLB20-M101:UNIT 2 PRIMARY AIR FAN 1 MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | REPOSISI MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | REPLACE BEARING IF NEEDED | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | WINDING RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0009 | UNIT 2 PRIMARY AIR FAN 1 IGV | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0009 | UNIT 2 PRIMARY AIR FAN 1 OUTLET MOV | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0009 | PA FAN 1 OUTLET PRESSURE TRANSMITTER 20HLB03CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0010 | MSW20HLN20-M101:UNIT 2 PRIMARY AIR FAN 1 LUBE OIL PUMP 1 MOTOR (STAND BY) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0010 | MSW20HLN20-M102:UNIT 2 PRIMARY AIR FAN 1 LUBE OIL PUMP 2 MOTOR (MAIN) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0010 | 20HLB01CP104: LO HEADER PRESSURE LOW ALARM FOR PA FAN-1 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0010 | 20HLB01CP103: PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-1 START | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0010 | 20HLB01CP102: PRESSURE SWITCH TO START LO PA FAN-1 STANDBY PUMP | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0010 | 20HLB01CP101: DP SWITCH ACROSS LO TANK FOR PA FAN-1 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0011 | REPOSISI MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | REPLACE BEARING IF NEEDED | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | WINDING RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | UNIT 2 PRIMARY AIR FAN 2 IGV | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | MSW20HLB20AA202:UNIT 2 PRIMARY AIR FAN 2 OUTLET MOV | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0011 | PA FAN 2 OUTLET PRESSURE TRANSMITTER 20HLB04CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0012 | MSW20HLN20-M201:UNIT 2 PRIMARY AIR FAN 2 LUBE OIL PUMP 1 MOTOR (STAND BY) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0012 | MSW20HLN20-M202:UNIT 2 PRIMARY AIR FAN 2 LUBE OIL PUMP 2 MOTOR (MAIN) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0012 | 20HLB02CP104: LO HEADER PRESSURE LOW ALARM FOR PA FAN-2 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0012 | 20HLB02CP103: PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-2 START | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0012 | 20HLB02CP102: PRESSURE SWITCH TO START LO PA FAN-2 STANDBY PUMP | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0012 | MSW20HLN20CL201:UNIT 2 PRIMARY AIR FAN 2 LUBE OIL TANK LEVEL SWITCH | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | REPOSISI MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | REPLACE BEARING IF NEEDED | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | WINDING RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | UNIT 2 SECONDARY AIR FAN 1 OUTLET MOV | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0013 | SA FAN 1 OUTLET PRESSURE TRANSMITTER 20HLB01CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0013 | UNIT 2 SECONDARY AIR FAN 1 IGV SA FAN 1 20HLB01EX001 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0014 | MSW20HLN10-M101:UNIT 2 SECONDARY AIR FAN 1 LUBE OIL PUMP 1 MOTOR (STAND BY) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0014 | MSW20HLN10-M102:UNIT 2 SECONDARY AIR FAN 1 LUBE OIL PUMP 2 MOTOR (MAIN) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0014 | 20HLB02CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-1 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0014 | 20HLB05CP104: LO HEADER PRESSURE LOW ALARM FOR SA FAN-1 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0014 | 20HLB05CP103: PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-1 START | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0014 | 20HLB05CP102: PRESSURE SWITCH TO START LO SA FAN-1 STANDBY PUMP | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0014 | 20HLB05CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-1 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0015 | REPOSISI MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | DISSASEMBLY COVER FAN And COVER BEARING SISI DE And NDE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | INSPEKSI And CLEANING BALL BEARING DE And NDE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | REPLACE BEARING IF NEEDED | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | BEARING REGREASING AND INSULATION RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | WINDING RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | ASSEMBLY ALL PART AND REPOSISI MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | UNIT 2 SECONDARY AIR FAN 1 OUTLET MOV | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | UNIT 2 SECONDARY AIR FAN 1 IGV SA FAN 2 20HLB01EX001 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0015 | SA FAN 2 OUTLET PRESSURE TRANSMITTER 20HLB02CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0016 | MSW20HLN10-M201:UNIT 2 SECONDARY AIR FAN 2 LUBE OIL PUMP 1 MOTOR (STAND BY) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0016 | MSW20HLN10-M202:UNIT 2 SECONDARY AIR FAN 2 LUBE OIL PUMP 2 MOTOR (MAIN) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0016 | 20HLB06CP104: LO HEADER PRESSURE LOW ALARM FOR SA FAN-2 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0016 | 20HLB06CP103: PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-2 START | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0016 | 20HLB06CP102: PRESSURE SWITCH TO START LO SA FAN-2 STANDBY PUMP | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0016 | 20HLB06CP101: DP SWITCH ACROSS LO TANK FOR SA FAN-2 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION FRAME MOTOR DRAG CHAIN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION FRAME MOTOR ROTARY AIR LOCK | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0017 | INSPECTION OF MFT ACTUATOR 20HHE11AA01 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION FRAME MOTOR DRAG CHAIN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION FRAME MOTOR ROTARY AIR LOCK | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0018 | INSPECTION OF MFT ACTUATOR 20HHE12AA01 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0019 | INSPECTION OF IGNITER GUN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | INSPECTION OF START UP BURNER SKID DEVICE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | LDO PRESSURE BEFORE MTV SWITCH 20HJF11CP301 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | ATOM AIR INLET PRESSURE LOW SWITCH 20HJN11CP301 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | LDO PRESSURE LOW TRIP FOR SUB 1 SWITCH 20HJF11CP302 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | ATOM AIR PRESSURE LOW TRIP FOR SUB 1 SWITCH 20HJN11CP302 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | LDO PRESSURE HIGH TRIP FOR SUB 1 SWITCH 20HJF11CP303 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | SCANNER AIR PRESSURE OK 1 SWITCH 20HJG69CP301 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | SCANNER AIR PRESSURE OK 2 SWITCH 20HJG69CP302 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SKID BURNER MAIN LDO LINE CONTROL VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SKID BURNER 1 LDO LINE CONTROL VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SKID BURNER 1 ATOMISING AIR LINE CONTROL VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SUB BURNER 1 VALVE 20HJN11AA003 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SKID BURNER 1 ATOM AIR ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SKID BURNER 1 LDO ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ACTUATOR SKID BURNER 1 SCAVENGING VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0019 | ATOM AIR PRESSURE AFTER SUB 1 TRANSMITTER 20HJN11CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0019 | LDO PRESS AFTER SUB1 FVC TRANSMITTER 20HJF11CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0020 | INSPECTION OF IGNITER GUN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | INSPECTION OF START UP BURNER SKID DEVICE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | LDO PRESSURE LOW TRIP FOR SUB 2 SWITCH 20HJF12CP302 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0020 | ATOM AIR PRESSURE LOW TRIP FOR SUB 2 SWITCH 20HJN12CP302 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0020 | LDO PRESSURE HIGH TRIP FOR SUB 2 SWITCH 20HJF12CP303 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0020 | ATOM AIR PRESSURE AFTER SUB 2 TRANSMITTER 20HJN12CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0020 | LDO PRESS AFTER SUB2 FCV TRANSMITTER 20HJF12CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0020 | ACTUATOR SKID BURNER 2 LDO LINE CONTROL VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | ACTUATOR SKID BURNER 2 ATOMISING AIR LINE CONTROL VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | ACTUATOR SKID BURNER 2 ATOM AIR ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | ACTUATOR SKID BURNER 2 LDO ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | ACTUATOR SKID BURNER 2 SCAVENGING VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0020 | ACTUATOR SUB BURNER 2 VALVE 20HJN12AA003 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | BEARING REPLACEMENT (IF NECESSARY) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0021 | SEALPOT BLOWER PRESS OUTLET TRANSMITTER 20HLB41CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0021 | P&S BLOWER PRESS OUTLET TRANSMITTER 20QEB20CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0022 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0022 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0022 | BEARING REPLACEMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0022 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0022 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0022 | INSPECTION TERMINASI | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0022 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M101:UNIT 2 ESP RAPPING MOTOR (GDRM) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M102:UNIT 2 ESP RAPPING MOTOR (CERM-1) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M103:UNIT 2 ESP RAPPING MOTOR (CERM-2) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M104:UNIT 2 ESP RAPPING MOTOR (CERM-3) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M105:UNIT 2 ESP RAPPING MOTOR (CERM-4) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M106:UNIT 2 ESP RAPPING MOTOR (CERM-5) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M107:UNIT 2 ESP RAPPING MOTOR (CERM-6) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M108:UNIT 2 ESP RAPPING MOTOR (EERM-1) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M109:UNIT 2 ESP RAPPING MOTOR (EERM-2) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M110:UNIT 2 ESP RAPPING MOTOR (EERM-3) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M120:UNIT 2 ESP RAPPING MOTOR (EERM-4) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M130:UNIT 2 ESP RAPPING MOTOR (EERM-5) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | MSW20HDE10-M140:UNIT 2 ESP RAPPING MOTOR (EERM-6) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | UNIT 2 ESP TRAFO 1 (GENERAL CLEANING, INSPEKSI, IR TEST) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | UNIT 2 ESP TRAFO 2 (GENERAL CLEANING, INSPEKSI, IR TEST) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | UNIT 2 ESP TRAFO 3 (GENERAL CLEANING, INSPEKSI, IR TEST) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | UNIT 2 ESP TRAFO 4 (GENERAL CLEANING, INSPEKSI, IR TEST) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | UNIT 2 ESP TRAFO 5 (GENERAL CLEANING, INSPEKSI, IR TEST) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0023 | UNIT 2 ESP TRAFO 6 (GENERAL CLEANING, INSPEKSI, IR TEST) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | INSPECTION TERMINASI | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10-M101:MOV DISCHARGE BFP-1 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10AA104:UNIT 2 BOILER FEED PUMP 1 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10AA105:UNIT 2 BOILER FEED PUMP 1 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CG101:UNIT 2 BOILER FEED PUMP 1 LIMIT SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | 20LAC10CP101:UNIT 2 BOILER FEED PUMP 1 PRESSURE DIFFERENTIAL SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT101:UNIT 2 BOILER FEED PUMP 1 R PHASE WDG TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT102:UNIT 2 BOILER FEED PUMP 1 B PHASE WDG TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT103:UNIT 2 BOILER FEED PUMP 1 B PHASE WDG TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT104:UNIT 2 BOILER FEED PUMP 1 B NDE MOTOR BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT105:UNIT 2 BOILER FEED PUMP 1 B NDE MOTOR BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT106:UNIT 2 BOILER FEED PUMP 1 B NDE PUMP BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10CT107:UNIT 2 BOILER FEED PUMP 1 B NDE PUMP BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0024 | MSW20LAC10GH101:UNIT 2 BOILER FEED PUMP 1 FCMA PANEL | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | INSPECTION BEARING And REPLACEMENT (JIKA DIPERLUKAN) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | INSPECTION TERMINASI | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0025 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10-M201:MOV DISCHARGE BFP-2 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10AA204:UNIT 2 BOILER FEED PUMP 2 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10AA205:UNIT 2 BOILER FEED PUMP 2 VALVE FOR PRESSURE DIFFERENTIAL SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CG201:UNIT 2 BOILER FEED PUMP 2 LIMIT SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CP201:UNIT 2 BOILER FEED PUMP 2 PRESSURE DIFFERENTIAL SWITCH | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT201:UNIT 2 BOILER FEED PUMP 2 R PHASE WDG TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT202:UNIT 2 BOILER FEED PUMP 2 B PHASE WDG TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT203:UNIT 2 BOILER FEED PUMP 2 B PHASE WDG TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT204:UNIT 2 BOILER FEED PUMP 2 B NDE MOTOR BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT205:UNIT 2 BOILER FEED PUMP 2 B NDE MOTOR BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT206:UNIT 2 BOILER FEED PUMP 2 B NDE PUMP BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10CT207:UNIT 2 BOILER FEED PUMP 2 B NDE PUMP BEARING TEMPERATURE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0025 | MSW20LAC10GH201:UNIT 2 BOILER FEED PUMP 2 FCMA PANEL | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0026 | UNIT 2 FEED WATER INLET ECONOMIZER MOTORIZED VALVE MOTOR 100% 20LAB30AA220 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0026 | UNIT 2 FEED WATER INLET ECONOMIZER MOTORIZED VALVE ISOLATION VALVE | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0026 | UNIT 2 FEED WATER INLET ECONOMIZER MOTORIZED VALVE MOTOR 30% 20LAB30AA210 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0026 | UNIT 2 FEED WATER INLET ECONOMIZER MOTORIZED VALVE ISOLATION VALVE | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0026 | ACTUATOR BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L CV 20LAE10AA210 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0026 | BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L MOV 20LAE10AA110 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0026 | DISTRIBUTOR LINE TO FEEDWATER TRANSMITTER 20LAB30CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0026 | INLET FEEDWATER PRESSURE TRANSMITTER 20HAC90CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0026 | INLET FEEDWATER FLOW TRANSMITTER 20HAC90CF001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0026 | INLET FEEDWATER FLOW TRANSMITTER 20HAC90CF002 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0027 | CALIBRATION PRESSURE GAUGE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0027 | CALIBRATION/FUNCTION TEST SPRAY CONTROL VALVE 20LAE10EX001 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0027 | CALIBRATION/FUNCTION ISOLATION (ON/OFF) VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0027 | DESH 1 SPRAY WATER FLOW TRANSMITTER 20LAE20CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0028 | DESH 2 SPRAY WATER FLOW TRANSMITTER 20LAE30CF001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0028 | CALIBRATION/FUNCTION TEST SPRAY CONTROL VALVE 20LAE12EX001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0028 | BEFORE DESH 2 TEMP TRANSMITTER CALIBRATION (20HAH46CT001, 20HAH36CT009, 20HAH36CT009) | 31/08/2026 | MSW | TRUE |  |  | 0
WO-180726-0028 | CALIBRATION/FUNCTION ISOLATION (ON/OFF) VALVE | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0029 | INSPECTION MEKANIK PENGGERAK | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION MOTOR CHARGING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION BEARING DRIVE RACK OUT/IN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | REGREASING SOCKET MAIN KONTAK | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION SYSTEM KONTROL | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | TEST KESEREMPAKAN | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSULATION RESISTANCE INSPECTION KONTAK | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSULATION RESISTANCE INSPECTION BUS BAR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | FUNCTION TEST | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | MOTOR CHARGING, CLOSING AND TRIPPING COIL RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION MODUL CONTROL BREAKER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION LAMPU SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INDIKATOR And LAMPU PANEL SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | DC POWER TESTING FOR 6.3 KV GCB SWITCHGEAR CONTROL SUPPLY | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION HEATER CUBICLE SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION And CLEANING TERMINASI SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION AND PROTECTION RELAY TESTING FOR GCB SWITCHGEAR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION GROUNDING SYSTEM SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSULATION RESISTANCE INSPECTION BUS BAR SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION CT & PT SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | FUNCTION TEST SWITCH GEAR GCB | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION HEATER SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION DISPLAY BREAKER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION HEATER BUSDUCT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION SILICA BUSDUCT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION CONTACT RESISTANCE BUSDUCT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0029 | INSPECTION ISOLATION RESISTANCE BUSDUCT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0030 | DISASSEMBLY BRACKET GENERATOR SISI FRONT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | DISASSEMBLY BRACKET GENERATOR SISI REAR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | DISASSEMBLY OIL DEFLECTOR BEARING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | CLEANING BODY GENERATOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | CLEANING OIL DEFLECTOR BEARING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | CLEANING BOLT & NUT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION OIL DEFLECTOR BEARING 3 & 4 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION SHROUD & FAN BLADE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION STATOR GENERATOR (IR, PI) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION ROTOR GENERATOR (IR, PI, RSO) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION VISUAL ISOLATOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION ROTOR GROUNDING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION VISUAL FLEXIBLE ISOLATOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION BRUSH GROUNDING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSULATION RESISTANCE INSPECTION GENERATOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION HEATER NEUTRAL SIDE CUBICLE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION HEATER LINE SIDE CUBICLE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | ASSEMBLY OIL DEFLECTOR BEARING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | ASSEMBLY BRACKET SISI FRONT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | ASSEMBLY BRACKET SISI REAR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | RESISTOR RESISTANCE MEASUREMENT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION & CLEANING PT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION & CLEANING CT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSULATION RESISTANCE MEASUREMENT PERMANEN MAGNET GENERATOR (PMG) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION DIODA EXCITER PERMANEN MAGNET GENERATOR (PMG) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION TERMINASI PERMANEN MAGNET GENERATOR (PMG) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION GROUNDING SYSTEM PERMANEN MAGNET GENERATOR (PMG) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION FUSE PANEL PERMANEN MAGNET GENERATOR (PMG) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION DISCONNECTING SWITCH NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION TRAFO NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION ISOLATOR BUSHING NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION TERMINASI NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | NEUTRAL GROUNDING RESISTOR (NGR) INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION HEATER BUSDUCT NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION SILICA BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION CONTACT RESISTANCE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | INSPECTION ISOLATION RESISTANCE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0030 | CLEANING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION ISOLATOR BUSHING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION TERMINASI | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | CLEANING BUSHING CONNECTION HV & LV | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION And CLEANING PANEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION SILICAGEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION GROUNDING SYSTEM | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | TRANSFORMER OIL LEAKAGE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | PROTECTIVE DEVICE TEST AND TRANSFORMER RESET | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION PANEL TAP CHANGER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | TRANSFORMER WINDING INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | RDS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | MECHANICAL RELAY TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION DISCONNECTING SWITCH NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION TRAFO NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION ISOLATOR BUSHING NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION TERMINASI NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION GROUNDING SYSTEM NETRAL GROUNDING RESISTANCE (NGR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION HEATER BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION SILICA BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION CONTACT RESISTANCE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | INSPECTION ISOLATION RESISTANCE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0031 | CLEANING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS101:UNIT 2 SWITCHGEAR 6.6KV INCOMING PANEL (MV UAT 2 CB9) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS102:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 1 PA FAN 1 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS103:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 2 PA FAN 2 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS104:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 3 SA FAN 1 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS105:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 4 SA FAN 2 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS106:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 5 ID FAN 1 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS107:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 6 ID FAN 2 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS108:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 8 BF PUMP 1 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS109:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 9 BF PUMP 2 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS110:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 7 CW PUMP 3 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS111:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 11 CW PUMP 4 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS112:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 OUTGOING FEEDER 12 CW PUMP 5 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS113:UNIT 2 SWITCHGEAR 6,6KV UNIT 2 TRAFO FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | UNIT 2 SWITCHGEAR 6,6KV UNIT 2 ADAPTER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0032 | MSW20BBA10GS114:UNIT 2 SWITCHGEAR 6,6KV METERING (L10) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0001 | SWITCHGEAR 6,6KV UNIT 2 INCOMMING GENERATOR 1 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | SWITCHGEAR 6,6KV UNIT 2 INCOMMING GENERATOR 2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | SWITCHGEAR 6,6KV UNIT 2 INCOMMING GENERATOR 3 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | SWITCHGEAR 6,6KV UNIT 2 INCOMMING GENERATOR 4 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | SWITCHGEAR 6,6KV UNIT 2 OUTGOING TRAFO 1 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | SWITCHGEAR 6,6KV UNIT 2 OUTGOING TRAFO 2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | MSW00BBA10CE201:MV COMMON METERING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | MSW00BBA10GH201:SWITCHGEAR 6.6KV COMMON BUSTIE RIGHT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | MSW00BBA10GH202:SWITCHGEAR 6.6KV COMMON BUSTIE LEFT | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0001 | MSW00BBA10GH203:SWITCHGEAR 6.6KV COMMON TRAFO FEEDER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP001) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP002) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | CONDENSATE PRESSURE TO BYPASS SPRAY PRESSURE TRANSMITTER (20LCE40CP003) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR TURBINE EXTRACTION III TO DEAERATOR CV 20LBD20AA210 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR MOV TURBINE STOP VALVE UNIT 2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR MOV PREHEATING 1 TURBINE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR MOV PREHEATING 2 TURBINE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE EXTRACTION II TO LPH2 TEMPERATURE TRANSMITTER (20LBD30CT001) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE EXTRACTION III TO DEAERATOR TEMPERATURE TRANSMITTER (20LBD20CT001) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE EXTRACTION I TO LPH1 TEMPERATURE TRANSMITTER (20LBD10CT001) | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | MSW20MAA10CP302 : UNIT 2 TURBINE BEHIND CONTROL STAGE PRESSURE TRANSMITTER (20MAA10CP001) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | MSW20MAA10CP303 : UNIT 2 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP002) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | MSW20MAA10CP304 : UNIT 2 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP003) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | MSW20MAA10CP305 : UNIT 2 TURBINE EXHAUST PRESSURE TRANSMITTER (20MAA10CP004) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | MSW20MAA10CP306 : UNIT 2 TURBINE BEHIND CONTROL STAGE PRESSURE TRANSMITTER (20MAA10CP005) | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | MOV TURBINE STEAM EXTRACTION-1 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | MOV TURBINE STEAM EXTRACTION-2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | MOV MAIN STEAM DRAIN STG-2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE CASING TEMPERATURE - INSIDE TRANSMITTER 20MAA10CT012 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE CASING TEMPERATURE - CENTER TRANSMITTER 20MAA10CT013 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP TRANSMITTER 20LBD11CT002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP TRANSMITTER 20LBD11CT001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR PRDS TO OUTLET EXTRACTION TRANSMITTER 20LBD11CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR PRDS TO OUTLET EXTRACTION II TRANSMITTER 20LBD11CP002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | FEEDWATER STORAGE TANK PRESSURE TRANSMITTER 20LAA20CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | CONTROL VALVE LPH-1 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | CONTROL VALVE LPH-2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | LP HEATER 2 TRANSMITTER 20LCC40CL001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | LP HEATER 2 TRANSMITTER 20LCC40CL002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | LPH II - TUBE SIDE OUTLET TO DEAERATOR TEMP TRANSMITTER 20LCC20CT001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | FEEDWATER STORAGE TANK TRANSMITTER 20LAA20CT001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | CYCLE MAKE UP PUMP DEAERATOR TRANSMITTER 20HGC20CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR TANK LEVEL 1 TRANSMITTER 20LAA20CL001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR TANK LEVEL 2 TRANSMITTER 20LAA20CL002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DEAERATOR TANK LEVEL 3 TRANSMITTER 20LAA20CL003 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE EXTRACTION III TO DEAERATOR PRESSURE TRANSMITTER 20LBD20CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE EXTRACTION III TO LPH PRESSURE TRANSMITTER 20LBD30CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | TURBINE EXTRACTION 1 TO PNEUMATIC OPERATED VALVE PRESSURE TRANSMITTER 20LBS10CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | LP HEATER 1 TRANSMITTER 20LCC30CL001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | LP HEATER 1 TRANSMITTER 20LCC30CL002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | FLOW CONDESATE TO LP HEATER 1 TRANSMITTER 20LCA40CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | CONDENSATE TO LP HEATER TRANSMITTER 20LCA40CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH101 : ALARM SYSTEM ADMIN BUILDING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH102 : ALARM SYSTEM DG SHEET | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH103 : PANEL MAIN FIRE ALARM SYSTEM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH104 : ALARM SYSTEM DM MCC ROOM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH105 : ALARM SYSTEM CHP MCC | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH106 : ALARM SYSTEM AHP MCC | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH107 : ALARM SYSTEM COOLING WATER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH108 : ALARM SYSTEM DM/RW.FW TW PUMP | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH109 : ALARM SYSTEM WORKSHOP OFFICE ROOM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH110 : ALARM SYSTEM SWAS ROOM | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH111 : ALARM SYSTEM STG BUILDING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH113 : ALARM SYSTEM SWITCHYARD BUILDING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0034 | MSW00CYE10GH114 : ALARM SYSTEM REMOTE SUBSTATION BUILDING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION AND CALIBRATION OXYGEN ANALYZER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | P.A APH OUTLET FLOW DP TRANSMITTER 20HLA15CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | P.A APH OUTLET FLOW DP TRANSMITTER 20HLA15CF002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | P.A APH OUTLET PRESSURE TRANSMITTER 20HLA15CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | AIR SUB1 FLOW DP TRANSMITTER 20HJL10CF010 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | AIR SUB2 FLOW DP TRANSMITTER 20HJL11CF010 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | SA APH OUTLET FLOW TRANSMITTER 20HLA25CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | SA APH OUTLET FLOW TRANSMITTER 20HLA25CF002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | SA APH OUTLET PRESSURE TRANSMITTER 20HLA25CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | UNIT 2 SECONDARY AIR FAN IGV SUB 1 20HJL10AA010 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | UNIT 2 SECONDARY AIR FAN IGV SUB 2 20HJL11AA010 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | UNIT 2 SECONDARY AIR FAN IGV SA CONTROL DAMPER 20HLA25AA010 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | PM PC OWS | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | PM PC EWS | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | PM panel RIO | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION & CALIBRATION STEAM DRUM VENTING ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION & CALIBRATION STEAM DRUM MOV VENTING REGULATING VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION & CALIBRATION STEAM DRUM CBD ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION & CALIBRATION STEAM DRUM MOV CBD REGULATING VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION & CALIBRATION STEAM DRUM IBD ISOLATION VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | INSPECTION & CALIBRATION STEAM DRUM MOV IBD REGULATING VALVE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0033 | DRUM LEVEL TRANSMITTER 20HAD10CL001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DRUM LEVEL TRANSMITTER 20HAD10CL002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DRUM LEVEL TRANSMITTER 20HAD10CL003 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DRUM PRESSURE TRANSMITTER 20HAD10CP002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DRUM PRESSURE TRANSMITTER 20HAD10CP003 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0033 | DRUM PRESSURE TRANSMITTER 20HAD10CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | COMBUSTER ASH DRAIN 1 (BED ASH COOLER DRAIN) MOV 20HHC01AA001 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0039 | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 20HHC01AA002 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0039 | ACTUATOR BED MATERIAL DISCHARGE GATE VALVE 20ETG31AA01 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0039 | COMBUSTOR LOWER PRESSURE TRANSMITTER 20HHC01CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CP102 : UNIT 2 COMBUSTOR DP WITH GRATE 20HHC01CP011 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CP103 : UNIT 2 COMBUSTOR UPPER DP 20HHC01CP012 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | AIR COMBUSTOR AT LEVEL PRES TRANSMITTER 20HHC01CP060 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CT101 : UNIT 2 COMBUSTOR LOWER TEMP 20HHC01CT011 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CT102 : UNIT 2 COMBUSTOR LOWER TEMP 20HHC01CT012 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CT103 : UNIT 2 COMBUSTOR LOWER TEMP 20HHC01CT013 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CT104 : UNIT 2 COMBUSTOR MIDDLE TEMP 20HHC01CT041 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CT105 : UNIT 2 COMBUSTOR MIDDLE TEMP 20HHC01CT042 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | MSW20HHC10CT106 : UNIT 2 COMBUSTOR MIDDLE TEMP 20HHC01CT043 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | INLET BACKPASS PRESSURE TRANSMITTER 20HBK01CP003 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | INLET BACKPASS PRESSURE TRANSMITTER 20HBK01CP002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | INLET BACKPASS PRESSURE TRANSMITTER 20HBK01CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | BACKPASS PRESSURE AFTER LT SH TRANSMITTER 20HBK01CP030 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0039 | BACKPASS PRESSURE AFTER ECO TRANSMITTER 20HBK01CP050 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0040 | MSW20HDF10CP102 : UNIT 2 BACKPASS INLET PRESSURE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0040 | CYCLONE TO SEALPOT PRESSURE TRANSMITTER 20HDF01CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0040 | MSW20HDF10CT101 : UNIT 2 BACKPASS INLET TEMPERATURE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0040 | MSW20HDF10CT102 : UNIT 2 CYCLONE OUTLET TEMP 20HNA01CT001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0040 | MSW20HDF10CT103 : UNIT 2 BACKPASS INLET TEMPERATURE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0040 | MSW20HDF10CT104 : UNIT 2 CYCLONE INLET TEMPERATURE | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0041 | ACTUATOR DAMPER SEALPOT BLOWER 1 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0041 | ACTUATOR DAMPER SEALPOT BLOWER 2 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0041 | CALIBRATION PRESSURE TRANSMITTER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0041 | CALIBRATION TEMPERATURE TRANSMITTER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0042 | ERV PRESSURE SWITCH 20LBA20CP502 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | INSPECTION AND CALIBRATION TEMP TRANSMITTER 20LBA10CT001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | INSPECTION AND CALIBRATION TEMP TRANSMITTER 20LBA10CT002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | INSPECTION AND CALIBRATION TEMP TRANSMITTER 20LBA10CT003 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | ACTUATOR MAIN STEAM LINE (START UP BYPASS) TO DEAERATOR PRDS I/L CV 20LBH10AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0042 | MS START-UP VENT VALVE (REGULATING) MOV 20LBA21AA011 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0042 | MS START-UP VENT VALVE (ISOLATION) MOV 20LBA21AA001 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0042 | MAIN STEAM LIVE PRESSURE TRANSMITTER 20LAB10CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | MAIN STEAM LIVE PRESSURE TRANSMITTER 20LAB10CP002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | MAIN STEAM LIVE PRESSURE TRANSMITTER 20LAB10CP003 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | INSPECTION AND CALIBRATION FLOW TRANSMITTER 20LBA10CF001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0042 | INSPECTION AND CALIBRATION FLOW TRANSMITTER 20LBA10CF002 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0043 | MSW20MAV10-M101 : UNIT 2 JACKING OIL PUMP MOTOR | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0043 | MSW20MAV10CP101 : UNIT 2 JACKING OIL PRESSURE TRANSMITTER | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0044 | INSPEKSI & PM OIL PUMP MOTOR ( AUXILIARY, EMERGENCY, JACKING, BREATHER ) | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0044 | INSPECTION AND CALIBRATION LUB OIL PRESSURE TRANSMITTER 20MAV40CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0044 | INSPECTION AND CALIBRATION LUB OIL PRESSURE TRANSMITTER 20MAV40CP002 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0044 | INSPECTION AND CALIBRATION LUB OIL PRESSURE TRANSMITTER 20MAV40CP003 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP001) | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP002) | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | VALVE POSITION BLOCK LIVE STEAM PT (20MAX45CP003) | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | VALVE BLOCK - OUTLET POSITION LIVE STEAM PT (20MAX45CP004) | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | CONTROL OIL PRESSURE PT (20MAX40CP001) | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | VALVE CHEST TEMPERATURE TRANSMITTER 20MAA10CT011 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-180726-0045 | LIVE STEAM PRESSURE TRANSMITTER 20LBA10CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | CALIBRATION/FUNCTION TEST CONTROL VALVE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0046 | CALIBRATION/FUNCTION TEST HP BYPASS CONTROL VALVE 20LBF10AA210 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0046 | HP BYPASS TEMPERATURE TRANSMITTER 20LBF10CT001 | 31/08/2026 | MSW | TRUE |  |  | 0
WO-180726-0046 | BYPASS PRESSURE TRANSMITTER 20MAG10CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0046 | MSW20LBF10CG101 : UNIT 2 STEAM BYPASS REDUCING CONTROL VALVE PRESSURE TRANSMITTER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0046 | MSW20LBF10CP101 : UNIT 2 STEAM BYPASS REDUCING PRESSURE TRANSMITTER 20LBF10CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0046 | MSW20LBF10CT101 : UNIT 2 STEAM BYPASS REDUCING TEMPERATURE TRANSMITTER | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0047 | DRAIN OF ESV 20MAL10AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0047 | DRAIN OF CV CHAMBER 20MAL20AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0047 | TURBINE DRAIN VALVE AFTER FIRST STAGE 20MAL30AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0047 | TURBINE DRAIN VALVE 20MAL40AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0047 | TURBINE DRAIN VALVE 20MAL50AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0047 | TURBINE DRAIN VALVE 20MAL60AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0047 | TURBINE DRAIN VALVE 20MAL70AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0048 | MSW20MAJ10-M102 : UNIT 2 VACUUM PUMP A MOTOR (MEGGER, INSPEKSI TERMINAL BLOK, And SISTEM COOLING MOTOR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0048 | DISCHARGE, SUCTION & VENTING VALVE VACUUM PUMP-1 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0048 | MSW20MAJ10AA101 : UNIT 2 AIR REMOVAL SYSTEM VACUUM BREAKER SOLENOID VALVE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0048 | MSW20MAJ10CG101 : UNIT 2 AIR REMOVAL SYSTEM POSITION TRANSMITTER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0049 | MSW20MAJ10-M202 : UNIT 2 VACUUM PUMP B MOTOR (MEGGER, INSPEKSI TERMINAL BLOK, And SISTEM COOLING MOTOR) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0049 | DISCHARGE, SUCTION & VENTING VALVE VACUUM PUMP-2 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0049 | MSW20MAJ10AA201 : UNIT 2 AIR REMOVAL SYSTEM VACUUM BREAKER SOLENOID VALVE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0049 | MSW20MAJ10CG201 : UNIT 2 AIR REMOVAL SYSTEM POSITION TRANSMITTER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0050 | MSW20MAG10CP103 : UNIT 2 CONDENSER BYPASS PRESSURE TRANSMITTER 20MAG10CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0050 | COOLING WATER SUPPLY TEMPERATURE TRANSMITTER 20PAB11CT001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0050 | COOLING WATER SUPPLY TEMPERATURE TRANSMITTER 20PAB12CT001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0050 | COOLING WATER RETURN TEMPERATURE TRANSMITTER 20PAB21CT001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0050 | COOLING WATER RETURN TEMPERATURE TRANSMITTER 20PAB22CT001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0051 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | INSPECTION TERMINASI | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | CALIBRATION LIMIT SWITCH | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0051 | PRESSURE TRANSMITTER CONDENSATE PUMP TO DELIVERY 20LCA30CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0051 | ACTUATOR CONDENSATE PUMP RECIRCULATION CONTROL VALVE 20LCA31AA210 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0051 | ACTUATOR MAIN CONDENSATE CONTROL VALVE 20LCA30AA240 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0051 | CEP DISCHARGE ISOLATION VALVE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0052 | INSPECTION FRAME MOTOR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | REGREASING (JIKA DILENGKAPI NIPPLE GREASE) | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | INSULATION RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | INSPECTION COOLING FAN | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | WINDING RESISTANCE INSPECTION | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | INSPECTION TERMINASI | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | INSPECTION KONEKSI GROUNDING SYSTEM | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | CALIBRATION LIMIT SWITCH | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0052 | CEP DISCHARGE ISOLATION VALVE | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | FREQUENCY PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | GENERATOR DIFFERENTIAL PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | SHORT CIRCUIT PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | OVERCURRENT PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | OVERVOLTAGE PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | ROTOR EARTH FAULT PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | STATOR EARTH FAULT PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | REVERSE POWER PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | UNDER EXCITATION PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | OVER EXCITATION PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | NEGATIVE SEQUENCE PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | OVERLOAD PROTECTION TEST | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0053 | CLEANING AND TIGHTENING | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0054 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE PANEL | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0054 | MEMBERSIHKAN FILTER PANEL | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0054 | PEMELIHARAAN FAN CONVERTER UNITROL | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0054 | MEMBERSIHKAN KOMPARTEMEN DALAM PANEL | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0054 | HOUSEKEEPING | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 1 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 2 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 3 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 4 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 5 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 6 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 7 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 8 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 9 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 10 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | CLEANING, INSPECTION, & REGREASING ALL SOOT BLOWER MOTOR 11 | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0055 | SOOT BLOWER STEAM OUTLET TRANSMITTER 20HCB10CP001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0055 | SOOT BLOWER STEAM FLOW TRANSMITTER 20HCB10CF001 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0055 | ACTUATOR VALVE DRAIN SOOT BLOWER 20HCB10AA201 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0055 | SOOT BLOWER VALVE MOV 20HCB10AA001 | 2026-07-21 00:00:00 | AMP | TRUE |  |  | 0
WO-180726-0055 | ACTUATOR SOOT BLOWER CONTROL VALVE 20HCB10EX001 | 2026-07-21 00:00:00 | MSW | TRUE |  |  | 0
WO-180726-0056 | PM PC OWS | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0056 | PM PC EWS | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0056 | PM panel RIO | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0057 | INSPEKSI LV TRANSFORMER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | RDC Test LV TRANSFORMER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | FUNGSI RACK OUT RACK IN | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN BUSBAR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | BUSBAR INSULATION RESISTANCE TEST *)including busbar and busduct | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | BUSBAR CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN KABEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN TRAFO KONTROL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN SOOTBLOWER MCC FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN TG MCC FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN KOMPARTEMEN ADAPTER PANEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | BUSTIE BUSDUCT CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN ACB INCOMMING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INCOMING ACB INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INCOMING ACB CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | CB ANALYSIS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN ACB ESP FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | ESP FEEDER ACB INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | ACB CONTACT RESISTANCE TEST ESP FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | ESP FEEDER CB ANALYSIS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN ACB BOILER FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | ACB CONTACT RESISTANCE TEST BOILER FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | BOILER FEEDER CB ANALYSIS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | PERAWATAN ACB COOLING TOWER MCC FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | COOLING TOWER FEEDER ACB INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | ACB CONTACT RESISTANCE TEST COOLING TOWER FEEDER | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | COOLING TOWER FEEDER CB ANALYSIS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INSPECTION HEATER BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INSPECTION BOLT BUSBAR, FLANGE & INSPECTION HOLE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INSPECTION SILICA BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | CHECK BUSDUCT LEAKAGE AND MOISTURE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INSPECTION CONTACT RESISTANCE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | INSPECTION ISOLATION RESISTANCE BUSDUCT | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0057 | HOUSEKEEPING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | PERAWATAN KOMPARTEMEN BUSBAR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | BUSBAR INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | BUSBAR CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | PERAWATAN KOMPARTEMEN KABEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | PERAWATAN MODULE WITHDRAWABLE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | PERAWATAN ACB INCOMMING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | INCOMING ACB INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | ACB CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | CB ANALYSIS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0058 | HOUSEKEEPING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | PERAWATAN KOMPARTEMEN BUSBAR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | BUSBAR INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | BUSBAR CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | PERAWATAN KOMPARTEMEN KABEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | PERAWATAN MODULE WITHDRAWABLE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0059 | HOUSEKEEPING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | PERAWATAN BAGIAN EXTERNAL ENCLOSURE MCC | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | PERAWATAN KOMPARTEMEN BUSBAR | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | BUSBAR INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | BUSBAR CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | PERAWATAN KOMPARTEMEN KABEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | PERAWATAN KOMPARTEMEN MARSHALLING PANEL | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | PERAWATAN MODULE WITHDRAWABLE | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | PERAWATAN ACB INCOMMING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | INCOMING ACB INSULATION RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | INCOMING ACB CONTACT RESISTANCE TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | CB ANALYSIS TEST | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0060 | HOUSEKEEPING | 2026-07-21 00:00:00 | JAPA | TRUE |  |  | 0
WO-180726-0061 | GLAND STEAM CONDENSER VENTING MOTOR | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0061 | GLAND STEAM PRESSURE TRANSMITTER 20MAW11CP001 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0061 | ACTUATOR GLAND STEAM PRESSURE CONTROL VALVE 20MAW10AA210 | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0061 | ACTUATOR GLAND STEAM TEMPERATURE CONTROL VALVE 20LCE10AA210 | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0061 | GENERAL CLEANING | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0142 | INSPECTION AND CALIBRATION OXYGEN ANALYZER | 2026-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0142 | INLET BACKPASS PRESSURE TRANSMITTER | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0142 | INLET BACKPASS PRESSURE TRANSMITTER | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0142 | INLET BACKPASS PRESSURE TRANSMITTER | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0142 | BACKPASS PRESSURE AFTER LT SH TRANSMITTER | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0142 | BACKPASS PRESSURE AFTER ECO TRANSMITTER | 31/08/2026 |  | TRUE |  |  | 0
WO-180726-0062 | Panel Bapcon - Rapcon Field 1 | 2025-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0062 | Panel Bapcon - Rapcon Field 2 | 2025-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0062 | Panel Bapcon - Rapcon Field 3 | 2025-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0062 | Panel Bapcon - Rapcon Field 4 | 2025-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0062 | Panel Bapcon - Rapcon Field 5 | 2025-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0062 | Panel Bapcon - Rapcon Field 6 | 2025-07-21 00:00:00 |  | TRUE |  |  | 0
WO-180726-0027 | ACTUATOR DESH-1 SPRAY WATER ISOLATION |  | AMP | TRUE |  |  | 0
WO-180726-0028 | ACTUATOR DESH-2 SPRAY WATER ISOLATION |  | AMP | TRUE |  |  | 0
WO-180726-0009 | ACTUATOR MOV OUTLET PA FAN 1 |  | AMP | TRUE |  |  | 0
WO-180726-0009 | ACTUATOR MOV PA FAN 1 |  | AMP | TRUE |  |  | 0
WO-180726-0024 | ACTUATOR ISOLATION STARTUP VENTING BOILER |  | MSW | TRUE |  |  | 0
WO-180726-0015 | ACTUATOR IGV SA FAN 2 20HLB02EX001 |  | MSW | TRUE |  |  | 0
WO-180726-0039 | FLUIDIZING VALVE BED MATERIAL |  | MSW | TRUE |  |  | 0
WO-180726-0039 | FLUIDIZING VALVE LIMESTONE 1&2 |  | MSW | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR STEAM DRUM VENTING ISOLATION VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR STEAM DRUM MOV VENTING VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR STEAM DRUM CBD ISOLATION VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR STEAM DRUM MOV CBD CONTROL VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR STEAM DRUM IBD ISOLATION VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0033 | ACTUATOR STEAM DRUM MOV IBD CONTROL VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0024 | ACTUATOR MOV PA FAN2 |  | MSW | TRUE |  |  | 0
WO-180726-0013 | ACTUATOR MOV OUTLET SA FAN 1 |  | MSW | TRUE |  |  | 0
WO-180726-0046 | ACTUATOR BYPASS SPRAY CONTROL VALVE 20LCE40AA210 |  | MSW | TRUE |  |  | 0
WO-180726-0045 | CEP DISCHARGE VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0045 | ACTUATOR ON/OFF NRV STEAM EXTRACTION 1, 2, 3 |  | MSW | TRUE |  |  | 0
WO-180726-0051 | ACTUATOR ON/OFF VALVE CEP-1 & CEP-2 |  | MSW | TRUE |  |  | 0
WO-180726-0026 | ACTUATOR MOV INLET ECONOMIZER |  | MSW | TRUE |  |  | 0
WO-180726-0026 | ACTUATOR MOV RECIRCULATION ECONOMIZER |  | MSW | TRUE |  |  | 0
WO-180726-0028 | 20HAH36CT0010: TEMPERATURE BEFORE DESH 2 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0027 | 20HAH46CT010: TEMPERATURE AFTER DESH 1 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0007 | 20HNA11CT001: CYCLONE OUTLET TEMPERATURE | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0045 | 20LBS10CT001: STGE EXTRACTION I TO LPH1 TEMP | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0019 | 20HJF13CP302: LDO PRESSURE LOW TRIP FOR LANCES | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0019 | 20HJF13CP303: LDO PRESSURE HIGH TRIP FOR LANCES | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0024 | 20HJG89CP301: LPG GAS PRESSURE BEFORE MTV | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0024 | 20LAC20CP101: DP SWITCH BFP 1 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0025 | 20LAC30CP101: DP SWITCH BFP 2 | 31/08/2026 | JAPA | TRUE |  |  | 0
WO-180726-0027 | ACTUATOR DESH-1 SPRAY WATER CONTROL VALVE |  | AMP | TRUE |  |  | 0
WO-180726-0045 | MOV DISCHARGE BFP-1 |  | AMP | TRUE |  |  | 0
WO-180726-0055 | SOOT BLOWER CONTROL VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0045 | ACTUATOR MOV TURBINE STOP VALVE |  | MSW | TRUE |  |  | 0
WO-180726-0019 | 20HJN13CP302: ATOM AIR PRESSURE LOW TRIP FOR LANCES | 31/08/2026 | JAPA | TRUE |  |  | 0

## ActuatorValve
Equipment_ID | Area | Equipment_Description | KKS | Unit | PIC | Status | Progress_Percent | Finish_Date | General_Inspection_TRUE_FALSE | Function_Test_TRUE_FALSE | Remarks | Findings | Action_Taken | Photo_Count | No_WO
AV-001 | BOILER | ACTUATOR FEED WATER CONTROL VALVE 100% 20LAB30AA220 | 20LAB30AA220 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0026
AV-002 | BOILER | ACTUATOR FEED WATER CONTROL VALVE 30% 20LAB30AA210 | 20LAB30AA210 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0026
AV-003 | BOILER | ACTUATOR DESH-1 SPRAY WATER ISOLATION |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0027
AV-004 | BOILER | ACTUATOR DESH-1 SPRAY WATER CONTROL VALVE |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0027
AV-005 | BOILER | ACTUATOR DESH-2 SPRAY WATER ISOLATION |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0027
AV-006 | BOILER | ACTUATOR DESH-2 SPRAY WATER CONTROL VALVE |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0027
AV-007 | BOILER | ACTUATOR FUEL COAL GATE VALVE 1 (MFT-1) 20HHE11AA01 | 20HHE11AA01 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0017
AV-008 | BOILER | ACTUATOR FUEL COAL GATE VALVE 2 (MFT-2) 20HHE12AA01 | 20HHE12AA01 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0018
AV-009 | ID FAN | ACTUATOR IGV ID FAN 1 20HNC01EX001 | 20HNC01EX001 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0007
AV-010 | ID FAN | ACTUATOR IGV ID FAN 2 20HNC01EX002 | 20HNC01EX002 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0008
AV-011 | ID FAN | ACTUATOR INLET ID FAN 1 MOV 20HNA61AA001 | 20HNA61AA001 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0007
AV-012 | ID FAN | ACTUATOR INLET ID FAN 2 MOV 20HNA62AA001 | 20HNA62AA001 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0008
AV-013 | ID FAN | ACTUATOR OUTLET ID FAN 1 MOV 20HNA71AA001 | 20HNA71AA001 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0007
AV-014 | ID FAN | ACTUATOR OUTLET ID FAN 2 MOV 20HNA72AA001 | 20HNA72AA001 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0008
AV-015 | PA FAN | ACTUATOR MOV OUTLET PA FAN 1 |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0009
AV-016 | PA FAN | ACTUATOR MOV PA FAN 1 |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0009
AV-017 | STG | BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L MOV 20LAE10AA110 | 20LAE10AA110 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0026
AV-018 | STG | ACTUATOR MAIN STEAM LINE (START UP BYPASS) TO DEAERATOR PRDS I/L CV 20LBH10AA210 | 20LBH10AA210 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE | Spring Patah |  |  | 0 | WO-180726-0042
AV-019 | STG | ACTUATOR BFP SPRAY LINE (FEED WATER) TO DEAERATOR PRDS I/L CV 20LAE10AA210 | 20LAE10AA210 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0026
AV-020 | STG | ACTUATOR TURBINE EXTRACTION III TO DEAERATOR CV 20LBD20AA210 | 20LBD20AA210 | 2 | AMP | FINISH | 100 |  | TRUE | TRUE | Seat Valvenya terangkat tdk duduk di body valvenya sehingga menghalangi pergerakan stem menuju close. Yg mmbuat seat valve terangkat krna threadnya loss/dol. |  |  | 0 | WO-180726-0033
AV-021 | STG | MOV DISCHARGE BFP-1 |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0024
AV-022 | STG | MOV DISCHARGE BFP-2 |  | 2 | AMP | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0025
AV-023 | BOILER | ACTUATOR ISOLATION STARTUP VENTING BOILER |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0024
AV-024 | BOILER | ACTUATOR IGV SA FAN 1 20HLB01EX001 | 20HLB01EX001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0013
AV-025 | BOILER | ACTUATOR IGV SA FAN 2 20HLB02EX001 | 20HLB02EX001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0015
AV-026 | BOILER | ACTUATOR IGV SA CONTROL DAMPER 20HLA25AA010 | 20HLA25AA010 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-027 | BOILER | ACTUATOR IGV SUB 1 20HJL10AA010 | 20HJL10AA010 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | Leakage on cylinder shaft affecting valve opening |  |  | 0 | WO-180726-0033
AV-028 | BOILER | ACTUATOR IGV SUB 2 20HJL11AA010 | 20HJL11AA010 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | Cylinder shaft heavy during initial opening from 0%-25% |  |  | 0 | WO-180726-0033
AV-029 | BOILER | ACTUATOR BED MATERIAL DISCHARGE GATE VALVE 20ETG31AA01 | 20ETG31AA01 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-030 | BOILER | ACTUATOR VALVE DRAIN SOOT BLOWER 20HCB10AA201 | 20HCB10AA201 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0055
AV-031 | BOILER | COMBUSTER ASH DRAIN 1 (BED ASH COLLER DRAIN) MOV 20HHC01AA001 | 20HHC01AA001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-032 | BOILER | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 20HHC01AA002 | 20HHC01AA002 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-033 | BOILER | SOOT BLOWER CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0055
AV-034 | BOILER | SOOT BLOWER ISOLATION VALVE MOV 20HCB10AA001 | 20HCB10AA001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0055
AV-035 | BOILER | MS START UP VENT VALVE (REG) MOV 20LBA21AA011 | 20LBA21AA011 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0042
AV-036 | BOILER | MS START UP VENT VALVE (ISO) MOV 20LBA21AA001 | 20LBA21AA001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0042
AV-037 | BOILER | ACTUATOR SOOT BLOWER CV 20HCB10EX001 | 20HCB10EX001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0055
AV-038 | BOILER | ACTUATOR DAMPER SEALPOT BLOWER 1 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0041
AV-039 | BOILER | ACTUATOR DAMPER SEALPOT BLOWER 2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0041
AV-040 | BOILER | COMBUSTER ASH DRAIN 1 (BED ASH COLLER DRAIN) MOV 10HHC01AA001 | 10HHC01AA001 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-041 | BOILER | COMBUSTER ASH DRAIN 2 (EMERGENCY ASH DRAIN) MOV 10HHC01AA002 | 10HHC01AA002 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-042 | BOILER | FLUIDIZING VALVE BED MATERIAL |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-043 | BOILER | FLUIDIZING VALVE LIMESTONE 1&2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0039
AV-044 | DRUM | ACTUATOR STEAM DRUM VENTING ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-045 | DRUM | ACTUATOR STEAM DRUM MOV VENTING VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-046 | DRUM | ACTUATOR STEAM DRUM CBD ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-047 | DRUM | ACTUATOR STEAM DRUM MOV CBD CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-048 | DRUM | ACTUATOR STEAM DRUM IBD ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-049 | DRUM | ACTUATOR STEAM DRUM MOV IBD CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-050 | PA FAN | ACTUATOR MOV OUTLET PA FAN 2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0009
AV-051 | PA FAN | ACTUATOR MOV PA FAN2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0009
AV-052 | SA FAN | ACTUATOR MOV OUTLET SA FAN 1 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0009
AV-053 | SA FAN | ACTUATOR MOV OUTLET SA FAN 2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0009
AV-054 | STG | ACTUATOR HP BYPASS CONTROL VALVE 20LBF10AA210 | 20LBF10AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0046
AV-055 | STG | ACTUATOR CONDENSATE PUMP RECIRCULATION CONTROL VALVE 20LCA31AA210 | 20LCA31AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | Leakage found on Shaft Seal & Air lock relay |  |  | 0 | WO-180726-0051
AV-056 | STG | ACTUATOR MAIN CONDENSATE CONTROL VALVE 20LCA30AA240 | 20LCA30AA240 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0051
AV-057 | STG | ACTUATOR GLAND STEAM PRESSURE CONTROL VALVE 20MAW10AA210 | 20MAW10AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | Leakage also found on shaft seal-->Pending action |  |  | 0 | WO-180726-0061
AV-058 | STG | ACTUATOR GLAND STEAM TEMP. CONTROL VALVE 20LCE10AA210 | 20LCE10AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | -Diaphragm, yoke & accessories no leakage, several connectors leaking-->Resealedg (OK). |  |  | 0 | WO-180726-0061
AV-059 | STG | ACTUATOR BYPASS SPRAY CONTROL VALVE 20LCE40AA210 | 20LCE40AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0046
AV-060 | STG | CEP DISCHARGE VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0051
AV-061 | STG | DISCHARGE, SUCTION & VENTING VALVE VACUM PUMP-1 & 2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | discharge valve Vacum Pump-1 bocor di SV, cover SV-nya retak. |  |  | 0 | WO-180726-0048
AV-062 | STG | MOV MAIN STEAM DRAIN STG-2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-063 | STG | DRAIN OF ESV 20MAL10AA210 | 20MAL10AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0047
AV-064 | STG | DRAIN OF CV CHAMBER 20MAL20AA210 | 20MAL20AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0047
AV-065 | STG | TURBINE DRAIN VALVE AFTER FIRST STAGE 20MAL30AA210 | 20MAL30AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0047
AV-066 | STG | TURBINE DRAIN VALVE 20MAL40AA210 | 20MAL40AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE | Air Regulator Valve no. 4 replaced with new unit. |  |  | 0 | WO-180726-0047
AV-067 | STG | TURBINE DRAIN VALVE 20MAL50AA210 | 20MAL50AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0047
AV-068 | STG | TURBINE DRAIN VALVE 20MAL60AA210 | 20MAL60AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0047
AV-069 | STG | TURBINE DRAIN VALVE 20MAL70AA210 | 20MAL70AA210 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0047
AV-070 | STG | CONTROL VALVE LPH-2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-071 | STG | CONTROL VALVE LPH-1 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-072 | STG | MOV TURBINE STEAM EXTRACTION-1 & 2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-073 | STG | ACTUATOR MOV TURBINE STOP VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-074 | STG | ACTUATOR MOV PREHEATING 1 TURBINE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-075 | STG | ACTUATOR MOV PREHEATING 2 TURBINE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0033
AV-076 | STG | ACTUATOR ON/OFF NRV STEAM EXTRACTION 1, 2, 3 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0045
AV-077 | STG | ACTUATOR ON/OFF VALVE CEP-1 & CEP-2 |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0051
AV-078 | SUB | ACTUATOR SUB BURNER 1 VALVE 20HJN11AA003 | 20HJN11AA003 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-079 | SUB | ACTUATOR SUB BURNER 2 VALVE 20HJN12AA003 | 20HJN12AA003 | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0020
AV-080 | SUB | ACTUATOR SKID BURNER MAIN LDO LINE CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-081 | SUB | ACTUATOR SKID BURNER 1 LDO LINE CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-082 | SUB | ACTUATOR SKID BURNER 1 ATOMISING AIR LINE CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-083 | SUB | ACTUATOR SKID BURNER 2 LDO LINE CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-084 | SUB | ACTUATOR SKID BURNER 2 ATOMISING AIR LINE CONTROL VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-085 | SUB | ACTUATOR SKID BURNER 1 ATOM AIR ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-086 | SUB | ACTUATOR SKID BURNER 1 LDO ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-087 | SUB | ACTUATOR SKID BURNER 1 SCAVENGING VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-088 | SUB | ACTUATOR SKID BURNER 2 ATOM AIR ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-089 | SUB | ACTUATOR SKID BURNER 2 LDO ISOLATION VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-090 | SUB | ACTUATOR SKID BURNER 2 SCAVENGING VALVE |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0019
AV-091 | BOILER | ACTUATOR MOV INLET ECONOMIZER |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0026
AV-092 | BOILER | ACTUATOR MOV RECIRCULATION ECONOMIZER |  | 2 | MSW | FINISH | 100 |  | TRUE | TRUE |  |  |  | 0 | WO-180726-0026

## Instrument_PressureTX
No | Area | Equipment | KKS | Unit | Range | Date | Status_WDONE_TRUE_FALSE | Remarks | Findings | Action_Taken | Photo_Count | Calibration_TRUE_FALSE | No_WO
1 | ESP | INLET ID FAN 2 | 20HNA62CP001 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0008
2 | ESP | INLET ID FAN 1 | 20HNA61CP001 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0007
3 | ESP | INLET PRESSURE ESP | 20HNA41CP001 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0007
4 | ESP | OUTLET PRESSURE ESP | 20HNA41CP002 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0007
5 | Boiler | AIR SUB1 FLOW DP | 20HJL10CF010 | 2 | 0-130mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
6 | Boiler | P.A APH OUTLET FLOW DP | 20HLA15CF001 | 2 | 0-130 mmH2O |  | TRUE |  |  |  | 0 |  | WO-180726-0033
7 | Boiler | P.A APH OUTLET FLOW DP | 20HLA15CF002 | 2 | 0.0-130.0 mmH2O |  | TRUE |  |  |  | 0 |  | WO-180726-0033
8 | Boiler | P.A APH OUTLET PRESSURE | 20HLA15CP001 | 2 | 0.0-350.0 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
9 | Boiler | ATOM AIR PRESSURE AFTER SUB 1 | 20HJN11CP001 | 2 | 0,7 - 14 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0019
10 | Boiler | ATOM AIR PRESSURE AFTER SUB 2 | 20HJN12CP001 | 2 | 0-14 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0020
11 | Boiler | LDO PRESS AFTER SUB2 FCV | 20HJF12CP001 | 2 | 0-20 bar |  | TRUE |  |  |  | 0 |  | WO-180726-0020
12 | Boiler | SEALPOT BLOWER PRESS OUTLET | 20HLB41CP001 | 2 | 0-1 bar |  | TRUE |  |  |  | 0 |  | WO-180726-0021
13 | Boiler | P&S BLOWER PRESS OUTLET | 20QEB20CP001 | 2 | 0-1500 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0021
14 | Boiler | LDO PRESS AFTER SUB1 FVC | 20HJF11CP001 | 2 | 0-20 bar |  | TRUE |  |  |  | 0 |  | WO-180726-0019
15 | Boiler | AIR SUB2 FLOW DP | 20HJL11CF010 | 2 | 0-130 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
16 | Boiler | COMBUSTOR LOWER PRESSURE | 20HHC01CP001 | 2 | 0.0 - 350 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
17 | Boiler | AIR COMBUSTOR AT LEVEL PRES | 20HHC01CP060 | 2 | 0 - 100 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
18 | Boiler | PA FAN 1 OUTLET PRESSURE | 20HLB03CP001 | 2 | 0-350 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0009
19 | Boiler | PA FAN 2 OUTLET PRESSURE | 20HLB04CP001 | 2 | 0-350 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0011
20 | Boiler | SA FAN 1 OUTLET PRESSURE | 20HLB01CP001 | 2 | 0-250 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0013
21 | Boiler | SA FAN 2 OUTLET PRESSURE | 20HLB02CP001 | 2 | 0-250 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0015
22 | Boiler | MAIN STEAM FLOW | 20LBA10CF001 | 2 | 0-12500 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0042
23 | Boiler | MAIN STEAM FLOW | 20LBA10CF002 | 2 | 0-12500 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0042
24 | Boiler | INLET FEEDWATER FLOW | 20HAC90CF001 | 2 | 0-5000 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0026
25 | Boiler | INLET FEEDWATER FLOW | 20HAC90CF002 | 2 | 0-5000 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0026
26 | Boiler | DISTRIBUTOR LINE TO FEEDWATER | 20LAB30CP001 | 2 | 0-180 bar |  | TRUE |  |  |  | 0 |  | WO-180726-0026
27 | Boiler | SA APH OUTLET FLOW | 20HLA25CF001 | 2 | 0-130 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
28 | Boiler | SA APH OUTLET FLOW | 20HLA25CF002 | 2 | 0 - 130 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
29 | Boiler | SA APH OUTLET PRESSURE | 20HLA25CP001 | 2 | 0-250 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
30 | Boiler | CYCLONE TO SEALPOT PRESSURE | 20HDF01CP001 | 2 | -39.00 - 196.00 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0040
31 | Boiler | DESH 1 SPRAY WATER FLOW | 20LAE20CF001 | 2 | 0.0 - 6700.0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0027
32 | Boiler | BACKPASS PRESSURE AFTER ECO | 20HBK01CP050 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
33 | Boiler | INLET FEEDWATER PRESSURE | 20HAC90CP001 | 2 | 0.00 - 160.00 bar |  | TRUE |  |  |  | 0 |  | WO-180726-0026
34 | Boiler | COMBUSTOR DP WITH GRATE | 20HHC01CP011 | 2 | 0 -250 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
35 | Boiler | COMBUSTOR UPPER DP | 20HHC01CP012 | 2 | -10 - 60 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
36 | Boiler | BACKPASS PRESSURE AFTER LT SH | 20HBK01CP030 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
37 | Boiler | DRUM LEVEL | 20HAD10CL001 | 2 | -910 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
38 | Boiler | DRUM LEVEL | 20HAD10CL002 | 2 | -910 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
39 | Boiler | DRUM LEVEL | 20HAD10CL003 | 2 | -910 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
40 | Boiler | SOOT BLOWER STEAM OUTLET | 20HCB10CP001 | 2 | 0 - 40 bar |  | TRUE |  |  |  | 0 |  | WO-180726-0055
41 | Boiler | SOOT BLOWER STEAM FLOW | 20HCB10CF001 | 2 | 30 - 35000 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0055
42 | Boiler | DESH 2 SPRAY WATER FLOW | 20LAE30CF001 | 2 | 16 - 6716 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0028
43 | Boiler | DRUM PRESSURE | 20HAD10CP002 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
44 | Boiler | DRUM PRESSURE | 20HAD10CP003 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
45 | Boiler | DRUM PRESSURE | 20HAD10CP001 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
46 | Boiler | MAIN STEAM LIVE PRESSURE | 20LAB10CP001 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0042
47 | Boiler | MAIN STEAM LIVE PRESSURE | 20LAB10CP002 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0042
48 | Boiler | MAIN STEAM LIVE PRESSURE | 20LAB10CP003 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0042
49 | Boiler | INLET BACKPASS PRESSURE | 20HBK01CP003 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
50 | Boiler | INLET BACKPASS PRESSURE | 20HBK01CP002 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
51 | Boiler | INLET BACKPASS PRESSURE | 20HBK01CP001 | 2 | -70 - 70 mbar |  | TRUE |  |  |  | 0 |  | WO-180726-0039
52 | STG | DEAERATOR PRDS TO OUTLET EXTRACTION | 20LBD11CP001 | 2 | 0 - 10 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
53 | STG | DEAERATOR PRDS TO OUTLET EXTRACTION II | 20LBD11CP002 | 2 | 0 - 10 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
54 | STG | FEEDWATER STORAGE TANK PRESSURE | 20LAA20CP001 | 2 | 0 - 10 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
55 | STG | LP HEATER 2 | 20LCC40CL001 | 2 | -500 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
56 | STG | LP HEATER 2 | 20LCC40CL002 | 2 | -500 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
57 | STG | CYCLE MAKE UP PUMP DEAERATOR | 20HGC20CF001 | 2 | 0 - 100 Kpa |  | TRUE |  |  |  | 0 |  | WO-180726-0033
58 | STG | DEAERATOR TANK LEVEL 1 | 20LAA20CL001 | 2 | -1750 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
59 | STG | DEAERATOR TANK LEVEL 2 | 20LAA20CL002 | 2 | -1750 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
60 | STG | DEAERATOR TANK LEVEL 3 | 20LAA20CL003 | 2 | -1750 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
61 | STG | TURBINE EXTRACTION III TO DEAERATOR PRESSURE | 20LBD20CP001 | 2 | 0 - 10 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
62 | STG | TURBINE EXTRACTION III TO LPH PRESSURE | 20LBD30CP001 | 2 | 0 - 4 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
63 | STG | LIVE STEAM PRESSURE TO BYPASS | 20LBF10CP001 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0046
64 | STG | TURBINE EXTRACTION 1 TO PNEUMATIC OPERATED VALVE | 20LBS10CP001 | 2 | 0 - 1 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
65 | STG | PRESSURE CONDENSATE PUMP TO DELIVERY | 20LCA30CP001 | 2 | 0 - 25 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0051
66 | STG | CONDENSATE TO LP HEATER | 20LCA40CF001 | 2 | 0 - 2500 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
67 | STG | CONDENSATE PRESSURE TO BYPASS SPRAY | 20LCE40CP001 | 2 | 0 -25 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
68 | STG | CONDENSATE PRESSURE TO BYPASS SPRAY | 20LCE40CP002 | 2 | 0 -25 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
69 | STG | CONDENSATE PRESSURE TO BYPASS SPRAY | 20LCE40CP003 | 2 | 0 -25 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
70 | STG | PRESSURE BEHIND TURBINE CONTROL | 20MAA10CP001 | 2 | -1 - 99 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
71 | STG | TURBINE EXHAUST PRESSURE | 20MAA10CP002 | 2 | -1 - 0.6 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
72 | STG | TURBINE EXHAUST PRESSURE | 20MAA10CP003 | 2 | -1 - 0.6 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
73 | STG | TURBINE EXHAUST PRESSURE | 20MAA10CP004 | 2 | -1 - 0.6 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
74 | STG | PRESSURE BEHIND TURBINE CONTROL STAGE | 20MAA10CP005 | 2 | -1 - 99 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0033
75 | STG | BYPASS PRESSURE | 20MAG10CP001 | 2 | -1 - 3 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0046
76 | STG | LUBRICATION OIL PRESSURE | 20MAV40CP001 | 2 | 0 - 4 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0044
77 | STG | LUBRICATION OIL PRESSURE | 20MAV40CP002 | 2 | 0 - 4 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0044
78 | STG | LUBRICATION OIL PRESSURE | 20MAV40CP003 | 2 | 0 - 4 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0044
79 | STG | GLAND STEAM PRESSURE | 20MAW11CP001 | 2 | 0 - 0.25 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0061
80 | STG | CONTROL OIL PRESSURE | 20MAX40CP001 | 2 | 0 - 16 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0045
81 | STG | VALVE POSITION BLOCK LIVE STEAM | 20MAX45CP001 | 2 | 0 - 16 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0045
82 | STG | VALVE POSITION BLOCK LIVE STEAM | 20MAX45CP002 | 2 | 0 - 16 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0045
83 | STG | VALVE POSITION BLOCK LIVE STEAM | 20MAX45CP003 | 2 | 1 - 16 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0045
84 | STG | LIVE STEAM PRESSURE | 20LBA10CP001 | 2 | 0 - 160 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0045
85 | STG | FLOW CONDESATE TO LP HEATER 1 | 20LCA40CF001 | 2 | 0 - 2500 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
86 | STG | LP HEATER 1 | 20LCC30CL001 | 2 | -500 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
87 | STG | LP HEATER 1 | 20LCC30CL002 | 2 | -500 - 0 mmH20 |  | TRUE |  |  |  | 0 |  | WO-180726-0033
88 | STG | VALVE BLOCK, OUTLET POSITION LIVE STEAM | 20MAX45CP004 | 2 | 0-16 Bar |  | TRUE |  |  |  | 0 |  | WO-180726-0045

## Instrument_TemperatureTX
No | Area | Equipment | KKS | Unit | Range | Finish_Date | Status_WDONE_TRUE_FALSE | Remarks | Findings | Action_Taken | Photo_Count | Calibration_TRUE_FALSE | No_WO
1 | BOILER | TEMPERATURE AFTER DESH 2 | 20HAH46CT001 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0028
2 | BOILER | TEMPERATURE BEFORE DESH 2 | 20HAH36CT009 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0028
3 | BOILER | TEMPERATURE BEFORE DESH 2 | 20HAH36CT0010 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0028
4 | BOILER | TEMPERATURE AFTER DESH 1 | 20HAH46CT010 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0027
5 | BOILER | CYCLONE OUTLET TEMPERATURE | 20HNA11CT001 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0007
6 | BOILER | CYCLONE OUTLET TEMPERATURE | 20HNA11CT002 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0007
7 | BOILER | CYCLONE OUTLET TEMPERATURE | 20HNA11CT003 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0007
8 | BOILER | COMBUSTOR MIDDLE TEMPERATURE | 20HHC01CT041 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0039
9 | BOILER | COMBUSTOR MIDDLE TEMPERATURE | 20HHC01CT042 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0039
10 | BOILER | COMBUSTOR MIDDLE TEMPERATURE | 20HHC01CT043 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0039
11 | BOILER | INLET CYCLONE | 20HNA01CT001 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0040
12 | BOILER | TEMPERATURE AFTER FINAL SH | 20LBA10CT001 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0042
13 | BOILER | TEMPERATURE AFTER FINAL SH | 20LBA10CT003 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0042
14 | BOILER | TEMPERATURE AFTER FINAL SH | 20LBA10CT002 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0042
15 | BOILER | COMBUSTOR LOWER TEMPERATURE | 20HHC01CT011 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0039
16 | BOILER | COMBUSTOR LOWER TEMPERATURE | 20HHC01CT012 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0039
17 | BOILER | COMBUSTOR LOWER TEMPERATURE | 20HHC01CT013 | 2 | 0-1200 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0039
18 | STG | FEEDWATER STORAGE TANK | 20LAA20CT001 | 2 | 0-150 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
19 | STG | LPH II - TUBE SIDE OUTLET TO DEAERATOR TEMP | 20LCC20CT001 | 2 | 0-150 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
20 | BOP | COOLING WATER SUPPLY TEMP | 20PAB11CT001 | 2 | 0-60 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0050
21 | BOP | COOLING WATER SUPPLY TEMP | 20PAB12CT001 | 2 | 0-60 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0050
22 | BOP | COOLING WATER RETURN TEMP | 20PAB21CT001 | 2 | 0-60 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0050
23 | BOP | COOLING WATER RETURN TEMP | 20PAB22CT001 | 2 | 0-60 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0050
24 | STG | VALVE CHEST TEMPERATURE | 20MAA10CT011 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0045
25 | STG | STGE CASING TEMPERATURE - INSIDE | 20MAA10CT012 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
26 | STG | STGE CASING TEMPERATURE - CENTER | 20MAA10CT013 | 2 | 0-600 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
27 | STG | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP | 20LBD11CT002 | 2 | 0-300 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
28 | STG | DEAERATOR PRDS OUTLET TO EXTRACTION I - DEAERATOR I/L TEMP | 20LBD11CT001 | 2 | 0-300 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
29 | STG | HP BYPASS TEMP | 20LBF10CT001 | 2 | 0-600 |  | TRUE |  |  |  | 0 |  | WO-180726-0046
30 | STG | STGE EXTRACTION II TO LPH2 TEMP | 20LBD30CT001 | 2 | 0-300 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
31 | STG | STGE EXTRACTION III TO DEAERATOR TEMP | 20LBD20CT001 | 2 | 0-300 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0033
32 | STG | STGE EXTRACTION I TO LPH1 TEMP | 20LBS10CT001 | 2 | 0-150 °C |  | TRUE |  |  |  | 0 |  | WO-180726-0045

## Instrument_PressureSwitch
No | Area | Description | KKS | Unit | Sub_Area | Set_Point | Contact_Type_NO_NC | AsFound_Set | AsFound_Reset | AsLeft_Set | AsLeft_Reset | Status_OK_NotOK | Status_WDONE_TRUE_FALSE | Dated | Finish_Date | Remarks | Findings | Action_Taken | Photo_Count | Calibration_TRUE_FALSE | No_WO
1 | BOILER | LDO PRESSURE BEFORE MTV | 20HJF11CP301 | 2 | SUB 1 | 8 Bar | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
2 | BOILER | ATOM AIR INKET PRESSURE LOW | 20HJN11CP301 | 2 | SUB 1 | 5.0 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
3 | BOILER | LDO PRESSURE LOW TRIP FOR SUB 1 | 20HJF11CP302 | 2 | SUB 1 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
4 | BOILER | ATOM AIR PRESSURE LOW TRIP FOR SUB 1 | 20HJN11CP302 | 2 | SUB 1 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
5 | BOILER | LDO PRESSURE HIGH TRIP FOR SUB 1 | 20HJF11CP303 | 2 | SUB 1 | 13.0 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
6 | BOILER | LDO PRESSURE LOW TRIP FOR SUB 2 | 20HJF12CP302 | 2 | SUB 2 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0020
7 | BOILER | ATOM AIR PRESSURE LOW TRIP FOR SUB 2 | 20HJN12CP302 | 2 | SUB 2 | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0020
8 | BOILER | LDO PRESSURE HIGH TRIP FOR SUB 2 | 20HJF12CP303 | 2 | SUB 2 | 13.0 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0020
9 | BOILER | LDO PRESSURE LOW TRIP FOR LANCES | 20HJF13CP302 | 2 | Lower Burner | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
10 | BOILER | ATOM AIR PRESSURE LOW TRIP FOR LANCES | 20HJN13CP302 | 2 | Lower Burner | 2.5 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
11 | BOILER | LDO PRESSURE HIGH TRIP FOR LANCES | 20HJF13CP303 | 2 | Lower Burner | 13.0 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
12 | BOILER | LPG GAS PRESSURE BEFORE MTV | 20HJG89CP301 | 2 | SUB | 1.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0024
13 | BOILER | SCANNER AIR PRESSURE OK 1 | 20HJG69CP301 | 2 | SUB | 0.6 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
14 | BOILER | SCANNER AIR PRESSURE OK 2 | 20HJG69CP302 | 2 | SUB | 2.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0019
15 | BOILER | LO HEADER PRESSURE LOW ALARM FOR PA FAN-1 | 20HLB01CP104 | 2 | PA Fan 1 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0010
16 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-1 START | 20HLB01CP103 | 2 | PA Fan 1 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0010
17 | BOILER | PRESSURE SWITCH TO START LO PA FAN-1 STANDBY PUMP | 20HLB01CP102 | 2 | PA Fan 1 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0010
18 | BOILER | DP SWITCH ACRROS LO TANK FOR PA FAN-1 | 20HLB01CP101 | 2 | PA Fan 1 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0010
19 | BOILER | LO HEADER PRESSURE LOW ALARM FOR PA FAN-2 | 20HLB02CP104 | 2 | PA Fan 2 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0012
20 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR PA FAN-2 START | 20HLB02CP103 | 2 | PA Fan 2 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0012
21 | BOILER | PRESSURE SWITCH TO START LO PA FAN-2 STANDBY PUMP | 20HLB02CP102 | 2 | PA Fan 2 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0012
22 | BOILER | DP SWITCH ACRROS LO TANK FOR SA FAN-1 | 20HLB02CP101 | 2 | PA Fan 2 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0014
23 | BOILER | LO HEADER PRESSURE LOW ALARM FOR SA FAN-1 | 20HLB05CP104 | 2 | SA Fan 1 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0014
24 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-1 START | 20HLB05CP103 | 2 | SA Fan 1 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0014
25 | BOILER | PRESSURE SWITCH TO START LO SA FAN-1 STANDBY PUMP | 20HLB05CP102 | 2 | SA Fan 1 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0014
26 | BOILER | DP SWITCH ACRROS LO TANK FOR SA FAN-1 | 20HLB05CP101 | 2 | SA Fan 1 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0014
27 | BOILER | LO HEADER PRESSURE LOW ALARM FOR SA FAN-2 | 20HLB06CP104 | 2 | SA Fan 2 | 0.4 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0016
28 | BOILER | PRESSURE SWITCH TO START PERMISSIVE FOR SA FAN-2 START | 20HLB06CP103 | 2 | SA Fan 2 | 0.8 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0016
29 | BOILER | PRESSURE SWITCH TO START LO SA FAN-2 STANDBY PUMP | 20HLB06CP102 | 2 | SA Fan 2 | 0.6 Kg/Cm2 | NC |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0016
30 | BOILER | DP SWITCH ACRROS LO TANK FOR SA FAN-2 | 20HLB06CP101 | 2 | SA Fan 2 | 0.5 Kg/Cm2 | NO |  |  |  |  | OK | TRUE | [5 empty] | 0 |  | WO-180726-0016
31 | STG | DP SWITCH BFP 1 | 20LAC20CP101 | 2 | BFP 1 | 0.5 Bar | NO | [5 empty] | TRUE | [5 empty] | 0 |  | WO-180726-0024
32 | STG | DP SWITCH BFP 2 | 20LAC30CP101 | 2 | BFP 2 | 0.5 Bar | NO | [5 empty] | TRUE | [5 empty] | 0 |  | WO-180726-0025
33 | BOILER | ERV PRESSURE SWITCH | 20LBA20CP502 | 2 | ERV | 93 Bar | NO | [5 empty] | TRUE | [5 empty] | 0 |  | WO-180726-0042

## PIC_Scope_Master
Category | Equipment_Scope_Name | Scope_Type_Vendor_MSW | Work_Scope_ME_SI_SE | Activity_Description | PIC | Unit
| Coordinator (Progress monitoring & Report) : | Vendor | M Farhan / H Aidi |  |  | 2
| 1. Electric Generator 31,5 MW/11 kV | Vendor | ME | Insulation resistance measurement, polarization index (PI), winding resistance test, connection check, cooler inspection, excitation system check, PMG, ventilation duct cleaning, grounding check | M ZAINI | 2
| 2. Generator Trafo 40 MVA,11/66 kV | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M ZAINI | 2
| 3. MV Auxiliary Trafo 10 MVA,11/6.6 kV | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M ZAINI | 2
| 4. LV Auxiliary Trafo 2.5 MVA,6.6/0.4 kV | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M ZAINI | 2
| 5. ESP Rectifier Trafo 250 kW,380 VAC/70 kVDC | Vendor | ME | Insulation resistance test, breakdown voltage test, bushing cleaning, bolt retorquing, protection function test, transformer oil BDV check, grounding check | M IQBAL | 2
| 6. Panel MV Switchgear 6.6 kV | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 2
| 7. Panel LV PMCC 380 V | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 2
| 8.Panel MCC 380 V (Boiler,Turbin Generator, ESP,AHP) | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 2
| 9. Panel Generator CB | Vendor | ME | CB contact resistance test, close-open timing test, CB mechanical mechanism lubrication, grounding check | M ZAINI | 2
| Generator CB Panel 11 ME Voltage Transformer Replacement | Vendor | ME |  | H AIDI | 2
| 10. Generator Control Panel | Vendor | ME |  | M ZAINI | 2
| 11. Generator Exciter Panel | Vendor | ME |  | M ZAINI | 2
| 12. Panel Bapcon – Rapcon ESP | Vendor | ME |  | M IQBAL | 2
| 13. Panel Inverter LV motor | Vendor | ME |  | M ZAINI | 2
| 14. Panel Soft Starter/FCMA | Vendor | ME |  | H AIDI | 2
| 15. Relay Proteksi | Vendor | ME | Secondary Injection Test to verify relay tripping against time curve and current setting values, event recorder log verification | M ZAINI | 2
| 16. LV Motor 380 V | Vendor | SI | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | YOGA | 2
| 17. MV Motor 6.6 kV | Vendor | ME | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | H AIDI | 2
| BFP motor 2 NDE bearing oil leak repair | Vendor | ME |  | YOGA | 2
| 21. Remote Control Panel (RCP) | Vendor | ME |  | M ZAINI | 2
| 22. Busduct Trafo | Vendor | SI | INSULATION RESISTANCE TEST, kontak resistan bagian konduktor, grounding check | M IQBAL | 2
| 23. Busduct Generator | Vendor | SI | INSULATION RESISTANCE TEST, kontak resistan bagian konduktor, grounding check | M IQBAL | 2
| 24. MV Motor Cable 6.6 kV | Vendor | SI | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | M IQBAL | 2
| 25. LV Motor Cable 380 V | Vendor | SI | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and ventilation duct cleaning | M IQBAL | 2
| 26. Electrical Grounding | Vendor | SI | Visual inspection on connections and damage, tightening & cleaning, grounding resistance measurement and verification | YOGA | 2
| B. Instrument | Vendor |  |  |  | 2
| 1. Panel DCS | Vendor | SI | Physical inspection of panel (cleanliness, doors, locks, grounding), CPU/I/O/Power Supply LED indicators, panel temperature, and ensuring no active alarms or system faults. | JHON | 2
| 2. Pressure tx range -70~1500 mBar | Vendor | SI | Verification & Calibration | FERRYUS | 2
| 3. Pressure tx range -1~180 Bar | Vendor | SI | Verification & Calibration | FERRYUS | 2
| 4. Flow tx range -500~12500 mmH2O | Vendor | SI | Verification & Calibration | FERRYUS | 2
| 5. Temperature tx range 0 ~ 1200 celcius | Vendor | SI | Verification & Calibration | FERRYUS | 2
| C. Rotating | Vendor |  |  |  | 2
| Gland Steam Sealing Condenser | Vendor | ME | Insulation resistance measurement, polarization index (PI), connection check, visual body check, fan cover, and cable terminal tightening check. | H AIDI | 2
| Rotary coal Feeder 1 | Vendor | SE | Replace Motor & Gearbox | H AIDI | 2
| Rotary coal Feeder 2 | Vendor | SE | Replace Motor & Gearbox | H AIDI | 2
| D. Actuator Valve | Vendor |  |  |  | 2
| KSB MIL SPRAY WATER LINE CONTROL VALVE, FEED WATER 30% | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| KSB MIL SPRAY WATER LINE CONTROL VALVE, FEED WATER 100% | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| KSB MIL SPRAY WATER LINE CONTROL VALVE, DESUPERHEATER 1&2 | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| KSB MIL SPRAY WATER LINE CONTROL VALVE, DESUPERHEATER 1&2 | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| Deaerator KSB MOV Gate Valve 1-1/2'' | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| Deaerator KSB MOV 2'' | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| Forbes Marshall WCV PRDS CONTROL VALVE | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| Forbes Marshall PRDS CONTROL VALVE | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| MFT Boiler Coal Gate | Vendor | ME | GENERAL INSPECTION, modify chute drain with Isolation Valve | M TOHER | 2
| ID Fan Inlet Gate Valve (Valve+Penumatic Actuator) IGV | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| ID Fan Inlet Damper (Valve+Motorized) | Vendor | ME | GENERAL INSPECTION, Replace MOV | M TOHER | 2
| ID Fan Outlet Damper (Valve+Motorized) | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| HP BYPASS Control Valve (Valve+Actuator) | Vendor | ME | GENERAL INSPECTION | M TOHER | 2
| E. Turbine Major Outage | Vendor |  |  |  | 2
| Generator Bearing | Vendor | SE | Replace Motor & Gearbox | H AIDI | 2
| SI: Inspection | Vendor |  |  |  | 2
| ME: Minor | Vendor |  |  |  | 2
| SE: Major | Vendor |  |  |  | 2
| MSW SCOPE | MSW | Activity | MSW PIC |  | 2
| Unit 1 - GCB Panel Cooling Fan Blower replacement (Mx) | MSW | Replace | M ZAINI |  | 2
| PRESSURE SWITCH | MSW | Verification & Calibration | FERRYUS |  | 2
| ACTUATOR ON OFF VALVE | MSW | General Inspection | JHON |  | 2
| IGV CONTROL (SA, SUB) | MSW | General Inspection | JHON |  | 2
| GOVERNOR VALVE | MSW | General Inspection | JHON |  | 2
| ACTUATOR CONTROL VALVE | MSW | General Inspection | M TOHER |  | 2
| ACTUATOR MOTORIZED VALVE | MSW | General Inspection | M TOHER |  | 2
| PROTECTION TEST | MSW | Function test | JHON |  | 2
| LEVEL SWITCH | MSW | Verification & Function Test | FERRYUS |  | 2
| FIRE ALARM SYSTEM | MSW | Verification & Function Test | M TOHER |  | 2
A. Master PIC EIC | Job Scope FARHAN | MSW | ME/SI/SE | EIC Personnel | FARHAN | 2
A. Master PIC EIC | Job Scope DEDE | MSW | ME/SI/SE | EIC Personnel | DEDE | 2
A. Master PIC EIC | Job Scope ZAINI Y | MSW | ME/SI/SE | EIC Personnel | ZAINI Y | 2
A. Master PIC EIC | Job Scope MAJID | MSW | ME/SI/SE | EIC Personnel | MAJID | 2
A. Master PIC EIC | Job Scope AMP | MSW | ME/SI/SE | EIC Personnel | AMP | 2
A. Master PIC EIC | Job Scope MSW | MSW | ME/SI/SE | EIC Personnel | MSW | 2
A. Master PIC EIC | Job Scope JAPA | MSW | ME/SI/SE | EIC Personnel | JAPA | 2